## Budget 2025
ITM plan year 2024 | 1000
As of 18 Nov'24
IMM | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Total
OB Removal (KBcm) | 7619.4483 | 7224.3023 | 6870.0231 | 7815.9147 | 8233.4755 | 7596.8792 | 8769.11 | 8498.0492 | 8442.1757 | 8242.1086 | 7836.3005 | 7566.691 | 94714.4782 | Done
PAMA (WB) | 2904.786 | 2754.4503 | 2424.321 | 2767.1447 | 2927.6178 | 2460.4194 | 3157.9028 | 3107.2173 | 2899.6426 | 2829.8233 | 2690.1553 | 2609.1784 | 33532.659
PAMA (EB) | 4714.6622 | 4469.852 | 4445.7021 | 5048.77 | 5305.8577 | 5136.4598 | 5611.2072 | 5390.8319 | 5542.5331 | 5412.2853 | 5146.1452 | 4957.5126 | 61181.8192
ROM Production (Kton) | 550 | 545 | 550 | 550 | 550 | 550 | 622.5 | 637.5 | 637.5 | 637.5 | 637.5 | 632.5 | 7100
PAMA (WB) | 192.5 | 187.5 | 192.5 | 190 | 185 | 155 | 130 | 135 | 145 | 110 | 120 | 120 | 1862.5
PAMA (EB) | 345 | 345 | 345 | 347.5 | 352.5 | 382.5 | 480 | 490 | 480 | 515 | 505 | 500 | 5087.5
Fine Coal | 12.5 | 12.5 | 12.5 | 12.5 | 12.5 | 12.5 | 12.5 | 12.5 | 12.5 | 12.5 | 12.5 | 12.5 | 150
SR ROM Total | 13.8535 | 13.2556 | 12.491 | 14.2108 | 14.97 | 13.8125 | 14.0869 | 13.3303 | 13.2426 | 12.9288 | 12.2922 | 11.9631 | 13.3401
FC Product (Kton) | 541.75 | 536.75 | 541.75 | 551.75 | 551.75 | 551.75 | 635.75 | 637.75 | 637.75 | 637.75 | 637.75 | 637.75 | 7100
PAMA (WB) | 192.5 | 187.5 | 192.5 | 190 | 185 | 155 | 130 | 135 | 145 | 110 | 120 | 120 | 1862.5
PAMA (EB) | 345 | 345 | 345 | 349 | 354 | 384 | 493 | 490 | 480 | 515 | 505 | 505 | 5110
Fine Coal | 4.25 | 4.25 | 4.25 | 12.75 | 12.75 | 12.75 | 12.75 | 12.75 | 12.75 | 12.75 | 12.75 | 12.75 | 127.5
SR FC Total | 14.0645 | 13.4593 | 12.6812 | 14.1657 | 14.9225 | 13.7687 | 13.7933 | 13.325 | 13.2374 | 12.9237 | 12.2874 | 11.8647 | 13.3401
IMM-WB.HCV.LS | 154.9822 | 150.1922 | 153.4446 | 142.7318 | 131.892 | 90.2567 | 45.0528 | 60.1041 | 62.6233 | 73.6379 | 78.4656 | 85.4199 | 1228.8032
CV(GAR) | 6066.6995 | 6061.099 | 6072.9614 | 6113.1737 | 6106.3251 | 6216.0563 | 6397.4706 | 6374.5335 | 6369.463 | 6395.7374 | 6207.9868 | 6224.9984 | 6169.7769
TS | 0.79939 | 0.7996 | 0.80631 | 0.80238 | 0.79513 | 0.79814 | 0.80006 | 0.80071 | 0.80424 | 0.87778 | 0.89103 | 0.79705 | 0.8108
Ash | 8.5932 | 8.5723 | 8.4653 | 8.3497 | 8.4545 | 8.0612 | 8.0877 | 8.0139 | 8.0939 | 8.3113 | 8.6583 | 8.1212 | 8.3746
Moist | 8.4968 | 8.6036 | 8.5701 | 8.2959 | 8.436 | 8.1042 | 7.1125 | 7.0457 | 7.1276 | 7.1603 | 7.2147 | 7.5403 | 8.0403
TM | 13.5221 | 13.629 | 13.5955 | 13.3212 | 13.4614 | 13.1296 | 12.1378 | 12.0711 | 12.153 | 12.1857 | 12.24 | 12.5656 | 13.0657
IMM-WB.HCV.HS | 37.5178 | 37.3078 | 39.0554 | 47.2682 | 53.108 | 64.7433 | 84.9472 | 74.8959 | 82.3767 | 36.3621 | 41.5344 | 34.5801 | 633.6968
CV(GAR) | 5995.4058 | 6102.8668 | 6012.8803 | 5956.2491 | 5900.982 | 5903.8514 | 5953.1501 | 5935.2903 | 5994.0694 | 5972.607 | 5974.5067 | 5973.0938 | 5965.7827
TS | 2.4296 | 2.4051 | 2.5319 | 2.5966 | 2.6453 | 2.7647 | 2.7578 | 2.7055 | 2.6432 | 2.4887 | 2.3842 | 1.9722 | 2.579
Ash | 13.6503 | 13.0727 | 13.5362 | 14.1977 | 14.7482 | 14.5558 | 13.6829 | 14.4235 | 13.8303 | 13.8021 | 13.9633 | 13.2396 | 13.9606
Moist | 6.0447 | 6.0271 | 6.0381 | 6.067 | 6.0651 | 7.0545 | 6.8576 | 6.9141 | 7.1513 | 7.5031 | 7.5101 | 7.1237 | 6.744
TM | 11.07 | 11.0525 | 11.0635 | 11.0924 | 11.0904 | 12.0799 | 11.883 | 11.9395 | 12.1767 | 12.5284 | 12.5355 | 12.1491 | 11.7694
IMM-EB.MCV.LS | 3.3846 | 2.1986 | 2.3031 | 2.7672 | 1.8759 | 1.1106 | 0 | 0 | 0 | 0 | 0 | 0 | 13.6399
CV(GAR) | 5821.883 | 5816.4871 | 5824.2204 | 5826.2223 | 5821.6228 | 5824.0809 | 0 | 0 | 0 | 0 | 0 | 0 | 5822.4314
TS | 0.89813 | 0.89994 | 0.9013 | 0.90153 | 0.90292 | 0.90326 | 0 | 0 | 0 | 0 | 0 | 0 | 0.90072
Ash | 8.6642 | 8.6538 | 8.6424 | 8.5289 | 8.516 | 8.5015 | 0 | 0 | 0 | 0 | 0 | 0 | 8.5978
Moist | 11.333 | 11.3369 | 11.3693 | 11.3501 | 11.3996 | 11.3577 | 0 | 0 | 0 | 0 | 0 | 0 | 11.3544
TM | 16.333 | 16.3369 | 16.3693 | 16.3501 | 16.3996 | 16.3577 | 0 | 0 | 0 | 0 | 0 | 0 | 16.3544
IMM-EB.MCV.MS | 2.5219 | 7.2155 | 26.7201 | 6.3272 | 12.6302 | 4.8088 | 12.095 | 14.9981 | 83.6973 | 94.4006 | 71.3353 | 85.9656 | 422.7155
CV(GAR) | 6013.744 | 5958.5719 | 6011.5142 | 6033.7912 | 5987.1311 | 6002.8141 | 6036.2059 | 6005.6296 | 5996.4183 | 6012.5832 | 6026.6617 | 6027.4417 | 6013.6725
TS | 1.5719 | 1.5705 | 1.5645 | 1.5541 | 1.5514 | 1.5491 | 1.5706 | 1.5667 | 1.5493 | 1.5533 | 1.5598 | 1.5724 | 1.5595
Ash | 6.0748 | 6.1531 | 6.1792 | 5.1976 | 5.2946 | 5.2369 | 5.1053 | 5.3674 | 5.3569 | 5.1697 | 5.1649 | 5.301 | 5.3287
Moist | 10.1273 | 10.2338 | 10.5326 | 10.3526 | 10.7819 | 10.4813 | 10.3659 | 10.4684 | 10.4436 | 10.274 | 10.2404 | 9.9508 | 10.2792
TM | 15.1273 | 15.2338 | 15.5326 | 15.3526 | 15.7819 | 15.4813 | 15.3659 | 15.4684 | 15.4436 | 15.274 | 15.2404 | 14.9508 | 15.2792
IMM-EB.MCV.HS | 339.0935 | 335.5859 | 315.9768 | 339.9056 | 339.494 | 378.0807 | 480.905 | 475.0019 | 396.3027 | 420.5994 | 433.6647 | 419.0344 | 4673.6446
CV(GAR) | 5916.7973 | 5925.4345 | 5916.7949 | 5912.981 | 5924.7515 | 5924.6893 | 5904.2294 | 5885.0998 | 5912.8315 | 5911.5994 | 5931.5837 | 5905.9088 | 5914.4155
TS | 2.4966 | 2.3878 | 2.3758 | 2.4776 | 2.3743 | 2.3234 | 2.4258 | 2.4636 | 2.4167 | 2.4358 | 2.3206 | 2.4316 | 2.4107
Ash | 5.9843 | 5.6663 | 5.7801 | 5.6993 | 5.574 | 5.7147 | 5.7035 | 5.9277 | 5.6702 | 5.6371 | 5.5902 | 5.6939 | 5.72
Moist | 10.2836 | 10.5562 | 10.6838 | 10.4873 | 10.6898 | 10.7239 | 10.6197 | 10.5236 | 10.4781 | 10.4971 | 10.5525 | 10.6017 | 10.5582
TM | 15.2836 | 15.5562 | 15.6838 | 15.4873 | 15.6898 | 15.7239 | 15.6197 | 15.5236 | 15.4781 | 15.4971 | 15.5525 | 15.6017 | 15.5582
Fine Coal | 4.25 | 4.25 | 4.25 | 12.75 | 12.75 | 12.75 | 12.75 | 12.75 | 12.75 | 12.75 | 12.75 | 12.75 | 127.5
CV(GAR) | 3146.0674 | 3146.0674 | 3146.0674 | 3146.0674 | 3146.0674 | 3146.0674 | 3146.0674 | 3146.0674 | 3146.0674 | 3146.0674 | 3146.0674 | 3146.0674 | 3146.0674
TS | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Ash | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40
Moist | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11
TM | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20
TCM | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Total
OB Removal (KBcm) | 4195 | 4015 | 4020 | 4250 | 4410 | 4660 | 4720 | 5055 | 4740 | 3990 | 3805 | 3790 | 51650 | Done
PAMA | 2025 | 1905 | 1870 | 2010 | 2110 | 2210 | 2320 | 2305 | 2240 | 1890 | 1745 | 1770 | 24400
MAP | 890 | 810 | 750 | 940 | 950 | 950 | 1000 | 1050 | 950 | 900 | 860 | 950 | 11000
PJPN | 1280 | 1300 | 1400 | 1300 | 1350 | 1500 | 1400 | 1700 | 1550 | 1200 | 1200 | 1070 | 16250
ROM Production (Kton) | 200 | 215 | 217 | 255 | 285 | 315 | 310 | 335.387 | 307 | 300 | 281 | 280 | 3300.387
PAMA | 130 | 145 | 150 | 160 | 170 | 200 | 195 | 210 | 210 | 195 | 180 | 185 | 2130
MAP | 45 | 40 | 37 | 45 | 50 | 50 | 50 | 55 | 47 | 45 | 41 | 45 | 550
PJPN | 25 | 30 | 30 | 50 | 65 | 65 | 65 | 70.387 | 50 | 60 | 60 | 50 | 620.387
SR ROM with void | 20.975 | 18.6744 | 18.5253 | 16.6667 | 15.4737 | 14.7937 | 15.2258 | 15.0721 | 15.4397 | 13.3 | 13.5409 | 13.5357 | 15.6497
FC Product CP (Kton) | 217 | 235 | 258 | 257 | 290 | 305 | 315 | 320 | 285 | 253 | 242 | 253 | 3230
TCM.HCV.LS | 110 | 130 | 130 | 140 | 150 | 170 | 170 | 150 | 155 | 115 | 115 | 95 | 1630
TCM.HCV.HS | 100 | 100 | 120 | 110 | 130 | 120 | 130 | 150 | 120 | 130 | 120 | 150 | 1480
TCM.HCV.MS | 7 | 5 | 8 | 7 | 10 | 15 | 15 | 20 | 10 | 8 | 7 | 8 | 120
FC Product 3rd party (Kton) | 139.1 | 139.4 | 138.6 | 138.1 | 139 | 138.3 | 138.5 | 137.7 | 145.6 | 146.2 | 138.3 | 137.7 | 1676.5
EBH.HCV.LS | 56.6 | 56.9 | 56.1 | 55.6 | 56.5 | 55.8 | 56 | 55.2 | 55.6 | 56.2 | 55.8 | 55.2 | 671.5
MBL.MCV.MS | 82.5 | 82.5 | 82.5 | 82.5 | 82.5 | 82.5 | 82.5 | 82.5 | 90 | 90 | 82.5 | 82.5 | 1005
SR FC | 19.3318 | 17.0851 | 15.5814 | 16.537 | 15.2069 | 15.2787 | 14.9841 | 15.7969 | 16.6316 | 15.7708 | 15.7231 | 14.9802 | 15.9907
TCM.HCV.LS | 110 | 130 | 130 | 140 | 150 | 170 | 170 | 150 | 155 | 115 | 115 | 95 | 1630
CV(GAR) | 6331.7794 | 6327.6426 | 6345.3425 | 6327.8237 | 6373.2296 | 6243.3002 | 6268.7387 | 6402.2298 | 6455.744 | 6429.1851 | 6453.9309 | 6360.7189 | 6355.6513
Sul < 0.7 | 0.63239 | 0.69248 | 0.652 | 0.6548 | 0.61487 | 0.6376 | 0.63464 | 0.55063 | 0.52383 | 0.52786 | 0.54698 | 0.54361 | 0.60341
ASH < 5.0 | 5.14 | 4.5591 | 4.5963 | 5.1237 | 4.8279 | 4.5406 | 5.4694 | 4.9514 | 4.2318 | 4.7988 | 4.93 | 4.9975 | 4.8411
IM | 7.9684 | 7.5074 | 7.3053 | 7.3142 | 7.2934 | 7.0845 | 7.3044 | 7.5576 | 7.1827 | 7.4775 | 7.325 | 7.6231 | 7.3863
TM | 13.5018 | 14.5066 | 14.2007 | 13.7425 | 13.7596 | 15.8885 | 14.3471 | 13.1866 | 13.1296 | 12.9827 | 12.4646 | 13.5285 | 13.8465
TCM.HCV.HS | 100 | 100 | 120 | 110 | 130 | 120 | 130 | 150 | 120 | 130 | 120 | 150 | 1480
CV(GAR) | 6528.8013 | 6523.441 | 6602.1856 | 6481.0855 | 6487.5274 | 6515.5714 | 6445.0323 | 6472.1448 | 6412.4032 | 6476.7335 | 6460.6228 | 6423.2952 | 6482.812
Sul < 2.0 | 1.8419 | 2.1454 | 1.7213 | 1.772 | 1.7758 | 2.0871 | 1.8138 | 1.8287 | 1.8482 | 1.8968 | 1.819 | 1.9905 | 1.8762
ASH < 5.0 | 6.7257 | 7.6729 | 55.9656 | 5.9371 | 5.2918 | 7.3265 | 5.9375 | 5.9832 | 6.008 | 6.0191 | 6.0931 | 5.979 | 10.2546
IM | 7.2396 | 7.118 | 6.7065 | 6.8833 | 6.7129 | 6.6877 | 6.6455 | 6.3583 | 6.7264 | 6.4663 | 6.2063 | 6.1537 | 6.6258
TM | 11.8026 | 10.6165 | 10.6667 | 11.5389 | 11.4782 | 10.0232 | 11.715 | 11.1861 | 11.926 | 11.4844 | 11.0808 | 11.4168 | 11.2522
TCM.LCV.MS.HA | 7 | 5 | 8 | 7 | 10 | 15 | 15 | 20 | 10 | 8 | 7 | 8 | 120
CV(GAR) | 3581.7631 | 3599.0009 | 4341.3047 | 3587.2263 | 3651.2002 | 5641.0449 | 5567.1958 | 5442.6121 | 5422.5222 | 5471.7948 | 5388.109 | 5438.9485 | 4963.5346
Sul < 1.2 | 1.16 | 1.15 | 1.44 | 0.51 | 0.5 | 1.45 | 1.5217 | 1.5933 | 1.6133 | 1.5833 | 1.5533 | 1.6133 | 1.3582
ASH < 5.0 | 13.6 | 13.18 | 12.69 | 14.445 | 14.2 | 6.835 | 8.9933 | 11.1517 | 11.1417 | 11.0117 | 11.1717 | 11.9817 | 11.1647
IM | 7.41 | 7.54 | 7.16 | 6.52 | 6.43 | 6.09 | 6.1267 | 6.1633 | 6.1633 | 6.1633 | 6.1633 | 6.1633 | 6.3891
TM | 13.89 | 14.11 | 14.412 | 13.208 | 13.588 | 13.532 | 13.3947 | 14.0533 | 14.0233 | 13.9833 | 14.4533 | 14.0533 | 13.8507
EBH.HCV.LS | 56.6 | 56.9 | 56.1 | 55.6 | 56.5 | 55.8 | 56 | 55.2 | 55.6 | 56.2 | 55.8 | 55.2 | 671.5
CV(GAR) | 6322 | 6322 | 6322 | 6322 | 6322 | 6322 | 6322 | 6322 | 6322 | 6322 | 6322 | 6322 | 6322
Sul < 1 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6
ASH | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7
IM | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12
TM | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14
MBL.MCV.MS | 82.5 | 82.5 | 82.5 | 82.5 | 82.5 | 82.5 | 82.5 | 82.5 | 90 | 90 | 82.5 | 82.5 | 1005
CV(GAR) | 5400 | 5400 | 5400 | 5400 | 5400 | 5400 | 5400 | 5400 | 5400 | 5400 | 5400 | 5400 | 5400
Sul < 1.2 | [12 empty] | 1 | bar: Jan to Dec
ASH | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6
IM | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15
TM | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24
BEK | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Total
OB Removal (KBcm) | 7995 | 7084 | 7619 | 7232 | 7571 | 7593 | 8097 | 8330 | 7698 | 7482 | 6860 | 7389 | 90950 | Done
TRUST | 2085 | 1784 | 1974 | 1997 | 1991 | 1968 | 2132 | 2305 | 2063 | 2062 | 1755 | 1884 | 24000
PAMA | 4250 | 3810 | 4105 | 4235 | 4480 | 4475 | 4785 | 4825 | 4495 | 4420 | 4115 | 4455 | 52450
SNS | 1660 | 1490 | 1540 | 1000 | 1100 | 1150 | 1180 | 1200 | 1140 | 1000 | 990 | 1050 | 14500
ROM Production (Kton) | 684 | 658 | 685.5 | 564 | 663 | 712 | 745 | 752 | 704 | 627.5 | 589 | 616 | 8000
TRUST | 194 | 188 | 185.5 | 156 | 196 | 212 | 245 | 252 | 234 | 192.5 | 169 | 176 | 2400
PAMA | 360 | 350 | 375 | 335 | 380 | 415 | 375 | 400 | 370 | 350 | 340 | 350 | 4400
SNS | 130 | 120 | 125 | 73 | 87 | 85 | 125 | 100 | 100 | 85 | 80 | 90 | 1200
SR ROM | 11.6886 | 10.766 | 11.1145 | 12.8227 | 11.4193 | 10.6643 | 10.8685 | 11.0771 | 10.9347 | 11.9235 | 11.6469 | 11.9951 | 11.3688
SR FC | 11.4214 | 10.12 | 10.8843 | 11.1262 | 11.6477 | 11.6815 | 11.5671 | 11.7324 | 10.9971 | 11.3364 | 10.7188 | 11.5453 | 11.2284
FC Product (KTons) | 700 | 700 | 700 | 650 | 650 | 650 | 700 | 710 | 700 | 660 | 640 | 640 | 8100
BEK.MCV.LS | 400 | 480 | 480 | 465 | 465 | 460 | 500 | 490 | 480 | 460 | 440 | 440 | 5560
CV(GAR) | 6030.4358 | 5774.2277 | 5860.9708 | 5868.1864 | 5954.6027 | 5916.1255 | 5984.187 | 5944.3266 | 5921.0085 | 5916.7362 | 5898.291 | 5928.9325 | 5915.2264
TS | 0.53158 | 0.52889 | 0.5114 | 0.47877 | 0.51889 | 0.54684 | 0.6156 | 0.65164 | 0.57083 | 0.61028 | 0.68843 | 0.67517 | 0.5772
Ash | 4.5798 | 4.3819 | 4.7059 | 4.7159 | 4.47 | 4.6727 | 5.1675 | 5.2807 | 5.3764 | 5.2082 | 4.9555 | 5.0376 | 4.8848
IM | 11.5325 | 12.1617 | 11.7688 | 10.9822 | 11.9963 | 11.3734 | 10.8514 | 11.2599 | 11.1283 | 11.3129 | 11.8103 | 11.5197 | 11.4694
TM | 16.0731 | 18.3447 | 16.1139 | 15.2818 | 15.685 | 15.0345 | 13.9867 | 14.31 | 14.2913 | 14.4636 | 14.865 | 14.5485 | 15.2419
BEK.MCV.MS | 300 | 220 | 220 | 185 | 185 | 190 | 200 | 220 | 220 | 200 | 200 | 200 | 2540
CV(GAR) | 5978.3055 | 5788.4874 | 5780.4749 | 5757.1239 | 5689.0306 | 5723.4269 | 5710.0663 | 5767.3036 | 5816.7184 | 5783.944 | 5714.3882 | 5899.7671 | 5792.8232
TS | 1.787 | 1.8051 | 1.7535 | 1.753 | 1.7123 | 1.7854 | 1.8239 | 1.742 | 1.7014 | 1.7606 | 1.7678 | 1.7233 | 1.7606
Ash | 4.7301 | 5.5271 | 5.5458 | 5.7433 | 6.1338 | 6.4532 | 6.4437 | 6.2121 | 5.7608 | 5.8895 | 6.1089 | 5.112 | 5.7572
IM | 11.0894 | 10.939 | 11.1033 | 10.7531 | 10.9318 | 10.5429 | 10.9263 | 10.5327 | 10.5196 | 10.609 | 10.4098 | 10.3006 | 10.7369
TM | 14.7767 | 14.7885 | 14.9686 | 14.6226 | 15.0392 | 14.4524 | 14.7662 | 14.3018 | 14.2251 | 14.4043 | 14.4451 | 13.7474 | 14.5518
JBG | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Total
OB Removal (KBcm) | 103.007 | 93.07 | 98.059 | 280.6245 | 579.3785 | 448.889 | 536.383 | 575.345 | 590.094 | 632.103 | 557.72 | 543.935 | 5038.608 | Done
Contractor Pit UCE ext | 103.007 | 93.07 | 98.059 | 280.6245 | 579.3785 | 448.889 | 536.383 | 575.345 | 590.094 | 632.103 | 557.72 | 543.935 | 5038.608
ROM Production (Kton) | 0 | 0 | 0 | 0 | 20 | 37 | 51 | 60 | 70 | 75 | 68 | 67 | 448
Contractor Pit UCE ext | 0 | 0 | 0 | 0 | 20 | 37 | 51 | 60 | 70 | 75 | 68 | 67 | 448
SR ROM | 0 | 0 | 0 | 0 | 28.9689 | 12.1321 | 10.5173 | 9.5891 | 8.4299 | 8.428 | 8.2018 | 8.1184 | 11.2469
SR FC | 0 | 0 | 0 | 0 | 32.1877 | 12.8254 | 10.7277 | 9.9197 | 8.6779 | 8.7792 | 8.4503 | 8.2414 | 11.6365
JBG Coal Loading | 14.6 | 14.6 | 7.3 | 7.3 | 21.9 | 36.5 | 43.8 | 58.4 | 58.4 | 58.4 | 58.4 | 51.1 | 430.7
JBG FC Product (Kton) / JBG | 0 | 0 | 0 | 0 | 18 | 35 | 50 | 58 | 68 | 72 | 66 | 66 | 433
CV(GAR) | 0 | 0 | 0 | 0 | 4442.3525 | 4414.0197 | 4416.3842 | 4432.5862 | 4408.926 | 4423.0872 | 4453.786 | 4407.9045 | 4423.7946
TS | 0 | 0 | 0 | 0 | 0.38874 | 0.35403 | 0.38864 | 0.37486 | 0.36433 | 0.35476 | 0.35693 | 0.38386 | 0.36899
Ash | 0 | 0 | 0 | 0 | 4.3469 | 4.2775 | 4.5772 | 4.4107 | 4.3138 | 4.438 | 4.3733 | 4.6218 | 4.4323
IM | 0 | 0 | 0 | 0 | 17.434 | 17.2038 | 17.034 | 16.8716 | 16.9773 | 16.7251 | 16.9357 | 16.7621 | 16.9259
TM | 0 | 0 | 0 | 0 | 30.1867 | 30.2656 | 30.3349 | 30.2198 | 30.2331 | 30.2451 | 30.1783 | 30.2279 | 30.2366
GPK | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Total
OB Removal (KBcm) | 630 | 580 | 630 | 610 | 700 | 675 | 745 | 790 | 785 | 880 | 705 | 770 | 8500 | Done
ARKA | 630 | 580 | 630 | 610 | 700 | 675 | 745 | 790 | 785 | 880 | 705 | 770 | 8500
ROM Production (Kton) | 184 | 166 | 182 | 175 | 180 | 175 | 160 | 160 | 160 | 196 | 175 | 187 | 2100
ARKA | 119 | 108 | 118 | 114 | 131 | 127 | 125 | 124 | 126 | 139 | 114 | 122 | 1467
SLS | 65 | 58 | 64 | 61 | 49 | 48 | 35 | 36 | 34 | 57 | 61 | 65 | 633
SR ROM | 3.4239 | 3.494 | 3.4615 | 3.4857 | 3.8889 | 3.8571 | 4.6562 | 4.9375 | 4.9062 | 4.4898 | 4.0286 | 4.1176 | 4.0476
SR FC | 3.15 | 3.2222 | 3.3158 | 3.4857 | 3.8889 | 3.8571 | 8.2778 | 15.8 | 8.7222 | 4.1905 | 2.7115 | 3.08 | 4.1463
FC Production (Ktons) | 200 | 180 | 190 | 175 | 180 | 175 | 90 | 50 | 90 | 210 | 260 | 250 | 2050
CV(GAR) | 3597.7504 | 3594.5296 | 3663.6762 | 3731.5323 | 3747.0877 | 3753.0309 | 3709.9842 | 3710.8591 | 3754.9789 | 3802.469 | 3810.8052 | 3790.9104 | 3727.504
TS | 0.11569 | 0.11701 | 0.15581 | 0.15133 | 0.15302 | 0.14876 | 0.16964 | 0.1691 | 0.15833 | 0.16553 | 0.17248 | 0.16287 | 0.15227
Ash | 10.1457 | 10.2139 | 9.4792 | 8.2664 | 7.972 | 8.1087 | 9.7175 | 9.7409 | 8.5788 | 6.4456 | 5.4512 | 5.9086 | 7.9761
IM | 27.2738 | 27.292 | 26.9771 | 25.1243 | 25.0639 | 24.2542 | 31.6027 | 31.4781 | 27.5216 | 26.4417 | 28.9143 | 29.0422 | 27.2546
TM | 37.9185 | 37.923 | 38.043 | 37.9509 | 37.979 | 38.0738 | 37.7175 | 37.7338 | 37.8637 | 38.4165 | 39.0685 | 39.1676 | 38.2852
TIS | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Total
OB Removal (KBcm) | 982.5 | 833.26 | 955 | 979.8 | 1028.75 | 1131.36 | 1343.54 | 1450.15 | 1249.8 | 960.24 | 867.28 | 919 | 12700.68 | Done
Contractor | 982.5 | 833.26 | 955 | 979.8 | 1028.75 | 1131.36 | 1343.54 | 1450.15 | 1249.8 | 960.24 | 867.28 | 919 | 12700.68
ROM Production (Kton) | 30 | 35 | 42 | 45 | 57 | 56 | 62 | 65 | 60 | 54 | 50 | 50 | 606
Contractor | 30 | 35 | 42 | 45 | 57 | 56 | 62 | 65 | 60 | 54 | 50 | 50 | 606
SR ROM | 32.75 | 23.8074 | 22.7381 | 21.7733 | 18.0482 | 20.2029 | 21.67 | 22.31 | 20.83 | 17.7822 | 17.3456 | 18.38 | 20.9582
SR FC | 32.75 | 27.7753 | 23.875 | 21.7733 | 20.575 | 22.6272 | 22.3923 | 24.1692 | 22.7236 | 17.4589 | 15.7687 | 15.3167 | 21.5266
FC Production (Ktons) | 30 | 30 | 40 | 45 | 50 | 50 | 60 | 60 | 55 | 55 | 55 | 60 | 590
CV(GAR) | 6824.4902 | 6820.347 | 6806.1231 | 6833.9324 | 6994.3648 | 7027.769 | 7159.1562 | 7071.2557 | 6895.4537 | 6801.9028 | 6932.8199 | 6909.6969 | 6937.7795
TS | 1.4308 | 1.514 | 1.5556 | 1.5556 | 1.5556 | 1.2556 | 1.2556 | 1.2956 | 1.1556 | 1.2556 | 1.1826 | 1.2556 | 1.3342
Ash | 2.9538 | 3.1342 | 3.1952 | 3.3935 | 3.2981 | 2.807 | 2.8034 | 3.0056 | 2.6377 | 2.8831 | 2.5935 | 2.6437 | 2.9184
TM | 9.2954 | 9.5623 | 9.5267 | 9.173 | 7.383 | 7.412 | 7.6268 | 7.9623 | 9.8486 | 10.6281 | 9.9458 | 10.1123 | 9.0079
IM | 4.4328 | 4.5235 | 4.5521 | 4.5577 | 4.7566 | 4.5533 | 4.6037 | 4.8186 | 4.569 | 4.9642 | 4.6397 | 4.7277 | 4.6608
NPR | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Total
OB Removal (KBcm) | 0 | 0 | 129 | 535 | 542 | 543 | 586 | 594 | 578 | 752 | 682 | 742.5 | 5683.5 | Done
Contractor | 0 | 0 | 129 | 535 | 542 | 543 | 586 | 594 | 578 | 752 | 682 | 742.5 | 5683.5
ROM Production (Kton) | 0 | 0 | 0 | 0 | 25 | 55 | 60 | 60 | 55 | 65 | 65 | 65 | 450
Contractor | 0 | 0 | 0 | 0 | 25 | 55 | 60 | 60 | 55 | 65 | 65 | 65 | 450
SR ROM | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 21.68 | 9.8727 | 9.7667 | 9.9 | 10.5091 | 11.5692 | 10.4923 | 11.4231 | 12.63
SR FC | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 31.8824 | 14.6757 | 14.65 | 14.85 | 15.6216 | 17.4884 | 15.8605 | 17.2674 | 18.945
FC Production (Ktons) | 0 | 0 | 0 | 0 | 17 | 37 | 40 | 40 | 37 | 43 | 43 | 43 | 300
CV(GAD) | 0 | 0 | 0 | 0 | 6479.8736 | 6587.4532 | 6598.4997 | 6640.8571 | 6546.9132 | 6622.5542 | 6577.0752 | 6514.6914 | 4957.0662
TS | 0 | 0 | 0 | 0 | 1.1963 | 1.2298 | 1.1899 | 1.1598 | 1.0431 | 1.0999 | 1.0172 | 0.99869 | 0.84071
Ash | 0 | 0 | 0 | 0 | 6.1898 | 6.1677 | 6.5217 | 6.2198 | 5.498 | 6.2002 | 5.4953 | 5.9413 | 4.55
IM |  |  |  | 0 | 8.626 | 7.4 | 6.7387 | 6.6266 | 8.5113 | 6.8655 | 8.0495 | 8.45 | 5.7605
TM | 0 | 0 | 0 | 0 | 14.7805 | 14.414 | 14.3683 | 14.3998 | 15.0003 | 14.3847 | 15.0759 | 15.0952 | 11.0795

## Outlook 0+12
ITM outlook 2025 (0+12) | 1000
| Out. | Out. | Out. | Out. | Out. | Out. | Out. | Out. | Out. | Out. | Out. | Out. | Out.
IMM | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Total | Budget 2025
OB Removal (KBcm) | 7628.0103 | 7275.0402 | 6917.9241 | 7858.7341 | 8278.4905 | 7640.614 | 8789.2468 | 8512.679 | 8487.7924 | 8286.6041 | 7878.5928 | 7651.8218 | 95205.55 | 94714.4782 | 100.5%
PAMA (WB) | 2766.4135 | 2778.6096 | 2447.1295 | 2781.4178 | 2942.6228 | 2548.7015 | 3112.9386 | 3121.8471 | 2945.2593 | 2874.3188 | 2732.4476 | 2649.3725 | 33701.0787 | 33532.659
PAMA (EB) | 4861.5967 | 4496.4306 | 4470.7946 | 5077.3162 | 5335.8677 | 5091.9125 | 5676.3082 | 5390.8319 | 5542.5331 | 5412.2853 | 5146.1452 | 5002.4492 | 61504.4713 | 61181.8192
ROM Production (Kton) | 554.0648 | 552.5 | 552.5 | 557.5 | 557.5 | 557.5 | 622.5 | 637.5 | 637.5 | 637.5 | 637.5 | 630.9352 | 7135 | 7100 | 100.5%
PAMA (WB) | 188.7832 | 170 | 170 | 160 | 175 | 150 | 140 | 130.2737 | 130 | 115 | 110 | 85.9427 | 1724.9996 | 1862.5
PAMA (EB) | 365.2816 | 370 | 370 | 385 | 370 | 395 | 470 | 494.7263 | 495 | 510 | 515 | 532.4925 | 5272.5004 | 5087.5
Fine Coal (WB) | 0 | 12.5 | 12.5 | 12.5 | 12.5 | 12.5 | 12.5 | 12.5 | 12.5 | 12.5 | 12.5 | 12.5 | 137.5 | 150
SR ROM Total | 13.7674 | 13.1675 | 12.5211 | 14.0964 | 14.8493 | 13.7051 | 14.1193 | 13.3532 | 13.3142 | 12.9986 | 12.3586 | 12.1277 | 13.3435 | 13.3401
FC Product (Kton) | 575 | 575 | 575 | 554.25 | 559.25 | 559.25 | 625.75 | 637.75 | 637.75 | 607 | 607 | 622 | 7135 | 7100
PAMA (WB) | 185 | 185 | 185 | 165 | 175 | 150 | 150 | 130.2737 | 130 | 100 | 95 | 74.7263 | 1725 | 1862.5
PAMA (EB) | 390 | 385.75 | 385.75 | 385 | 371.5 | 396.5 | 463 | 494.7263 | 495 | 494.25 | 499.25 | 534.5237 | 5295.25 | 5110
Fine Coal | 0 | 4.25 | 4.25 | 4.25 | 12.75 | 12.75 | 12.75 | 12.75 | 12.75 | 12.75 | 12.75 | 12.75 | 114.75 | 127.5
SR FC Total | 13.2661 | 12.6522 | 12.0312 | 14.179 | 14.8028 | 13.6623 | 14.0459 | 13.348 | 13.309 | 13.6517 | 12.9796 | 12.302 | 13.3435 | 13.3401
IMM-WB.HCV.LS | 128 | 127.8972 | 125.948 | 123.7237 | 121.2849 | 72.6933 | 51.7765 | 63.5694 | 60.5097 | 63.6341 | 63.9549 | 73.7892 | 1076.781 | 1228.8032 |  | HCV.LS
CV(GAR) | 6056.5044 | 6054.4664 | 6060.4292 | 6107.8098 | 6113.6029 | 6164.2166 | 6395.8697 | 6385.8035 | 6374.9065 | 6403.0078 | 6240.9311 | 6210.111 | 6171.9284 | 6169.7769
TS | 0.80255 | 0.79953 | 0.80439 | 0.79981 | 0.79531 | 0.79963 | 0.79865 | 0.80333 | 0.79961 | 0.83949 | 0.84973 | 0.83518 | 0.80799 | 0.8108
Ash | 8.964 | 8.6166 | 8.5486 | 8.4231 | 8.4693 | 8.3242 | 8.2711 | 8 | 7.9679 | 8.1902 | 8.1985 | 8.2054 | 8.4237 | 8.3746
Moist | 8.4747 | 8.6985 | 8.8457 | 8.5395 | 8.6056 | 8.6071 | 7.2978 | 7.0138 | 7.1238 | 7.1299 | 7.0581 | 7.7179 | 8.1416 | 8.0403
TM | 13.3241 | 13.7239 | 13.871 | 13.5648 | 13.631 | 13.6325 | 12.3231 | 12.0392 | 12.1492 | 12.1553 | 12.0835 | 12.7433 | 13.146 | 13.0657
IMM-WB.HCV.HS | 57 | 57.1028 | 59.052 | 41.2763 | 53.7151 | 77.3067 | 98.2235 | 66.7042 | 69.4903 | 36.3659 | 31.0451 | 0.93716 | 648.219 | 633.6968 |  | MCV.HS
CV(GAR) | 5986.1578 | 6173.5681 | 6011.4535 | 5973.6523 | 5924.8145 | 5894.6697 | 5962.1308 | 5930.0109 | 6005.5198 | 5934.0912 | 5986.2386 | 5823.7307 | 5977.6863 | 5965.7827
TS | 2.1575 | 2.5144 | 2.483 | 2.6032 | 2.6338 | 2.744 | 2.7636 | 2.6981 | 2.6091 | 2.5875 | 2.4796 | 2.3813 | 2.5922 | 2.579
Ash | 12.4427 | 13.06 | 13.0008 | 13.8721 | 14.3974 | 14.7586 | 13.5097 | 14.2548 | 13.3246 | 13.975 | 13.7272 | 14.8851 | 13.6708 | 13.9606
Moist | 6.41 | 5.5947 | 6.0025 | 6.0768 | 6.0587 | 7.077 | 6.8342 | 6.7892 | 6.831 | 7.2712 | 7.2743 | 7.8622 | 6.5705 | 6.744
TM | 11.8107 | 10.6201 | 11.0279 | 11.1022 | 11.084 | 12.1024 | 11.8596 | 11.8146 | 11.8564 | 12.2965 | 12.2997 | 12.8876 | 11.6289 | 11.7694
IMM-EB.MCV.LS | 3.5 | 2.2366 | 2.4267 | 2.7672 | 1.8759 | 1.0397 | 0 | 0 | 0 | 0 | 0 | 0 | 13.8461 | 13.6399 |  | MCV.LS
CV(GAR) | 5856.5504 | 5817.4439 | 5826.7921 | 5826.0545 | 5822.6987 | 5826.1463 | 0 | 0 | 0 | 0 | 0 | 0 | 5832.0538 | 5822.4314
TS | 0.9005 | 0.90545 | 0.90943 | 0.90188 | 0.90557 | 0.91112 | 0 | 0 | 0 | 0 | 0 | 0 | 0.90462 | 0.90072
Ash | 7.7055 | 8.6308 | 8.6015 | 8.5322 | 8.5297 | 8.467 | 0 | 0 | 0 | 0 | 0 | 0 | 8.3461 | 8.5978
Moist | 12.0415 | 11.3267 | 11.3558 | 11.3496 | 11.3875 | 11.347 | 0 | 0 | 0 | 0 | 0 | 0 | 11.5268 | 11.3544
TM | 16.4755 | 16.3267 | 16.3558 | 16.3496 | 16.3875 | 16.347 | 0 | 0 | 0 | 0 | 0 | 0 | 16.3837 | 16.3544
IMM-EB.MCV.MS | 15 | 6.9718 | 21.3777 | 3.4013 | 22.0906 | 4.5999 | 41.5703 | 40.7729 | 79.8482 | 87.0012 | 77.7978 | 75.9579 | 476.3898 | 422.7155 |  | HCV.MS
CV(GAR) | 5918.5614 | 5954.7474 | 6008.4875 | 6032.4641 | 5995.2123 | 6003.9591 | 6003.0099 | 6001.1416 | 6011.5797 | 5999.8733 | 6040.1578 | 6028.7914 | 6010.6292 | 6013.6725
TS | 1.5875 | 1.5558 | 1.5457 | 1.5545 | 1.575 | 1.5507 | 1.5529 | 1.5598 | 1.5743 | 1.5666 | 1.591 | 1.5736 | 1.5709 | 1.5595
Ash | 5.1836 | 6.1748 | 6.1701 | 5.2235 | 5.3979 | 5.2386 | 5.1541 | 5.2235 | 5.4137 | 5.4676 | 5.219 | 5.3018 | 5.369 | 5.3287
Moist | 11.923 | 10.2428 | 10.5328 | 10.3487 | 10.691 | 10.4716 | 10.6218 | 10.5728 | 10.3501 | 10.2451 | 10.1283 | 9.9459 | 10.3461 | 10.2792
TM | 16.6957 | 15.2428 | 15.5328 | 15.3487 | 15.691 | 15.4716 | 15.6218 | 15.5728 | 15.3501 | 15.2451 | 15.1283 | 14.9459 | 15.339 | 15.2792
IMM-EB.MCV.HS | 371.5 | 376.5415 | 361.9456 | 378.8315 | 347.5336 | 390.8604 | 421.4297 | 453.9534 | 415.1518 | 407.2488 | 421.4522 | 458.5657 | 4805.0141 | 4673.6446 |  | MCV.HS
CV(GAR) | 5902.1319 | 5916.5389 | 5922.1585 | 5914.5409 | 5925.7421 | 5920.6933 | 5898.7092 | 5885.4229 | 5917.7048 | 5911.2382 | 5935.692 | 5909.796 | 5912.8788 | 5914.4155
TS | 2.3883 | 2.3937 | 2.3549 | 2.4779 | 2.3768 | 2.3487 | 2.4366 | 2.4656 | 2.4545 | 2.4643 | 2.3499 | 2.4319 | 2.4137 | 2.4107
Ash | 5.7182 | 5.7264 | 5.7547 | 5.6691 | 5.5841 | 5.7363 | 5.6945 | 5.8263 | 5.6808 | 5.7577 | 5.6903 | 5.6781 | 5.7115 | 5.72
Moist | 11.2608 | 10.57 | 10.6716 | 10.509 | 10.6806 | 10.7263 | 10.6505 | 10.5526 | 10.4549 | 10.4721 | 10.4816 | 10.5772 | 10.6271 | 10.5582
TM | 15.9224 | 15.57 | 15.6716 | 15.509 | 15.6806 | 15.7263 | 15.6505 | 15.5526 | 15.4549 | 15.4721 | 15.4816 | 15.5772 | 15.6009 | 15.5582
Fine Coal | 0 | 4.25 | 4.25 | 4.25 | 12.75 | 12.75 | 12.75 | 12.75 | 12.75 | 12.75 | 12.75 | 12.75 | 114.75 | 127.5
CV(GAR) | 3146.0674 | 3146.0674 | 3146.0674 | 3146.0674 | 3146.0674 | 3146.0674 | 3146.0674 | 3146.0674 | 3146.0674 | 3146.0674 | 3146.0674 | 3146.0674 | 3146.0674 | 3146.0674
TS | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Ash | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40
Moist | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11
TM | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20
TCM | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Total | Budget 2025
OB Removal (KBcm) | 4040 | 3610 | 3860 | 4015 | 4045 | 4115 | 4295 | 4410 | 3955 | 3535 | 3300 | 3720 | 46900 | 51650 | 90.8%
PAMA | 2050 | 1900 | 2160 | 2075 | 2120 | 2140 | 2145 | 2160 | 2105 | 1835 | 1740 | 1970 | 24400 | 24400
MAP | 890 | 810 | 750 | 940 | 950 | 950 | 1000 | 1050 | 950 | 900 | 860 | 950 | 11000 | 11000
PJPN | 1100 | 900 | 950 | 1000 | 975 | 1025 | 1150 | 1200 | 900 | 800 | 700 | 800 | 11500 | 16250
ROM Production (Kton) | 230 | 208 | 242 | 250 | 280 | 294 | 315 | 320 | 313 | 287 | 285 | 276 | 3300 | 3300.387 | 99.99%
PAMA | 165 | 150 | 170 | 160 | 170 | 180 | 195 | 200 | 200 | 180 | 185 | 175 | 2130 | 2130
MAP | 35 | 30 | 37 | 40 | 50 | 52 | 55 | 55 | 53 | 47 | 45 | 51 | 550 | 550
PJPN | 30 | 28 | 35 | 50 | 60 | 62 | 65 | 65 | 60 | 60 | 55 | 50 | 620 | 620.387
Temporary ROM Stock | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SR ROM with void | 17.5652 | 17.3558 | 15.9504 | 16.06 | 14.4464 | 13.9966 | 13.6349 | 13.7812 | 12.6358 | 12.3171 | 11.5789 | 13.4783 | 14.2121 | 15.6497
FC Product CP (Kton) | 237 | 235 | 258 | 257 | 290 | 305 | 315 | 320 | 285 | 253 | 242 | 253 | 3250 | 3230
TCM.HCV.LS | 111.96 | 131.4 | 132.24 | 141.96 | 152.8 | 174.2 | 174.2 | 155.6 | 157.8 | 117.24 | 116.96 | 97.24 | 1663.6 | 1630
TCM.HCV.HS | 125.04 | 103.6 | 125.76 | 115.04 | 137.2 | 130.8 | 140.8 | 164.4 | 127.2 | 135.76 | 125.04 | 155.76 | 1586.4 | 1480
TCM.HCV.MS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 120
FC Product 3rd party (Kton) | 57.1257 | 53.4973 | 58.8103 | 75.2631 | 125.3982 | 94.7562 | 83.1464 | 58.1837 | 37.1395 | 68.7549 | 52.9974 | 55 | 820.0726 | 1676.5
EBH.HCV.LS | 7.1098 | 40.5275 | 51.9524 | 50.1264 | 109.9789 | 87.8438 | 83.1464 | 58.1837 | 37.1395 | 60.3145 | 52.9974 | 45 | 684.3203 | 671.5
MBL.MCV.MS | 50.0159 | 12.9697 | 6.8579 | 25.1368 | 15.4192 | 6.9123 | 0 | 0 | 0 | 8.4404 | 0 | 10 | 135.7523 | 1005
SR FC | 17.0464 | 15.3617 | 14.9612 | 15.6226 | 13.9483 | 13.4918 | 13.6349 | 13.7812 | 13.8772 | 13.9723 | 13.6364 | 14.7036 | 14.4308 | 15.9907
TCM.HCV.LS | 111.96 | 131.4 | 132.24 | 141.96 | 152.8 | 174.2 | 174.2 | 155.6 | 157.8 | 117.24 | 116.96 | 97.24 | 1663.6 | 1630
CV(GAR) | 6256.8826 | 6151.8686 | 6323.6991 | 6386.9863 | 6358.9709 | 6190.1228 | 6322.8213 | 6416.6271 | 6423.6804 | 6428.0881 | 6488.4941 | 6366.8033 | 6339.829 | 6355.6513
Sul < 0.7 | 0.67659 | 0.7566 | 0.77548 | 0.68147 | 0.69079 | 0.72769 | 0.69183 | 0.72233 | 0.63605 | 0.58099 | 0.56337 | 0.57147 | 0.67903 | 0.60341
ASH < 5.0 | 5.4656 | 5.0761 | 5.2984 | 4.878 | 5.0063 | 5.7426 | 4.8599 | 4.8093 | 4.8555 | 4.9385 | 4.5793 | 4.9814 | 5.0478 | 4.8411
IM | 7.0157 | 6.8285 | 7.0933 | 7.2353 | 7.5619 | 7.7033 | 7.5591 | 7.6174 | 7.9039 | 7.7868 | 7.7503 | 7.7999 | 7.4972 | 7.3863
TM | 14.5018 | 14.5715 | 14.2656 | 13.8074 | 13.8245 | 15.9534 | 14.412 | 13.2515 | 13.1945 | 13.0476 | 12.5295 | 13.5934 | 13.9745 | 13.8465
TCM.HCV.HS | 125.04 | 103.6 | 125.76 | 115.04 | 137.2 | 130.8 | 140.8 | 164.4 | 127.2 | 135.76 | 125.04 | 155.76 | 1586.4 | 1480
CV(GAR) | 6538.5941 | 6552.6194 | 6466.1138 | 6361.4349 | 6402.1858 | 6559.1839 | 6321.2724 | 6444.2453 | 6431.0105 | 6471.068 | 6428.6582 | 6431.8252 | 6448.1988 | 6482.812
Sul < 2.0 | 1.8417 | 1.8597 | 1.8736 | 1.8545 | 1.8846 | 1.8768 | 2.1488 | 1.8592 | 1.7933 | 1.8227 | 1.9993 | 1.9065 | 1.8953 | 1.8762
ASH < 5.0 | 4.5934 | 5.8943 | 6.3069 | 6.8186 | 6.6718 | 5.832 | 7.4564 | 6.3987 | 5.7059 | 5.3122 | 6.4005 | 5.762 | 6.1065 | 10.2546
IM | 6.8551 | 6.5454 | 6.3104 | 6.4792 | 6.4581 | 6.4971 | 6.2776 | 6.4414 | 6.4545 | 6.3794 | 6.255 | 5.9538 | 6.3978 | 6.6258
TM | 11.8675 | 10.6814 | 10.7316 | 11.6038 | 11.5431 | 10.0881 | 11.7799 | 11.251 | 11.9909 | 11.5493 | 11.1457 | 11.4817 | 11.3223 | 11.2522
EBH.HCV.LS | 7.1098 | 40.5275 | 51.9524 | 50.1264 | 109.9789 | 87.8438 | 83.1464 | 58.1837 | 37.1395 | 60.3145 | 52.9974 | 45 | 684.3203 | 671.5
CV(GAR) | 6322 | 6322 | 6322 | 6322 | 6322 | 6322 | 6322 | 6322 | 6322 | 6322 | 6322 | 6322 | 6322 | 6322
Sul < 1.2 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6
ASH < 5.0 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7
IM | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12
TM | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14
MBL.MCV.MS | 50.0159 | 12.9697 | 6.8579 | 25.1368 | 15.4192 | 6.9123 | 0 | 0 | 0 | 8.4404 | 0 | 10 | 135.7523 | 1005
CV(GAR) | 5400 | 5400 | 5400 | 5400 | 5400 | 5400 | 5400 | 5400 | 5400 | 5400 | 5400 | 5400 | 5400 | 5400
Sul < 1.2 | [12 empty] | 1 | 1 | bar: Jan to Dec
ASH < 5.0 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6
IM | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15
TM | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24
BEK | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Total | Budget 2025
OB Removal (KBcm) | 8106 | 7044 | 7554 | 7692 | 7896 | 7993 | 8152 | 8475 | 7883 | 7841 | 7210 | 7654 | 93500 | 90950 | 102.8%
TRUST | 2085 | 1784 | 1974 | 1997 | 1991 | 1968 | 2132 | 2305 | 2063 | 2062 | 1755 | 1884 | 24000 | 24000
PAMA | 4366 | 3810 | 4105 | 4495 | 4755 | 4755 | 5020 | 5120 | 4770 | 4729 | 4450 | 4625 | 55000 | 52450
SNS | 1655 | 1450 | 1475 | 1200 | 1150 | 1270 | 1000 | 1050 | 1050 | 1050 | 1005 | 1145 | 14500 | 14500
ROM Production (Kton) | 775 | 675 | 700 | 665 | 715 | 720 | 720 | 725 | 710 | 650 | 590 | 605 | 8250 | 8000 | 103.1%
TRUST | 195 | 185 | 180 | 155 | 200 | 210 | 245 | 250 | 235 | 200 | 170 | 175 | 2400 | 2400
PAMA | 400 | 350 | 380 | 400 | 400 | 400 | 400 | 400 | 400 | 370 | 350 | 350 | 4600 | 4400
SNS | 180 | 140 | 140 | 110 | 115 | 110 | 75 | 75 | 75 | 80 | 70 | 80 | 1250 | 1200
SR ROM | 10.4594 | 10.4356 | 10.7914 | 11.5669 | 11.0434 | 11.1014 | 11.3222 | 11.6897 | 11.1028 | 12.0631 | 12.2203 | 12.6512 | 11.3333 | 11.3688
SR FC | 11.1807 | 10.5134 | 10.6695 | 10.6833 | 11.6978 | 10.7001 | 11.3855 | 12.5556 | 11.1028 | 11.2014 | 10.3 | 11.5271 | 11.1177 | 11.2284
FC Product (KTons) | 725 | 670 | 708 | 720 | 675 | 747 | 716 | 675 | 710 | 700 | 700 | 664 | 8410 | 8100
BEK.MCV.LS | 600 | 555 | 525 | 550 | 525 | 557 | 496 | 475 | 475 | 500 | 450 | 437 | 6145 | 5560
CV(GAR) | 6280.5639 | 6252.5209 | 6243.3113 | 6307.1116 | 6286.3205 | 6280.5754 | 6227.8661 | 6300.8924 | 6288.6627 | 6203.2688 | 6216.2188 | 6209.7275 | 6259.6225 | 5915.2264
TS | 0.56471 | 0.55668 | 0.55669 | 0.54717 | 0.52439 | 0.51918 | 0.5225 | 0.51774 | 0.5269 | 0.49841 | 0.52296 | 0.50041 | 0.53117 | 0.5772
Ash | 4.3366 | 4.2266 | 4.2709 | 4.0494 | 3.9386 | 3.9237 | 3.9035 | 3.9665 | 3.9003 | 3.8293 | 3.8365 | 3.8301 | 4.0127 | 4.8848
IM | 10.1987 | 10.5001 | 10.5686 | 10.3025 | 10.4932 | 10.539 | 10.875 | 10.398 | 10.4779 | 11.1034 | 11.0284 | 11.0658 | 10.6104 | 11.4694
TM | 14.0374 | 14.3095 | 14.3587 | 14.0353 | 14.2391 | 14.2888 | 14.6785 | 14.1472 | 14.2402 | 14.9314 | 14.8415 | 14.8909 | 14.3975 | 15.2419
BEK.HCV.MS | 125 | 115 | 183 | 170 | 150 | 190 | 220 | 200 | 235 | 200 | 250 | 227 | 2265 | 2540
CV(GAR) | 6058.5868 | 6047.2677 | 6100.957 | 6145.8377 | 6178.2938 | 6144.6558 | 6173.6558 | 6153.3994 | 6154.0234 | 6178.4594 | 6201.2344 | 6192.2436 | 6152.3067 | 5792.8232
TS | 2.0346 | 2.0348 | 1.8115 | 1.753 | 1.7549 | 1.6816 | 1.5393 | 1.6659 | 1.6443 | 1.6269 | 1.5082 | 1.5299 | 1.6815 | 1.7606
Ash | 5.0116 | 5.2597 | 4.1283 | 4.2179 | 4.3166 | 4.2131 | 4.0309 | 4.3307 | 4.2957 | 4.3373 | 4.1808 | 4.2106 | 4.3191 | 5.7572
IM | 11.0449 | 10.9697 | 10.8644 | 10.6692 | 10.627 | 10.473 | 10.5944 | 10.3602 | 10.3987 | 10.6411 | 11.1585 | 11.2095 | 10.7448 | 10.7369
TM | 14.9097 | 14.8473 | 14.9344 | 14.6645 | 14.5016 | 14.5933 | 14.5627 | 14.4108 | 14.4393 | 14.4467 | 14.6809 | 14.7258 | 14.6254 | 14.5518
JBG | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Total | Budget 2025
OB Removal (KBcm) | 0 | 0 | 0 | 103.007 | 93.07 | 98.059 | 280.6245 | 579.3785 | 448.889 | 536.383 | 575.345 | 590.094 | 3304.85 | 5038.608 | 65.59%
Pit UCE-Extend | 0 | 0 | 0 | 103.007 | 93.07 | 98.059 | 280.6245 | 579.3785 | 448.889 | 536.383 | 575.345 | 590.094 | 3304.85 | 5038.608
ROM Production (Kton) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 37 | 51 | 60 | 70 | 238 | 448 | 53.12%
Pit UCE-Extend | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 37 | 51 | 60 | 70 | 238 | 448
SR ROM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28.9689 | 12.1321 | 10.5173 | 9.5891 | 8.4299 | 13.8859 | 11.2469
SR FC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32.1877 | 12.8254 | 10.7277 | 9.5891 | 9.8349 | 14.82 | 11.6365
JBG Coal Loading | 0 | 0 | 7.3 | 7.3 | 14.6 | 14.6 | 7.3 | 14.6 | 29.2 | 43.8 | 43.8 | 58.4 | 240.9 | 430.7
JBG FC Product (Kton) / JBG | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 35 | 50 | 60 | 60 | 223 | 433
CV(GAR) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4442.3525 | 4414.0197 | 4416.3842 | 4432.5862 | 4408.926 | 4420.4618 | 4423.7946
TS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.38874 | 0.35403 | 0.38864 | 0.37486 | 0.36433 | 0.37297 | 0.36899
Ash | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.3469 | 4.2775 | 4.5772 | 4.4107 | 4.3138 | 4.3959 | 4.4323
IM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17.434 | 17.2038 | 17.034 | 16.8716 | 16.9773 | 17.034 | 16.9259
TM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30.1867 | 30.2656 | 30.3349 | 30.2198 | 30.2331 | 30.2537 | 30.2366
GPK | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Total | Budget 2025
OB Removal (KBcm) | 575 | 605 | 640 | 620 | 700 | 685 | 745 | 790 | 785 | 880 | 705 | 770 | 8500 | 8500 | 100%
ARKA | 575 | 605 | 640 | 620 | 700 | 685 | 745 | 790 | 785 | 880 | 705 | 770 | 8500 | 8500
ROM Production (Kton) | 200 | 195 | 215 | 200 | 190 | 175 | 130 | 150 | 145 | 150 | 170 | 180 | 2100 | 2100 | 100%
ARKA | 152 | 142 | 152 | 140 | 121 | 126 | 101.5625 | 116.25 | 114.1875 | 104.2857 | 110.7429 | 115.9091 | 1495.9377 | 1467
SLS | 48 | 53 | 63 | 60 | 69 | 49 | 28.4375 | 33.75 | 30.8125 | 45.7143 | 59.2571 | 64.0909 | 604.0623 | 633
Other Contractor | [12 empty] | 0
SR ROM | 2.875 | 3.1026 | 2.9767 | 3.1 | 3.6842 | 3.9143 | 5.7308 | 5.2667 | 5.4138 | 5.8667 | 4.1471 | 4.2778 | 4.0476 | 4.0476
SR FC | 2.2115 | 2.75 | 2.9091 | 3.5429 | 3.8889 | 3.9143 | 10.6429 | 13.1667 | 8.7222 | 5.8667 | 3.0652 | 3.5 | 4.1463 | 4.1463
FC Production (Ktons) | 260 | 220 | 220 | 175 | 180 | 175 | 70 | 60 | 90 | 150 | 230 | 220 | 2050 | 2050
CV(GAR) | 3931.6483 | 3836.4397 | 3834.8511 | 3742.9497 | 3747.2197 | 3754.385 | 3723.7461 | 3728.5725 | 3750.4824 | 3819.915 | 3805.1584 | 3782.593 | 3804.2487 | 3727.504
TS | 0.15843 | 0.16162 | 0.14299 | 0.15284 | 0.15351 | 0.14793 | 0.16258 | 0.15862 | 0.15713 | 0.14501 | 0.17393 | 0.17583 | 0.15802 | 0.15227
Ash | 9.1172 | 6.5871 | 7.0916 | 8.0688 | 7.9587 | 8.146 | 9.3058 | 9.2219 | 8.632 | 6.4843 | 5.2903 | 6.0645 | 7.3927 | 7.9761
IM | 17.1384 | 22.5739 | 23.0887 | 25.1498 | 25.1086 | 24.0631 | 31.5483 | 32.1076 | 28.6479 | 26.0198 | 28.8494 | 28.5107 | 24.9548 | 26.0911
TM | 34.2287 | 38.0922 | 38.0435 | 37.9804 | 37.989 | 38.0992 | 37.8447 | 37.5012 | 37.9002 | 38.2716 | 39.2265 | 38.8933 | 37.7711 | 37.9133
TIS | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Total | Budget 2025
OB Removal (KBcm) | 855.3422 | 725.4173 | 831.4013 | 852.9917 | 895.6064 | 869.2178 | 898.1918 | 898.1918 | 869.2178 | 835.9632 | 755.0343 | 800.0606 | 10086.6361 | 12700.68 | 79.42%
PJPN | 855.3422 | 725.4173 | 831.4013 | 852.9917 | 895.6064 | 869.2178 | 898.1918 | 898.1918 | 869.2178 | 835.9632 | 755.0343 | 800.0606 | 10086.6361 | 12700.68
ROM Production (Kton) | 37.083 | 45.7818 | 49.8752 | 48.6999 | 53.9104 | 49.0446 | 53.7505 | 54.9281 | 52.4901 | 58.9393 | 47.0838 | 54.4135 | 606 | 606 | 100%
PJPN | 37.083 | 45.7818 | 49.8752 | 48.6999 | 53.9104 | 49.0446 | 53.7505 | 54.9281 | 52.4901 | 58.9393 | 47.0838 | 54.4135 | 606 | 606
SR ROM | 23.0656 | 15.8451 | 16.6696 | 17.5153 | 16.6129 | 17.723 | 16.7104 | 16.3521 | 16.5597 | 14.1835 | 16.036 | 14.7033 | 16.6446 | 20.9582
SR FC | 24.4383 | 16.1204 | 16.628 | 18.9554 | 16.2838 | 19.316 | 17.9638 | 16.3308 | 17.3844 | 15.1993 | 15.1007 | 14.5466 | 17.096 | 21.5266
FC Production (Ktons) | 35 | 45 | 50 | 45 | 55 | 45 | 50 | 55 | 50 | 55 | 50 | 55 | 590 | 590
TIS.HCV.HS | 35 | 45 | 50 | 45 | 55 | 45 | 50 | 55 | 50 | 55 | 50 | 55 | 590 | 351.8731
CV(GAR) | 6824.4902 | 6820.347 | 6806.1231 | 6833.9324 | 6994.3648 | 7027.769 | 7159.1562 | 7071.2557 | 6895.4537 | 6801.9028 | 6932.8199 | 6909.6969 | 6927.0747 | 6964.5927
TS | 1.6047 | 1.5533 | 1.6022 | 1.5399 | 1.5377 | 1.2556 | 1.2556 | 1.2956 | 1.1556 | 1.2556 | 1.1826 | 1.2556 | 1.3654 | 1.6046
Ash | 2.9538 | 3.1342 | 3.1952 | 3.3935 | 3.2981 | 2.807 | 2.8034 | 3.0056 | 2.6377 | 2.8831 | 2.5935 | 2.6437 | 2.9417 | 3.3562
IM | 4.4328 | 4.5235 | 4.5521 | 4.5577 | 4.7566 | 4.5533 | 4.6037 | 4.8186 | 4.569 | 4.9642 | 4.6397 | 4.7277 | 4.6553 | 6.0188
TM | 9.2954 | 9.5623 | 9.5267 | 9.173 | 7.383 | 7.412 | 7.6268 | 7.9623 | 9.8486 | 10.6281 | 9.9458 | 10.1123 | 9.0408 | 7.5848
Note on A8: Belfry Parulian Pandiangan: include high ash
Note on A86: Belfry Parulian Pandiangan: incoming coal volume (quality is not as actual but as range in contract)
Note on A92: Belfry Parulian Pandiangan: incoming coal volume (quality is not as actual but as range in contract)
Note on A100: Belfry Parulian Pandiangan: include Mud
Note on A125: Belfry Parulian Pandiangan: include Mud and sliding volume

## BudgVSact. June (hidden)
SITES | OB |  | ROM |  | FC |  | SR (OB/ROM) |  | Diff. (Act.%)
| Budget | Actual | Budget | Actual | Budget | Actual | Budget | Actual | OB | ROM
IMM | 45360.0431 | 45598.8131 | 3295 | 3331.5648 | 3275.5 | 3397.75 | 13.7663 | 13.6869 | 100.5% | 101.1%
TCM | 25550 | 23685 | 1487 | 1504 | 1562 | 1582 | 17.1822 | 15.748 | 92.7% | 101.1%
BEK | 45094 | 46285 | 3966.5 | 4250 | 4050 | 4245 | 11.3687 | 10.8906 | 102.6% | 107.1%
JBG | 1603.028 | 294.136 | 57 | 0 | 53 | 0 | 28.1233 | #DIV/0! | 18.35% | 0%
GPK | 3825 | 3825 | 1062 | 1175 | 1100 | 1230 | 3.6017 | 3.2553 | 100% | 110.6%
TIS | 5910.67 | 5029.9767 | 265 | 284.3948 | 245 | 275 | 22.3044 | 17.6866 | 85.1% | 107.3%
TOTAL | 127342.7411 | 124717.9258 | 10132.5 | 10544.9597 | 10285.5 | 10729.75 | 12.5678 | 11.8273 | 97.94% | 104.1%
|  |  |  | 104.1% |  | 104.3%