## Budget 2025
ITM plan year 2024 | 1000
As of 18 Nov'24
IMM | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Total
OB Removal (KBcm) | 7619.4483 | 7224.3023 | 6870.0231 | 7815.9147 | 8233.4755 | 7596.8792 | 8769.11 | 8498.0492 | 8442.1757 | 8242.1086 | 7836.3005 | 7566.691 | 94714.4782 | Done
PAMA (WB) | 2904.786 | 2754.4503 | 2424.321 | 2767.1447 | 2927.6178 | 2460.4194 | 3157.9028 | 3107.2173 | 2899.6426 | 2829.8233 | 2690.1553 | 2609.1784 | 33532.659
PAMA (EB) | 4714.6622 | 4469.852 | 4445.7021 | 5048.77 | 5305.8577 | 5136.4598 | 5611.2072 | 5390.8319 | 5542.5331 | 5412.2853 | 5146.1452 | 4957.5126 | 61181.8192
ROM Production (Kton) | 537.5 | 532.5 | 537.5 | 537.5 | 537.5 | 537.5 | 610 | 625 | 625 | 625 | 625 | 620 | 6950
PAMA (WB) | 192.5 | 187.5 | 192.5 | 190 | 185 | 155 | 130 | 135 | 145 | 110 | 120 | 120 | 1862.5
PAMA (EB) | 345 | 345 | 345 | 347.5 | 352.5 | 382.5 | 480 | 490 | 480 | 515 | 505 | 500 | 5087.5
Fine Coal | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SR ROM Total | 14.1757 | 13.5668 | 12.7814 | 14.5412 | 15.3181 | 14.1337 | 14.3756 | 13.5969 | 13.5075 | 13.1874 | 12.5381 | 12.2043 | 13.628
FC Product (Kton) | 541.75 | 536.75 | 541.75 | 551.75 | 551.75 | 551.75 | 635.75 | 637.75 | 637.75 | 637.75 | 637.75 | 637.75 | 7100
PAMA (WB) | 192.5 | 187.5 | 192.5 | 190 | 185 | 155 | 130 | 135 | 145 | 110 | 120 | 120 | 1862.5
PAMA (EB) | 345 | 345 | 345 | 349 | 354 | 384 | 493 | 490 | 480 | 515 | 505 | 505 | 5110
Fine Coal | 4.25 | 4.25 | 4.25 | 12.75 | 12.75 | 12.75 | 12.75 | 12.75 | 12.75 | 12.75 | 12.75 | 12.75 | 127.5
SR FC Total | 14.0645 | 13.4593 | 12.6812 | 14.1657 | 14.9225 | 13.7687 | 13.7933 | 13.325 | 13.2374 | 12.9237 | 12.2874 | 11.8647 | 13.3401
IMM-WB.HCV.LS | 154.9822 | 150.1922 | 153.4446 | 142.7318 | 131.892 | 90.2567 | 45.0528 | 60.1041 | 62.6233 | 73.6379 | 78.4656 | 85.4199 | 1228.8032
CV(GAR) | 6066.6995 | 6061.099 | 6072.9614 | 6113.1737 | 6106.3251 | 6216.0563 | 6397.4706 | 6374.5335 | 6369.463 | 6395.7374 | 6207.9868 | 6224.9984 | 6169.7769
TS | 0.79939 | 0.7996 | 0.80631 | 0.80238 | 0.79513 | 0.79814 | 0.80006 | 0.80071 | 0.80424 | 0.87778 | 0.89103 | 0.79705 | 0.8108
Ash | 8.5932 | 8.5723 | 8.4653 | 8.3497 | 8.4545 | 8.0612 | 8.0877 | 8.0139 | 8.0939 | 8.3113 | 8.6583 | 8.1212 | 8.3746
Moist | 8.4968 | 8.6036 | 8.5701 | 8.2959 | 8.436 | 8.1042 | 7.1125 | 7.0457 | 7.1276 | 7.1603 | 7.2147 | 7.5403 | 8.0403
TM | 13.5221 | 13.629 | 13.5955 | 13.3212 | 13.4614 | 13.1296 | 12.1378 | 12.0711 | 12.153 | 12.1857 | 12.24 | 12.5656 | 13.0657
IMM-WB.HCV.HS | 37.5178 | 37.3078 | 39.0554 | 47.2682 | 53.108 | 64.7433 | 84.9472 | 74.8959 | 82.3767 | 36.3621 | 41.5344 | 34.5801 | 633.6968
CV(GAR) | 5995.4058 | 6102.8668 | 6012.8803 | 5956.2491 | 5900.982 | 5903.8514 | 5953.1501 | 5935.2903 | 5994.0694 | 5972.607 | 5974.5067 | 5973.0938 | 5965.7827
TS | 2.4296 | 2.4051 | 2.5319 | 2.5966 | 2.6453 | 2.7647 | 2.7578 | 2.7055 | 2.6432 | 2.4887 | 2.3842 | 1.9722 | 2.579
Ash | 13.6503 | 13.0727 | 13.5362 | 14.1977 | 14.7482 | 14.5558 | 13.6829 | 14.4235 | 13.8303 | 13.8021 | 13.9633 | 13.2396 | 13.9606
Moist | 6.0447 | 6.0271 | 6.0381 | 6.067 | 6.0651 | 7.0545 | 6.8576 | 6.9141 | 7.1513 | 7.5031 | 7.5101 | 7.1237 | 6.744
TM | 11.07 | 11.0525 | 11.0635 | 11.0924 | 11.0904 | 12.0799 | 11.883 | 11.9395 | 12.1767 | 12.5284 | 12.5355 | 12.1491 | 11.7694
IMM-EB.MCV.LS | 3.3846 | 2.1986 | 2.3031 | 2.7672 | 1.8759 | 1.1106 | 0 | 0 | 0 | 0 | 0 | 0 | 13.6399
CV(GAR) | 5821.883 | 5816.4871 | 5824.2204 | 5826.2223 | 5821.6228 | 5824.0809 | 0 | 0 | 0 | 0 | 0 | 0 | 5822.4314
TS | 0.89813 | 0.89994 | 0.9013 | 0.90153 | 0.90292 | 0.90326 | 0 | 0 | 0 | 0 | 0 | 0 | 0.90072
Ash | 8.6642 | 8.6538 | 8.6424 | 8.5289 | 8.516 | 8.5015 | 0 | 0 | 0 | 0 | 0 | 0 | 8.5978
Moist | 11.333 | 11.3369 | 11.3693 | 11.3501 | 11.3996 | 11.3577 | 0 | 0 | 0 | 0 | 0 | 0 | 11.3544
TM | 16.333 | 16.3369 | 16.3693 | 16.3501 | 16.3996 | 16.3577 | 0 | 0 | 0 | 0 | 0 | 0 | 16.3544
IMM-EB.MCV.MS | 2.5219 | 7.2155 | 26.7201 | 6.3272 | 12.6302 | 4.8088 | 12.095 | 14.9981 | 83.6973 | 94.4006 | 71.3353 | 85.9656 | 422.7155
CV(GAR) | 6013.744 | 5958.5719 | 6011.5142 | 6033.7912 | 5987.1311 | 6002.8141 | 6036.2059 | 6005.6296 | 5996.4183 | 6012.5832 | 6026.6617 | 6027.4417 | 6013.6725
TS | 1.5719 | 1.5705 | 1.5645 | 1.5541 | 1.5514 | 1.5491 | 1.5706 | 1.5667 | 1.5493 | 1.5533 | 1.5598 | 1.5724 | 1.5595
Ash | 6.0748 | 6.1531 | 6.1792 | 5.1976 | 5.2946 | 5.2369 | 5.1053 | 5.3674 | 5.3569 | 5.1697 | 5.1649 | 5.301 | 5.3287
Moist | 10.1273 | 10.2338 | 10.5326 | 10.3526 | 10.7819 | 10.4813 | 10.3659 | 10.4684 | 10.4436 | 10.274 | 10.2404 | 9.9508 | 10.2792
TM | 15.1273 | 15.2338 | 15.5326 | 15.3526 | 15.7819 | 15.4813 | 15.3659 | 15.4684 | 15.4436 | 15.274 | 15.2404 | 14.9508 | 15.2792
IMM-EB.MCV.HS | 339.0935 | 335.5859 | 315.9768 | 339.9056 | 339.494 | 378.0807 | 480.905 | 475.0019 | 396.3027 | 420.5994 | 433.6647 | 419.0344 | 4673.6446
CV(GAR) | 5916.7973 | 5925.4345 | 5916.7949 | 5912.981 | 5924.7515 | 5924.6893 | 5904.2294 | 5885.0998 | 5912.8315 | 5911.5994 | 5931.5837 | 5905.9088 | 5914.4155
TS | 2.4966 | 2.3878 | 2.3758 | 2.4776 | 2.3743 | 2.3234 | 2.4258 | 2.4636 | 2.4167 | 2.4358 | 2.3206 | 2.4316 | 2.4107
Ash | 5.9843 | 5.6663 | 5.7801 | 5.6993 | 5.574 | 5.7147 | 5.7035 | 5.9277 | 5.6702 | 5.6371 | 5.5902 | 5.6939 | 5.72
Moist | 10.2836 | 10.5562 | 10.6838 | 10.4873 | 10.6898 | 10.7239 | 10.6197 | 10.5236 | 10.4781 | 10.4971 | 10.5525 | 10.6017 | 10.5582
TM | 15.2836 | 15.5562 | 15.6838 | 15.4873 | 15.6898 | 15.7239 | 15.6197 | 15.5236 | 15.4781 | 15.4971 | 15.5525 | 15.6017 | 15.5582
Fine Coal | 4.25 | 4.25 | 4.25 | 12.75 | 12.75 | 12.75 | 12.75 | 12.75 | 12.75 | 12.75 | 12.75 | 12.75 | 127.5
CV(GAR) | 3146.0674 | 3146.0674 | 3146.0674 | 3146.0674 | 3146.0674 | 3146.0674 | 3146.0674 | 3146.0674 | 3146.0674 | 3146.0674 | 3146.0674 | 3146.0674 | 3146.0674
TS | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Ash | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40
Moist | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11
TM | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20
TCM | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Total
OB Removal (KBcm) | 4195 | 4015 | 4020 | 4250 | 4410 | 4660 | 4720 | 5055 | 4740 | 3990 | 3805 | 3790 | 51650 | Done
PAMA | 2025 | 1905 | 1870 | 2010 | 2110 | 2210 | 2320 | 2305 | 2240 | 1890 | 1745 | 1770 | 24400
MAP | 890 | 810 | 750 | 940 | 950 | 950 | 1000 | 1050 | 950 | 900 | 860 | 950 | 11000
PJPN | 1280 | 1300 | 1400 | 1300 | 1350 | 1500 | 1400 | 1700 | 1550 | 1200 | 1200 | 1070 | 16250
ROM Production (Kton) | 200 | 215 | 217 | 255 | 285 | 315 | 310 | 335.387 | 307 | 300 | 281 | 280 | 3300.387
PAMA | 130 | 145 | 150 | 160 | 170 | 200 | 195 | 210 | 210 | 195 | 180 | 185 | 2130
MAP | 45 | 40 | 37 | 45 | 50 | 50 | 50 | 55 | 47 | 45 | 41 | 45 | 550
PJPN | 25 | 30 | 30 | 50 | 65 | 65 | 65 | 70.387 | 50 | 60 | 60 | 50 | 620.387
SR ROM with void | 20.975 | 18.6744 | 18.5253 | 16.6667 | 15.4737 | 14.7937 | 15.2258 | 15.0721 | 15.4397 | 13.3 | 13.5409 | 13.5357 | 15.6497
FC Product CP (Kton) | 217 | 235 | 258 | 257 | 290 | 305 | 315 | 320 | 285 | 253 | 242 | 253 | 3230
TCM.HCV.LS | 110 | 130 | 130 | 140 | 150 | 170 | 170 | 150 | 155 | 115 | 115 | 95 | 1630
TCM.HCV.HS | 100 | 100 | 120 | 110 | 130 | 120 | 130 | 150 | 120 | 130 | 120 | 150 | 1480
TCM.HCV.MS | 7 | 5 | 8 | 7 | 10 | 15 | 15 | 20 | 10 | 8 | 7 | 8 | 120
FC Product 3rd party (Kton) | 139.1 | 139.4 | 138.6 | 138.1 | 139 | 138.3 | 138.5 | 137.7 | 145.6 | 146.2 | 138.3 | 137.7 | 1676.5
EBH.HCV.LS | 56.6 | 56.9 | 56.1 | 55.6 | 56.5 | 55.8 | 56 | 55.2 | 55.6 | 56.2 | 55.8 | 55.2 | 671.5
MBL.MCV.MS | 82.5 | 82.5 | 82.5 | 82.5 | 82.5 | 82.5 | 82.5 | 82.5 | 90 | 90 | 82.5 | 82.5 | 1005
SR FC | 19.3318 | 17.0851 | 15.5814 | 16.537 | 15.2069 | 15.2787 | 14.9841 | 15.7969 | 16.6316 | 15.7708 | 15.7231 | 14.9802 | 15.9907
TCM.HCV.LS | 110 | 130 | 130 | 140 | 150 | 170 | 170 | 150 | 155 | 115 | 115 | 95 | 1630
CV(GAR) | 6331.7794 | 6327.6426 | 6345.3425 | 6327.8237 | 6373.2296 | 6243.3002 | 6268.7387 | 6402.2298 | 6455.744 | 6429.1851 | 6453.9309 | 6360.7189 | 6355.6513
Sul < 0.7 | 0.63239 | 0.69248 | 0.652 | 0.6548 | 0.61487 | 0.6376 | 0.63464 | 0.55063 | 0.52383 | 0.52786 | 0.54698 | 0.54361 | 0.60341
ASH < 5.0 | 5.14 | 4.5591 | 4.5963 | 5.1237 | 4.8279 | 4.5406 | 5.4694 | 4.9514 | 4.2318 | 4.7988 | 4.93 | 4.9975 | 4.8411
IM | 7.9684 | 7.5074 | 7.3053 | 7.3142 | 7.2934 | 7.0845 | 7.3044 | 7.5576 | 7.1827 | 7.4775 | 7.325 | 7.6231 | 7.3863
TM | 13.5018 | 14.5066 | 14.2007 | 13.7425 | 13.7596 | 15.8885 | 14.3471 | 13.1866 | 13.1296 | 12.9827 | 12.4646 | 13.5285 | 13.8465
TCM.HCV.HS | 100 | 100 | 120 | 110 | 130 | 120 | 130 | 150 | 120 | 130 | 120 | 150 | 1480
CV(GAR) | 6528.8013 | 6523.441 | 6602.1856 | 6481.0855 | 6487.5274 | 6515.5714 | 6445.0323 | 6472.1448 | 6412.4032 | 6476.7335 | 6460.6228 | 6423.2952 | 6482.812
Sul < 2.0 | 1.8419 | 2.1454 | 1.7213 | 1.772 | 1.7758 | 2.0871 | 1.8138 | 1.8287 | 1.8482 | 1.8968 | 1.819 | 1.9905 | 1.8762
ASH < 5.0 | 6.7257 | 7.6729 | 55.9656 | 5.9371 | 5.2918 | 7.3265 | 5.9375 | 5.9832 | 6.008 | 6.0191 | 6.0931 | 5.979 | 10.2546
IM | 7.2396 | 7.118 | 6.7065 | 6.8833 | 6.7129 | 6.6877 | 6.6455 | 6.3583 | 6.7264 | 6.4663 | 6.2063 | 6.1537 | 6.6258
TM | 11.8026 | 10.6165 | 10.6667 | 11.5389 | 11.4782 | 10.0232 | 11.715 | 11.1861 | 11.926 | 11.4844 | 11.0808 | 11.4168 | 11.2522
TCM.LCV.MS.HA | 7 | 5 | 8 | 7 | 10 | 15 | 15 | 20 | 10 | 8 | 7 | 8 | 120
CV(GAR) | 3581.7631 | 3599.0009 | 4341.3047 | 3587.2263 | 3651.2002 | 5641.0449 | 5567.1958 | 5442.6121 | 5422.5222 | 5471.7948 | 5388.109 | 5438.9485 | 4963.5346
Sul < 1.2 | 1.16 | 1.15 | 1.44 | 0.51 | 0.5 | 1.45 | 1.5217 | 1.5933 | 1.6133 | 1.5833 | 1.5533 | 1.6133 | 1.3582
ASH < 5.0 | 13.6 | 13.18 | 12.69 | 14.445 | 14.2 | 6.835 | 8.9933 | 11.1517 | 11.1417 | 11.0117 | 11.1717 | 11.9817 | 11.1647
IM | 7.41 | 7.54 | 7.16 | 6.52 | 6.43 | 6.09 | 6.1267 | 6.1633 | 6.1633 | 6.1633 | 6.1633 | 6.1633 | 6.3891
TM | 13.89 | 14.11 | 14.412 | 13.208 | 13.588 | 13.532 | 13.3947 | 14.0533 | 14.0233 | 13.9833 | 14.4533 | 14.0533 | 13.8507
EBH.HCV.LS | 56.6 | 56.9 | 56.1 | 55.6 | 56.5 | 55.8 | 56 | 55.2 | 55.6 | 56.2 | 55.8 | 55.2 | 671.5
CV(GAR) | 6322 | 6322 | 6322 | 6322 | 6322 | 6322 | 6322 | 6322 | 6322 | 6322 | 6322 | 6322 | 6322
Sul < 1 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6
ASH | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7
IM | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12
TM | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14
MBL.MCV.MS | 82.5 | 82.5 | 82.5 | 82.5 | 82.5 | 82.5 | 82.5 | 82.5 | 90 | 90 | 82.5 | 82.5 | 1005
CV(GAR) | 5400 | 5400 | 5400 | 5400 | 5400 | 5400 | 5400 | 5400 | 5400 | 5400 | 5400 | 5400 | 5400
Sul < 1.2 | [12 empty] | 1 | bar: Jan to Dec
ASH | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6
IM | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15
TM | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24
BEK | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Total
OB Removal (KBcm) | 7995 | 7084 | 7619 | 7232 | 7571 | 7593 | 8097 | 8330 | 7698 | 7482 | 6860 | 7389 | 90950 | Done
TRUST | 2085 | 1784 | 1974 | 1997 | 1991 | 1968 | 2132 | 2305 | 2063 | 2062 | 1755 | 1884 | 24000
PAMA | 4250 | 3810 | 4105 | 4235 | 4480 | 4475 | 4785 | 4825 | 4495 | 4420 | 4115 | 4455 | 52450
SNS | 1660 | 1490 | 1540 | 1000 | 1100 | 1150 | 1180 | 1200 | 1140 | 1000 | 990 | 1050 | 14500
ROM Production (Kton) | 684 | 658 | 685.5 | 564 | 663 | 712 | 745 | 752 | 704 | 627.5 | 589 | 616 | 8000
TRUST | 194 | 188 | 185.5 | 156 | 196 | 212 | 245 | 252 | 234 | 192.5 | 169 | 176 | 2400
PAMA | 360 | 350 | 375 | 335 | 380 | 415 | 375 | 400 | 370 | 350 | 340 | 350 | 4400
SNS | 130 | 120 | 125 | 73 | 87 | 85 | 125 | 100 | 100 | 85 | 80 | 90 | 1200
SR ROM | 11.6886 | 10.766 | 11.1145 | 12.8227 | 11.4193 | 10.6643 | 10.8685 | 11.0771 | 10.9347 | 11.9235 | 11.6469 | 11.9951 | 11.3688
SR FC | 11.4214 | 10.12 | 10.8843 | 11.1262 | 11.6477 | 11.6815 | 11.5671 | 11.7324 | 10.9971 | 11.3364 | 10.7188 | 11.5453 | 11.2284
FC Product (KTons) | 700 | 700 | 700 | 650 | 650 | 650 | 700 | 710 | 700 | 660 | 640 | 640 | 8100
BEK.HCV.LS | 400 | 480 | 480 | 465 | 465 | 460 | 500 | 490 | 480 | 460 | 440 | 440 | 5560
CV(GAR) | 6030.4358 | 5774.2277 | 5860.9708 | 5868.1864 | 5954.6027 | 5916.1255 | 5984.187 | 5944.3266 | 5921.0085 | 5916.7362 | 5898.291 | 5928.9325 | 5915.2264
TS | 0.53158 | 0.52889 | 0.5114 | 0.47877 | 0.51889 | 0.54684 | 0.6156 | 0.65164 | 0.57083 | 0.61028 | 0.68843 | 0.67517 | 0.5772
Ash | 4.5798 | 4.3819 | 4.7059 | 4.7159 | 4.47 | 4.6727 | 5.1675 | 5.2807 | 5.3764 | 5.2082 | 4.9555 | 5.0376 | 4.8848
IM | 11.5325 | 12.1617 | 11.7688 | 10.9822 | 11.9963 | 11.3734 | 10.8514 | 11.2599 | 11.1283 | 11.3129 | 11.8103 | 11.5197 | 11.4694
TM | 16.0731 | 18.3447 | 16.1139 | 15.2818 | 15.685 | 15.0345 | 13.9867 | 14.31 | 14.2913 | 14.4636 | 14.865 | 14.5485 | 15.2419
BEK.HCV.HS | 300 | 220 | 220 | 185 | 185 | 190 | 200 | 220 | 220 | 200 | 200 | 200 | 2540
CV(GAR) | 5978.3055 | 5788.4874 | 5780.4749 | 5757.1239 | 5689.0306 | 5723.4269 | 5710.0663 | 5767.3036 | 5816.7184 | 5783.944 | 5714.3882 | 5899.7671 | 5792.8232
TS | 1.787 | 1.8051 | 1.7535 | 1.753 | 1.7123 | 1.7854 | 1.8239 | 1.742 | 1.7014 | 1.7606 | 1.7678 | 1.7233 | 1.7606
Ash | 4.7301 | 5.5271 | 5.5458 | 5.7433 | 6.1338 | 6.4532 | 6.4437 | 6.2121 | 5.7608 | 5.8895 | 6.1089 | 5.112 | 5.7572
IM | 11.0894 | 10.939 | 11.1033 | 10.7531 | 10.9318 | 10.5429 | 10.9263 | 10.5327 | 10.5196 | 10.609 | 10.4098 | 10.3006 | 10.7369
TM | 14.7767 | 14.7885 | 14.9686 | 14.6226 | 15.0392 | 14.4524 | 14.7662 | 14.3018 | 14.2251 | 14.4043 | 14.4451 | 13.7474 | 14.5518
JBG | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Total
OB Removal (KBcm) | 103.007 | 93.07 | 98.059 | 280.6245 | 579.3785 | 448.889 | 536.383 | 575.345 | 590.094 | 632.103 | 557.72 | 543.935 | 5038.608 | Done
Contractor Pit UCE ext | 103.007 | 93.07 | 98.059 | 280.6245 | 579.3785 | 448.889 | 536.383 | 575.345 | 590.094 | 632.103 | 557.72 | 543.935 | 5038.608
ROM Production (Kton) | 0 | 0 | 0 | 0 | 20 | 37 | 51 | 60 | 70 | 75 | 68 | 67 | 448
Contractor Pit UCE ext | 0 | 0 | 0 | 0 | 20 | 37 | 51 | 60 | 70 | 75 | 68 | 67 | 448
SR ROM | 0 | 0 | 0 | 0 | 28.9689 | 12.1321 | 10.5173 | 9.5891 | 8.4299 | 8.428 | 8.2018 | 8.1184 | 11.2469
SR FC | 0 | 0 | 0 | 0 | 32.1877 | 12.8254 | 10.7277 | 9.9197 | 8.6779 | 8.7792 | 8.4503 | 8.2414 | 11.6365
JBG Coal Loading | 14.6 | 14.6 | 7.3 | 7.3 | 21.9 | 36.5 | 43.8 | 58.4 | 58.4 | 58.4 | 58.4 | 51.1 | 430.7
JBG FC Product (Kton) / JBG | 0 | 0 | 0 | 0 | 18 | 35 | 50 | 58 | 68 | 72 | 66 | 66 | 433
CV(GAR) | 0 | 0 | 0 | 0 | 4442.3525 | 4414.0197 | 4416.3842 | 4432.5862 | 4408.926 | 4423.0872 | 4453.786 | 4407.9045 | 4423.7946
TS | 0 | 0 | 0 | 0 | 0.38874 | 0.35403 | 0.38864 | 0.37486 | 0.36433 | 0.35476 | 0.35693 | 0.38386 | 0.36899
Ash | 0 | 0 | 0 | 0 | 4.3469 | 4.2775 | 4.5772 | 4.4107 | 4.3138 | 4.438 | 4.3733 | 4.6218 | 4.4323
IM | 0 | 0 | 0 | 0 | 17.434 | 17.2038 | 17.034 | 16.8716 | 16.9773 | 16.7251 | 16.9357 | 16.7621 | 16.9259
TM | 0 | 0 | 0 | 0 | 30.1867 | 30.2656 | 30.3349 | 30.2198 | 30.2331 | 30.2451 | 30.1783 | 30.2279 | 30.2366
GPK | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Total
OB Removal (KBcm) | 630 | 580 | 630 | 610 | 700 | 675 | 745 | 790 | 785 | 880 | 705 | 770 | 8500 | Done
ARKA | 630 | 580 | 630 | 610 | 700 | 675 | 745 | 790 | 785 | 880 | 705 | 770 | 8500
ROM Production (Kton) | 184 | 166 | 182 | 175 | 180 | 175 | 160 | 160 | 160 | 196 | 175 | 187 | 2100
ARKA | 119 | 108 | 118 | 114 | 131 | 127 | 125 | 124 | 126 | 139 | 114 | 122 | 1467
SLS | 65 | 58 | 64 | 61 | 49 | 48 | 35 | 36 | 34 | 57 | 61 | 65 | 633
SR ROM | 3.4239 | 3.494 | 3.4615 | 3.4857 | 3.8889 | 3.8571 | 4.6562 | 4.9375 | 4.9062 | 4.4898 | 4.0286 | 4.1176 | 4.0476
SR FC | 3.15 | 3.2222 | 3.3158 | 3.4857 | 3.8889 | 3.8571 | 8.2778 | 15.8 | 8.7222 | 4.1905 | 2.7115 | 3.08 | 4.1463
FC Production (Ktons) | 200 | 180 | 190 | 175 | 180 | 175 | 90 | 50 | 90 | 210 | 260 | 250 | 2050
CV(GAR) | 3597.7504 | 3594.5296 | 3663.6762 | 3731.5323 | 3747.0877 | 3753.0309 | 3709.9842 | 3710.8591 | 3754.9789 | 3802.469 | 3810.8052 | 3790.9104 | 3727.504
TS | 0.11569 | 0.11701 | 0.15581 | 0.15133 | 0.15302 | 0.14876 | 0.16964 | 0.1691 | 0.15833 | 0.16553 | 0.17248 | 0.16287 | 0.15227
Ash | 10.1457 | 10.2139 | 9.4792 | 8.2664 | 7.972 | 8.1087 | 9.7175 | 9.7409 | 8.5788 | 6.4456 | 5.4512 | 5.9086 | 7.9761
IM | 27.2738 | 27.292 | 26.9771 | 25.1243 | 25.0639 | 24.2542 | 31.6027 | 31.4781 | 27.5216 | 26.4417 | 28.9143 | 29.0422 | 27.2546
TM | 37.9185 | 37.923 | 38.043 | 37.9509 | 37.979 | 38.0738 | 37.7175 | 37.7338 | 37.8637 | 38.4165 | 39.0685 | 39.1676 | 38.2852
TIS | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Total
OB Removal (KBcm) | 767.6336 | 734.7931 | 815.1462 | 831.0273 | 859.4709 | 916.3581 | 1023.2017 | 1020.3858 | 1007.9939 | 961.3227 | 867.198 | 903.6556 | 10708.1867 | Done
Contractor | 767.6336 | 734.7931 | 815.1462 | 831.0273 | 859.4709 | 916.3581 | 1023.2017 | 1020.3858 | 1007.9939 | 961.3227 | 867.198 | 903.6556 | 10708.1867
ROM Production (Kton) | 40.6021 | 37.5931 | 41.6296 | 45.5535 | 50.2535 | 55.2541 | 61.4542 | 61.231 | 61.1144 | 55.8895 | 46.816 | 48.6088 | 605.9999
Contractor | 40.6021 | 37.5931 | 41.6296 | 45.5535 | 50.2535 | 55.2541 | 61.4542 | 61.231 | 61.1144 | 55.8895 | 46.816 | 48.6088 | 605.9999
SR ROM | 18.9063 | 19.5459 | 19.5809 | 18.2429 | 17.1027 | 16.5844 | 16.6498 | 16.6645 | 16.4936 | 17.2004 | 18.5235 | 18.5904 | 17.6703
SR FC | 23.9885 | 26.2426 | 20.3787 | 20.7757 | 17.1894 | 16.6611 | 17.0534 | 17.0064 | 17.9999 | 16.022 | 15.7672 | 16.4301 | 18.1188
FC Production (Ktons) | 32 | 28 | 40 | 40 | 50 | 55 | 60 | 60 | 56 | 60 | 55 | 55 | 591
CV(GAR) | 6898.8055 | 6898.8055 | 6898.8055 | 7061.2455 | 7061.2455 | 7061.2455 | 6892.9578 | 6892.9578 | 6930.9674 | 6803.0068 | 6804.9228 | 6822.1666 | 6914.9248
TS | 1.2251 | 1.1251 | 1.0112 | 0.95955 | 0.95955 | 0.91395 | 0.84903 | 0.85955 | 0.8749 | 1.0751 | 1.0129 | 1.0815 | 0.97968
Ash | 3.7895 | 3.7895 | 3.7895 | 3.6003 | 3.6003 | 3.6003 | 3.8711 | 3.8711 | 3.8711 | 3.7895 | 3.7895 | 3.7895 | 3.7674
TM | 8.7195 | 8.7195 | 8.7195 | 7.3393 | 7.3393 | 7.3393 | 9.7585 | 9.7585 | 9.7585 | 8.7195 | 8.7195 | 8.7195 | 8.6903
IM | 4.7164 | 4.7164 | 4.7164 | 4.4047 | 4.4047 | 4.4047 | 5.0329 | 5.0329 | 5.0329 | 4.7164 | 4.7164 | 4.7164 | 4.7342
NPR | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Total
OB Removal (KBcm) | 0 | 0 | 129 | 535 | 542 | 543 | 586 | 594 | 578 | 752 | 682 | 742.5 | 5683.5 | Done
Contractor | 0 | 0 | 129 | 535 | 542 | 543 | 586 | 594 | 578 | 752 | 682 | 742.5 | 5683.5
ROM Production (Kton) | 0 | 0 | 0 | 0 | 25 | 55 | 60 | 60 | 55 | 65 | 65 | 65 | 450
Contractor | 0 | 0 | 0 | 0 | 25 | 55 | 60 | 60 | 55 | 65 | 65 | 65 | 450
SR ROM | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 21.68 | 9.8727 | 9.7667 | 9.9 | 10.5091 | 11.5692 | 10.4923 | 11.4231 | 12.63
SR FC | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 31.8824 | 14.6757 | 14.65 | 14.85 | 15.6216 | 17.4884 | 15.8605 | 17.2674 | 18.945
FC Production (Ktons) | 0 | 0 | 0 | 0 | 17 | 37 | 40 | 40 | 37 | 43 | 43 | 43 | 300
CV(GAD) | 0 | 0 | 0 | 0 | 6479.8736 | 6587.4532 | 6598.4997 | 6640.8571 | 6546.9132 | 6622.5542 | 6577.0752 | 6514.6914 | 5016.4003
TS | 0 | 0 | 0 | 0 | 1.1963 | 1.2298 | 1.1899 | 1.1598 | 1.0431 | 1.0999 | 1.0172 | 0.99869 | 0.85231
Ash | 0 | 0 | 0 | 0 | 6.1898 | 6.1677 | 6.5217 | 6.2198 | 5.498 | 6.2002 | 5.4953 | 5.9413 | 4.606
IM |  |  |  | 0 | 8.626 | 7.4 | 6.7387 | 6.6266 | 8.5113 | 6.8655 | 8.0495 | 8.45 | 5.8143
TM | 0 | 0 | 0 | 0 | 14.7805 | 14.414 | 14.3683 | 14.3998 | 15.0003 | 14.3847 | 15.0759 | 15.0952 | 11.202

## Outlook 1+11
ITM outlook 2025 (1+11)
| Act. | Out. | Out. | Out. | Out. | Out. | Out. | Out. | Out. | Out. | Out. | Out. | Out.
IMM | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Total | Budget 2025
OB Removal (KBcm) | 6763.0376 | 7204.7792 | 6917.9241 | 7858.7341 | 8278.4905 | 7640.614 | 8789.2468 | 8512.679 | 8487.7924 | 8535.8485 | 8136.9468 | 8079.457 | 95205.55 | 94714.4782 | 100.5%
PAMA (WB) | 2244.6941 | 2615.5034 | 2447.1295 | 2781.4178 | 2942.6228 | 2717.2507 | 3166.2637 | 3121.8471 | 2945.2593 | 3007.1905 | 2874.4289 | 2837.4709 | 33701.0787 | 33532.659
PAMA (EB) | 4518.3435 | 4589.2758 | 4470.7946 | 5077.3162 | 5335.8677 | 4923.3633 | 5622.9831 | 5390.8319 | 5542.5331 | 5528.658 | 5262.518 | 5241.9861 | 61504.4713 | 61181.8192
ROM Production (Kton) | 542.8336 | 554.2083 | 540 | 545 | 545 | 545 | 610 | 625 | 625 | 625 | 625 | 627.9581 | 7010 | 6950 | 100.9%
PAMA (WB) | 158.4259 | 168.7195 | 170 | 160 | 175 | 150 | 140.3001 | 145 | 130 | 115 | 110 | 110.0541 | 1732.4996 | 1862.5
PAMA (EB) | 384.4077 | 385.4888 | 370 | 385 | 370 | 395 | 469.6999 | 480 | 495 | 510 | 515 | 517.904 | 5277.5004 | 5087.5
Fine Coal (WB) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SR ROM Total | 12.4588 | 13.0001 | 12.811 | 14.4197 | 15.1899 | 14.0195 | 14.4086 | 13.6203 | 13.5805 | 13.6574 | 13.0191 | 12.8662 | 13.5814 | 13.628
FC Product (Kton) | 612.6829 | 575 | 575 | 554.25 | 559.25 | 559.25 | 625.75 | 637.75 | 637.75 | 607 | 607 | 584.3171 | 7135 | 7100
PAMA (WB) | 203.8423 | 185 | 185 | 165 | 175 | 150 | 150.3001 | 145 | 130 | 100 | 95 | 45.8576 | 1730 | 1862.5
PAMA (EB) | 408.8406 | 390 | 385.75 | 385 | 380 | 396.5 | 462.6999 | 480 | 495 | 494.25 | 499.25 | 525.7095 | 5303 | 5110
Fine Coal | 0 | 0 | 4.25 | 4.25 | 4.25 | 12.75 | 12.75 | 12.75 | 12.75 | 12.75 | 12.75 | 12.75 | 102 | 127.5
SR FC Total | 11.0384 | 12.5301 | 12.0312 | 14.179 | 14.8028 | 13.6623 | 14.0459 | 13.348 | 13.309 | 14.0624 | 13.4052 | 13.8272 | 13.3435 | 13.3401
IMM-WB.HCV.LS | 146.1825 | 128 | 125.948 | 122.7237 | 119.2849 | 71.0619 | 79.5866 | 67.2846 | 60.5097 | 63.6341 | 63.9549 | 37.8697 | 1086.0407 | 1228.8032
CV(GAR) | 6193.9879 | 5991.2568 | 6037.821 | 6105.4869 | 6103.386 | 6194.7244 | 6206.0096 | 6387.6667 | 6374.9065 | 6403.0078 | 6240.9311 | 6226.0716 | 6171.1702 | 6169.7769
TS | 0.61678 | 0.65384 | 0.80192 | 0.79689 | 0.79591 | 0.79799 | 0.79959 | 0.79698 | 0.79961 | 0.83949 | 0.84973 | 0.84321 | 0.76391 | 0.8108
Ash | 8.4183 | 8.7122 | 8.6717 | 8.9373 | 8.2532 | 8.2897 | 8.4437 | 7.9801 | 7.9679 | 8.1902 | 8.1985 | 8.1833 | 8.4296 | 8.3746
Moist | 8.6372 | 8.9799 | 8.9625 | 8.5535 | 8.6799 | 8.4687 | 8.2168 | 7.0178 | 7.1238 | 7.1299 | 7.0581 | 7.6007 | 8.2666 | 8.0403
TM | 11.4895 | 14.0596 | 13.9879 | 13.5788 | 13.7053 | 13.494 | 13.2421 | 12.0432 | 12.1492 | 12.1553 | 12.0835 | 12.6261 | 13.0059 | 13.0657
IMM-WB.HCV.HS | 57.6598 | 57 | 59.052 | 42.2763 | 55.7151 | 78.9381 | 70.7135 | 77.7154 | 69.4903 | 36.3659 | 31.0451 | 7.9879 | 643.9593 | 633.6968
CV(GAR) | 5947.3932 | 6110.136 | 6026.7428 | 5979.4143 | 5915.5718 | 5897.7507 | 5947.0367 | 5929.9035 | 6005.5198 | 5934.0912 | 5986.2386 | 5812.0059 | 5965.9033 | 5965.7827
TS | 1.9789 | 2.1891 | 2.4731 | 2.6282 | 2.6105 | 2.752 | 2.744 | 2.7008 | 2.6091 | 2.5875 | 2.4796 | 2.5485 | 2.5396 | 2.579
Ash | 12.3989 | 12.8136 | 12.8214 | 13.3602 | 14.2021 | 14.6906 | 13.819 | 14.343 | 13.3246 | 13.975 | 13.7272 | 15.5242 | 13.6567 | 13.9606
Moist | 7.8249 | 6.4358 | 6.0071 | 6.0471 | 6.0639 | 7.0695 | 6.8627 | 6.8367 | 6.831 | 7.2712 | 7.2743 | 7.8027 | 6.7833 | 6.744
TM | 10.9111 | 10.7874 | 11.0325 | 11.0725 | 11.0892 | 12.0948 | 11.8881 | 11.8621 | 11.8564 | 12.2965 | 12.2997 | 12.8281 | 11.5754 | 11.7694
IMM-EB.MCV.LS | 4.1512 | 5 | 2.4267 | 2.7672 | 1.9259 | 1.0397 | 0 | 0 | 0 | 0 | 0 | 0 | 17.3106 | 13.6399
CV(GAR) | 5768.2424 | 5887.5504 | 5837.6384 | 5826.0545 | 5825.4925 | 5826.1463 | 0 | 0 | 0 | 0 | 0 | 0 | 5831.5202 | 5822.4314
TS | 0.90471 | 0.97962 | 0.92387 | 0.90174 | 0.92197 | 0.91112 | 0 | 0 | 0 | 0 | 0 | 0 | 0.93086 | 0.90072
Ash | 8.498 | 8.3927 | 8.6472 | 8.5322 | 8.4246 | 8.467 | 0 | 0 | 0 | 0 | 0 | 0 | 8.4839 | 8.5978
Moist | 10.8615 | 12.1052 | 11.415 | 11.3496 | 11.3636 | 11.347 | 0 | 0 | 0 | 0 | 0 | 0 | 11.4614 | 11.3544
TM | 14.3085 | 16.3331 | 16.415 | 16.3496 | 16.3636 | 16.347 | 0 | 0 | 0 | 0 | 0 | 0 | 15.8659 | 16.3544
IMM-EB.MCV.MS | 16.3857 | 15 | 21.3777 | 3.4013 | 21.1906 | 4.5999 | 41.4454 | 33.3685 | 79.8482 | 87.0012 | 77.7978 | 75.5584 | 476.9747 | 422.7155
CV(GAR) | 6095.6967 | 5945.7345 | 5948.4174 | 6032.4641 | 5984.4011 | 6003.9591 | 6002.903 | 6003.8109 | 6011.5797 | 5999.8733 | 6040.1578 | 6028.9875 | 6012.4219 | 6013.6725
TS | 1.5214 | 1.5065 | 1.5317 | 1.5544 | 1.5709 | 1.5507 | 1.5529 | 1.5705 | 1.5743 | 1.5666 | 1.591 | 1.5733 | 1.5669 | 1.5595
Ash | 5.1476 | 6.9165 | 6.4867 | 5.2235 | 5.2452 | 5.2386 | 5.1535 | 5.2496 | 5.4137 | 5.4676 | 5.219 | 5.3105 | 5.417 | 5.3287
Moist | 11.5254 | 11.0445 | 10.9432 | 10.3487 | 10.6537 | 10.4716 | 10.6223 | 10.5439 | 10.3501 | 10.2451 | 10.1283 | 9.956 | 10.373 | 10.2792
TM | 13.6454 | 15.365 | 15.9432 | 15.3487 | 15.6537 | 15.4716 | 15.6223 | 15.5439 | 15.3501 | 15.2451 | 15.1283 | 14.956 | 15.2527 | 15.2792
IMM-EB.MCV.HS | 388.3038 | 370 | 361.9456 | 378.8315 | 356.8836 | 390.8604 | 421.2545 | 446.6315 | 415.1518 | 407.2488 | 421.4522 | 450.1511 | 4808.7147 | 4673.6446
CV(GAR) | 5993.4453 | 5874.5153 | 5916.1665 | 5901.7246 | 5923.1636 | 5920.6933 | 5898.7103 | 5886.3649 | 5917.7048 | 5911.2382 | 5935.692 | 5910.7659 | 5915.5755 | 5914.4155
TS | 2.2774 | 2.3259 | 2.3516 | 2.4737 | 2.3559 | 2.3487 | 2.4365 | 2.4801 | 2.4545 | 2.4643 | 2.3499 | 2.4286 | 2.3982 | 2.4107
Ash | 5.9664 | 6.1269 | 5.7582 | 5.6262 | 5.3983 | 5.7363 | 5.6945 | 5.8786 | 5.6808 | 5.7577 | 5.6903 | 5.6686 | 5.749 | 5.72
Moist | 11.4322 | 10.8986 | 11.0375 | 10.7221 | 10.778 | 10.7263 | 10.6506 | 10.5257 | 10.4549 | 10.4721 | 10.4816 | 10.5774 | 10.7179 | 10.5582
TM | 13.742 | 15.7933 | 16.0375 | 15.7221 | 15.778 | 15.7263 | 15.6506 | 15.5257 | 15.4549 | 15.4721 | 15.4816 | 15.5774 | 15.4925 | 15.5582
Fine Coal | 0 | 0 | 4.25 | 4.25 | 4.25 | 12.75 | 12.75 | 12.75 | 12.75 | 12.75 | 12.75 | 12.75 | 102 | 127.5
CV(GAR) | 0 | 0 | 3146.0674 | 3146.0674 | 3146.0674 | 3146.0674 | 3146.0674 | 3146.0674 | 3146.0674 | 3146.0674 | 3146.0674 | 3146.0674 | 3146.0674 | 3146.0674
TS | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Ash | 0 | 0 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40
Moist | 0 | 0 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11
TM | 0 | 0 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20
TCM | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Total | Budget 2025
OB Removal (KBcm) | 3736.1074 | 3800 | 4055 | 3925 | 3975 | 4210 | 4015 | 4210 | 3655 | 3080 | 3027.5713 | 3011.3213 | 44700 | 51650 | 86.54%
PAMA | 1350.2909 | 1740 | 2155 | 2075 | 2120 | 2240 | 2265 | 2360 | 2205 | 1910 | 1987.5713 | 1992.1378 | 24400 | 24400
MAP | 1111.151 | 1050 | 850 | 850 | 880 | 950 | 1000 | 1050 | 950 | 800 | 760 | 748.849 | 11000 | 11000
PJPN | 1274.6654 | 1010 | 1050 | 1000 | 975 | 1020 | 750 | 800 | 500 | 370 | 280 | 270.3346 | 9300 | 16250
ROM Production (Kton) | 197.2844 | 210 | 242 | 278 | 285 | 294 | 318 | 325 | 315 | 282 | 275 | 278.7156 | 3300 | 3300.387 | 99.99%
PAMA | 128.1928 | 140 | 170 | 178 | 175 | 180 | 198 | 205 | 202 | 180 | 185 | 188.8072 | 2130 | 2130
MAP | 31.1921 | 30 | 37 | 50 | 50 | 52 | 55 | 55 | 53 | 47 | 45 | 44.8079 | 550 | 550
PJPN | 37.8996 | 40 | 35 | 50 | 60 | 62 | 65 | 65 | 60 | 55 | 45 | 45.1004 | 620 | 620.387
Temporary ROM Stock | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SR ROM with void | 18.9377 | 18.0952 | 16.7562 | 14.1187 | 13.9474 | 14.3197 | 12.6258 | 12.9538 | 11.6032 | 10.922 | 11.0094 | 10.8043 | 13.5455 | 15.6497
FC Product CP (Kton) | 236.9432 | 200 | 283 | 255 | 289 | 310 | 265 | 349 | 280 | 273 | 242 | 267.0568 | 3250 | 3230
TCM.HCV.LS | 162.6798 | 120 | 188 | 175 | 152 | 174 | 134 | 175 | 153 | 127 | 117 | 107.3202 | 1785 | 1630
TCM.HCV.HS | 74.2634 | 80 | 95 | 80 | 137 | 136 | 131 | 174 | 127 | 146 | 125 | 159.7366 | 1465 | 1480
TCM.HCV.MS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 120
FC Product 3rd party (Kton) | 57.1257 | 53.4973 | 58.8103 | 75.2631 | 125.3982 | 94.7562 | 83.1464 | 58.1837 | 37.1395 | 68.7549 | 52.9974 | 55 | 820.0726 | 1676.5
EBH.HCV.LS | 7.1098 | 40.5275 | 51.9524 | 50.1264 | 109.9789 | 87.8438 | 83.1464 | 58.1837 | 37.1395 | 60.3145 | 52.9974 | 45 | 684.3203 | 671.5
MBL.MCV.MS | 50.0159 | 12.9697 | 6.8579 | 25.1368 | 15.4192 | 6.9123 | 0 | 0 | 0 | 8.4404 | 0 | 10 | 135.7523 | 1005
SR FC | 15.7679 | 19 | 14.3286 | 15.3922 | 13.7543 | 13.5806 | 15.1509 | 12.063 | 13.0536 | 11.2821 | 12.5106 | 11.276 | 13.7538 | 15.9907
TCM.HCV.LS | 162.6798 | 120 | 188 | 175 | 152 | 174 | 134 | 175 | 153 | 127 | 117 | 107.3202 | 1785 | 1630
CV(GAR) | 6732.4288 | 6332.0778 | 6421.9623 | 6340.6925 | 6365.6097 | 6472.734 | 6511.5528 | 6520.4866 | 6549.4995 | 6509.347 | 6415.5325 | 6471.126 | 6472.4659 | 6355.6513
Sul < 0.7 | 0.62137 | 0.75687 | 0.76622 | 0.68607 | 0.68175 | 0.73623 | 0.67492 | 0.57136 | 0.52273 | 0.50848 | 0.49866 | 0.51295 | 0.63648 | 0.60341
ASH < 5.0 | 3.4667 | 5.0761 | 5.2984 | 4.878 | 5.0063 | 5.7426 | 5.0699 | 5.1093 | 5.5227 | 5.5085 | 5.4987 | 5.513 | 5.1182 | 4.8411
IM | 6.8418 | 6.907 | 7.0159 | 7.2481 | 7.4081 | 7.4573 | 7.5515 | 7.6142 | 7.8091 | 7.5248 | 7.5663 | 7.5887 | 7.3655 | 7.3863
TM | 11.1733 | 12.5145 | 12.2671 | 13.747 | 12.615 | 11.5763 | 11.3024 | 11.3655 | 11.5398 | 12.2268 | 13.3115 | 12.4276 | 12.1435 | 13.8465
TCM.HCV.HS | 74.2634 | 80 | 95 | 80 | 137 | 136 | 131 | 174 | 127 | 146 | 125 | 159.7366 | 1465 | 1480
CV(GAR) | 6697.6812 | 6477.0152 | 6431.1937 | 6209.3024 | 6332.3965 | 6539.4916 | 6423.6841 | 6491.8862 | 6409.7944 | 6402.0292 | 6333.5109 | 6367.0709 | 6422.3513 | 6482.812
Sul < 2.0 | 1.6302 | 1.8597 | 1.8736 | 1.8545 | 1.8846 | 1.8768 | 1.95 | 1.8592 | 1.7933 | 1.8227 | 1.9 | 1.9065 | 1.8597 | 1.8762
ASH < 5.0 | 2.9843 | 5.8943 | 6.3069 | 6.8186 | 6.6718 | 5.832 | 7.4564 | 6.3987 | 5.7059 | 5.3122 | 6.4005 | 5.762 | 6.0449 | 10.2546
IM | 6.3755 | 6.5454 | 6.3104 | 6.4792 | 6.4581 | 6.4971 | 6.2776 | 6.4414 | 6.4545 | 6.3794 | 6.255 | 5.9538 | 6.3553 | 6.6258
TM | 11.045 | 11.6814 | 11.7316 | 11.8038 | 11.8431 | 10.0881 | 10.7799 | 10.251 | 11.9909 | 12.5493 | 12.1457 | 12.4817 | 11.516 | 11.2522
EBH.HCV.LS | 7.1098 | 40.5275 | 51.9524 | 50.1264 | 109.9789 | 87.8438 | 83.1464 | 58.1837 | 37.1395 | 60.3145 | 52.9974 | 45 | 684.3203 | 671.5
CV(GAR) | 6322 | 6322 | 6322 | 6322 | 6322 | 6322 | 6322 | 6322 | 6322 | 6322 | 6322 | 6322 | 6322 | 6322
Sul < 1.2 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6
ASH < 5.0 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7
IM | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12
TM | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14
MBL.MCV.MS | 50.0159 | 12.9697 | 6.8579 | 25.1368 | 15.4192 | 6.9123 | 0 | 0 | 0 | 8.4404 | 0 | 10 | 135.7523 | 1005
CV(GAR) | 5400 | 5400 | 5400 | 5400 | 5400 | 5400 | 5400 | 5400 | 5400 | 5400 | 5400 | 5400 | 5400 | 5400
Sul < 1.2 | [12 empty] | 1 | 1 | bar: Jan to Dec
ASH < 5.0 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6
IM | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15
TM | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24
BEK | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Total | Budget 2025
OB Removal (KBcm) | 7740.8131 | 7924.9731 | 8248.9731 | 7792 | 7941.9414 | 7893 | 7952 | 8175 | 7683 | 7641 | 7110 | 7397.2997 | 93500.0003 | 90950 | 102.8%
TRUST | 1657.8774 | 1806 | 1840 | 2197 | 2136.9414 | 1968 | 2132 | 2205 | 2063 | 2062 | 1955 | 1977.1813 | 24000 | 24000
PAMA | 4075.4608 | 3970 | 4235 | 4495 | 4755 | 4755 | 5020 | 5120 | 4770 | 4729 | 4450 | 4625.5392 | 55000 | 52450
SNS | 2007.4749 | 2148.9731 | 2173.9731 | 1100 | 1050 | 1170 | 800 | 850 | 850 | 850 | 705 | 794.5792 | 14500.0003 | 14500
ROM Production (Kton) | 737.0865 | 730 | 700 | 665 | 715 | 720 | 720 | 725 | 660 | 630 | 620 | 627.9135 | 8250 | 8000 | 103.1%
TRUST | 144.008 | 190 | 180 | 155 | 200 | 210 | 245 | 250 | 235 | 200 | 200 | 190.992 | 2400 | 2400
PAMA | 410.2388 | 400 | 380 | 400 | 400 | 400 | 400 | 400 | 350 | 350 | 350 | 359.7612 | 4600 | 4400
SNS | 182.8397 | 140 | 140 | 110 | 115 | 110 | 75 | 75 | 75 | 80 | 70 | 77.1603 | 1250 | 1200
SR ROM | 10.5019 | 10.8561 | 11.7842 | 11.7173 | 11.1076 | 10.9625 | 11.0444 | 11.2759 | 11.6409 | 12.1286 | 11.4677 | 11.7808 | 11.3333 | 11.3688
SR FC | 10.3695 | 11.8283 | 11.6511 | 10.8222 | 11.7658 | 10.5663 | 11.1061 | 12.1111 | 10.8211 | 10.9157 | 10.1571 | 11.5133 | 11.1177 | 11.2284
FC Product (KTons) | 746.5015 | 670 | 708 | 720 | 675 | 747 | 716 | 675 | 710 | 700 | 700 | 642.4985 | 8410 | 8100
BEK.HCV.LS | 625.8496 | 555 | 525 | 550 | 525 | 557 | 496 | 475 | 475 | 500 | 450 | 411.1504 | 6145 | 5560
CV(GAR) | 6097.4967 | 6254.096 | 6261.8957 | 6303.8809 | 6283.6427 | 6279.4564 | 6227.8086 | 6304.9145 | 6276.3057 | 6222.4967 | 6221.7549 | 6233.6933 | 6245.3108 | 5915.2264
TS | 0.54477 | 0.53855 | 0.56422 | 0.54838 | 0.52471 | 0.51912 | 0.52261 | 0.51909 | 0.60039 | 0.53026 | 0.52657 | 0.51303 | 0.53804 | 0.5772
Ash | 4.6247 | 3.9215 | 4.2513 | 4.0421 | 3.9461 | 3.9272 | 3.9014 | 3.9705 | 3.9276 | 3.8214 | 3.8338 | 3.8334 | 4.0169 | 4.8848
IM | 10.4598 | 10.6169 | 10.4589 | 10.3189 | 10.5044 | 10.544 | 10.8771 | 10.3719 | 10.5819 | 10.9817 | 10.9922 | 10.9128 | 10.6208 | 11.4694
TM | 16.139 | 14.421 | 14.2313 | 14.057 | 14.2538 | 14.2951 | 14.6805 | 14.1179 | 14.3251 | 14.791 | 14.8016 | 14.7201 | 14.5896 | 15.2419
BEK.HCV.HS | 120.6519 | 115 | 183 | 170 | 150 | 190 | 220 | 200 | 235 | 200 | 250 | 231.3481 | 2265 | 2540
CV(GAR) | 6099.469 | 6116.8969 | 6183.0028 | 6192.9933 | 6204.5332 | 6203.0262 | 6216.2935 | 6205.5017 | 6204.2217 | 6201.5682 | 6197.8462 | 6191.1531 | 6190.584 | 5792.8232
TS | 1.9961 | 1.9533 | 1.9696 | 1.8906 | 1.8529 | 1.867 | 1.7384 | 1.7756 | 1.7613 | 1.705 | 1.5097 | 1.5229 | 1.767 | 1.7606
Ash | 4.8307 | 4.8199 | 4.4116 | 4.5044 | 4.5001 | 4.5529 | 4.3866 | 4.551 | 4.517 | 4.5134 | 4.1887 | 4.1982 | 4.4627 | 5.7572
IM | 10.559 | 10.7949 | 10.6662 | 10.6196 | 10.6046 | 10.5045 | 10.582 | 10.4458 | 10.4888 | 10.6335 | 11.1808 | 11.2442 | 10.7128 | 10.7369
TM | 15.5418 | 14.6392 | 14.4306 | 14.3502 | 14.3073 | 14.2238 | 14.2465 | 14.1485 | 14.1865 | 14.2778 | 14.7037 | 14.7494 | 14.4499 | 14.5518
JBG | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Total | Budget 2025
OB Removal (KBcm) | 0 | 0 | 0 | 0 | 0 | 160 | 183 | 355 | 366 | 394 | 348 | 313 | 2119 | 5038.608 | 42.06%
Pit UCE-Extend | 0 | 0 | 0 | 0 | 0 | 160 | 183 | 355 | 366 | 394 | 348 | 313 | 2119 | 5038.608
ROM Production (Kton) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 24 | 59 | 57 | 58 | 200 | 448 | 44.64%
Pit UCE-Extend | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 24 | 59 | 57 | 58 | 200 | 448
SR ROM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 177.5 | 15.25 | 6.678 | 6.1053 | 5.3966 | 10.595 | 11.2469
SR FC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 177.5 | 16.6364 | 7.0357 | 6.3273 | 5.2167 | 10.8667 | 11.6365
JBG Coal Loading | 0 | 0 | 0 | 7.3 | 7.3 | 14.6 | 14.6 | 7.3 | 21.9 | 43.8 | 43.8 | 58.4 | 219 | 430.7
JBG FC Product (Kton) / JBG | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 22 | 56 | 55 | 60 | 195 | 433
CV(GAR) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4486.6141 | 4432.8755 | 4380.2803 | 4389.5884 | 4258.1278 | 4352.3447 | 4423.7946
TS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.39501 | 0.4259 | 0.39214 | 0.38833 | 0.32217 | 0.37337 | 0.36899
Ash | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5.0567 | 4.8165 | 5.5125 | 5.082 | 5.3704 | 5.2642 | 4.4323
IM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18.0309 | 16.9178 | 16.5652 | 16.4508 | 15.5682 | 16.281 | 16.9259
TM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29.4063 | 29.7121 | 30.3939 | 30.2747 | 29.4248 | 29.975 | 30.2366
GPK | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Total | Budget 2025
OB Removal (KBcm) | 534.7729 | 530 | 590 | 630 | 720 | 695 | 775 | 815 | 796 | 865 | 755 | 794.2271 | 8500 | 8500 | 100%
ARKA | 534.7729 | 530 | 590 | 630 | 720 | 695 | 775 | 815 | 796 | 865 | 755 | 794.2271 | 8500 | 8500
ROM Production (Kton) | 202.9475 | 185 | 218 | 200 | 190 | 175 | 140 | 147 | 145 | 150 | 170 | 177.0525 | 2100 | 2100 | 100%
ARKA | 159.0138 | 135 | 154 | 140 | 121 | 115 | 101.5625 | 105 | 114.1875 | 110 | 109 | 114.0111 | 1477.7749 | 1467
SLS | 43.9337 | 50 | 64 | 60 | 69 | 60 | 38.4375 | 42 | 30.8125 | 40 | 61 | 63.0414 | 622.2251 | 633
Other Contractor | [12 empty] | 0
SR ROM | 2.635 | 2.8649 | 2.7064 | 3.15 | 3.7895 | 3.9714 | 5.5357 | 5.5442 | 5.4897 | 5.7667 | 4.4412 | 4.4858 | 4.0476 | 4.0476
SR FC | 1.992 | 2.5238 | 2.6818 | 3.6 | 4 | 3.9714 | 11.0714 | 13.5833 | 8.8444 | 5.7083 | 3.2826 | 3.6101 | 4.1463 | 4.1463
FC Production (Ktons) | 268.4669 | 210 | 220 | 175 | 180 | 175 | 70 | 60 | 90 | 151.5331 | 230 | 220 | 2050 | 2050
CV(GAR) | 3547.1798 | 3749.4038 | 3722.2405 | 3734.463 | 3719.5866 | 3748.2895 | 3743.2418 | 3706.5355 | 3706.0256 | 3744.6717 | 3744.7068 | 3737.4498 | 3710.4878 | 3727.504
TS | 0.14 | 0.16056 | 0.13904 | 0.13563 | 0.13112 | 0.1281 | 0.1213 | 0.13043 | 0.14856 | 0.14655 | 0.16376 | 0.16475 | 0.1451 | 0.15227
Ash | 8.4611 | 7.3873 | 8.9319 | 8.2145 | 8.4126 | 7.6574 | 7.583 | 8.6141 | 8.875 | 7.5007 | 7.1654 | 7.1189 | 7.94 | 7.9761
IM | 22.4033 | 21.0091 | 22.1657 | 21.8099 | 21.7737 | 22.6508 | 23.5827 | 23.3035 | 22.5993 | 20.983 | 22.3714 | 23.0861 | 22.1901 | 27.2546
TM | 40.7078 | 38.2269 | 37.5124 | 37.9247 | 37.7888 | 38.1172 | 37.9521 | 37.5382 | 37.7401 | 37.8784 | 38.1536 | 38.2286 | 38.3168 | 38.2852
TIS | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Total | Budget 2025
OB Removal (KBcm) | 661.7443 | 734.7931 | 815.1462 | 831.0273 | 859.4709 | 916.3581 | 1058.4981 | 1055.6822 | 1025.6421 | 978.9709 | 867.198 | 903.6556 | 10708.1867 | 10708.1867 | 100%
PJPN | 661.7443 | 734.7931 | 815.1462 | 831.0273 | 859.4709 | 916.3581 | 1058.4981 | 1055.6822 | 1025.6421 | 978.9709 | 867.198 | 903.6556 | 10708.1867 | 10708.1867
ROM Production (Kton) | 36.6685 | 30 | 32 | 50 | 60 | 57 | 62 | 65 | 60 | 54 | 50 | 49.3315 | 606 | 605.9999 | 100%
PJPN | 36.6685 | 30 | 32 | 50 | 60 | 57 | 62 | 65 | 60 | 54 | 50 | 49.3315 | 606 | 605.9999
SR ROM | 18.0466 | 24.4931 | 25.4733 | 16.6205 | 14.3245 | 16.0765 | 17.0726 | 16.2413 | 17.094 | 18.1291 | 17.344 | 18.318 | 17.6703 | 17.6703
SR FC | 69.6709 | 0 | 108.3971 | 110.2158 | 114.1396 | 0 | 10.9471 | 10.918 | 10.9609 | 10.1247 | 9.2677 | 9.3457 | 17.6703 | 18.1188
FC Production (Ktons) | 9.4982 | 0 | 7.52 | 7.54 | 7.53 | 0 | 96.6917 | 96.6917 | 93.5726 | 96.6917 | 93.5726 | 96.6917 | 606 | 591
TIS.HCV.HS | 9.4982 | 0 | 7.52 | 7.54 | 7.53 | 0 | 96.6917 | 96.6917 | 93.5726 | 96.6917 | 93.5726 | 96.6917 | 606 | 591
CV(GAR) | 6571.5022 | 0 | 6968.9684 | 6964.0423 | 6975.7068 | 0 | 7171.989 | 7120.4717 | 7114.1618 | 7057.5158 | 7128.2417 | 7107.8178 | 7102.6236 | 6914.9248
TS | 1.7712 | 0 | 1.6319 | 1.5621 | 1.5602 | 0 | 1.1164 | 1.1424 | 1.0304 | 1.1182 | 1.068 | 1.131 | 1.1301 | 0.97968
Ash | 4.8216 | 0 | 3.6876 | 3.4446 | 3.4133 | 0 | 3.1617 | 3.2017 | 3.1825 | 3.2215 | 3.2524 | 3.2159 | 3.2427 | 3.7674
IM | 5.7298 | 0 | 4.6394 | 4.9404 | 4.9947 | 0 | 4.8628 | 4.7991 | 4.794 | 4.7934 | 4.7041 | 4.7619 | 4.8038 | 8.6903
TM | 10.0619 | 0 | 7.4467 | 7.815 | 7.8609 | 0 | 7.8453 | 7.7228 | 7.709 | 7.7325 | 7.7436 | 7.8519 | 7.8017 | 4.7342
NPR | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Total | Budget 2025
OB Removal (KBcm) | 0 | 0 | 0 | 110 | 354 | 565 | 722 | 847 | 823 | 782 | 709 | 771.5 | 5683.5 | 5683.5
PAMA | 0 | 0 | 0 | 110 | 354 | 565 | 722 | 847 | 823 | 782 | 709 | 771.5 | 5683.5 | 5683.5
ROM Production (Kton) | 0 | 0 | 0 | 0 | 0 | 25 | 50 | 60 | 60 | 97 | 86 | 72 | 450 | 450
PAMA | 0 | 0 | 0 | 0 | 0 | 25 | 50 | 60 | 60 | 97 | 86 | 72 | 450 | 450
SR ROM | 0 | 0 | 0 | 0 | 0 | 22.6 | 14.44 | 14.1167 | 13.7167 | 8.0619 | 8.2442 | 10.7153 | 12.63 | 12.63
SR FC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22.8919 | 11.7571 | 11.6716 | 11.8167 | 11.6894 | 18.945 | 18.945
FC Production (Ktons) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 37 | 70 | 67 | 60 | 66 | 300 | 300
CV(GAR) | 0 | 0 | 0 | 0 | 0 | 5946.1362 | 6028.6762 | 6063.9097 | 6080.6698 | 6096.0461 | 6048.2828 | 6082.9854 | 6076.0688 | 5016.4003
TS | 0 | 0 | 0 | 0 | 0 | 1.3131 | 0.923 | 1.08 | 1.076 | 1.161 | 1.162 | 1.065 | 1.1103 | 0.85231
Ash | 0 | 0 | 0 | 0 | 0 | 6.9242 | 5.169 | 5.695 | 5.548 | 5.956 | 6.401 | 6.163 | 5.9632 | 4.606
IM | 0 | 0 | 0 | 0 | 0 | 9.516 | 10.744 | 8.28 | 8.631 | 6.977 | 6.84 | 6.853 | 7.469 | 5.8143
TM | 0 | 0 | 0 | 0 | 0 | 15.3147 | 16.158 | 14.966 | 15.047 | 14.434 | 14.518 | 14.552 | 14.6854 | 11.202
Note on A8: Belfry Parulian Pandiangan: include high ash
Note on A86: Belfry Parulian Pandiangan: incoming coal volume (quality is not as actual but as range in contract)
Note on A92: Belfry Parulian Pandiangan: incoming coal volume (quality is not as actual but as range in contract)
Note on A100: Belfry Parulian Pandiangan: include Mud
Note on A125: Belfry Parulian Pandiangan: include Mud and sliding volume

## BudgVSact. June (hidden)
SITES | OB |  | ROM |  | FC |  | SR (OB/ROM) |  | Diff. (Act.%)
| Budget | Actual | Budget | Actual | Budget | Actual | Budget | Actual | OB | ROM
IMM | 45360.0431 | 44663.5794 | 3220 | 3272.0419 | 3275.5 | 3435.4329 | 14.087 | 13.6501 | 98.46% | 101.6%
TCM | 25550 | 23701.1074 | 1487 | 1506.2844 | 1562 | 1573.9432 | 17.1822 | 15.7348 | 92.76% | 101.3%
BEK | 45094 | 47541.7006 | 3966.5 | 4267.0865 | 4050 | 4266.5015 | 11.3687 | 11.1415 | 105.4% | 107.6%
JBG | 1603.028 | 160 | 57 | 0 | 53 | 0 | 28.1233 | #DIV/0! | 9.981% | 0%
GPK | 3825 | 3699.7729 | 1062 | 1170.9475 | 1100 | 1228.4669 | 3.6017 | 3.1596 | 96.73% | 110.3%
TIS | 4924.429 | 4818.5397 | 270.886 | 265.6685 | 245 | 32.0881 | 18.179 | 18.1374 | 97.85% | 98.07%
TOTAL | 126356.5002 | 124584.7001 | 10063.386 | 10482.0289 | 10285.5 | 10536.4327 | 12.5561 | 11.8856 | 98.6% | 104.2%
|  |  |  | 104.2% |  | 102.4%