## Pro Outlook 07 Nov 2025
[15 empty] | A |  | A
FINAL DRAFT OF ITM PLANBASE
ITM MINE PLAN YEAR 2025
|  |  | Act | Act | Act | Act | Act | Act | Act | Act | Act | Act | Out | Out | 2025-11-07 |  | Y2025 Bgt
ok | IMM | EO Y24 | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec |  |  | Total
| ROM Production |  | 542.8336 | 554.1195 | 482.7867 | 444.512 | 639.8002 | 581.9161 | 700.5704 | 501.6955 | 550.7224 | 650.5665 | 668.5186 | 630.0754 | 6948.1169 |  | 6950 | Done | ROM exclude fine coal
| FC Product (Kton) |  | 612.6829 | 584.9149 | 501.0107 | 479.3049 | 587.8985 | 588.8116 | 635.408 | 595.5322 | 562.7058 | 651.0839 | 665 | 670.6465 | 7135 |  | 7100
| FC Ready to Haul Product (Kton) |  | 601.1434 | 585.3366 | 497.2848 | 489.5928 | 579.758 | 570.544 | 613.682 | 645.2684 | 552.0209 | 652.9793 | 665 | 682.3898 | 7135 |  | 7100
| IMM-WB.HCV.LS |  | 146.1825 | 147.4608 | 104.9995 | 70.1282 | 84.5309 | 85.3152 | 119.5693 | 57.6065 | 44.6649 | 55.2584 | 61 | 60.75 | 1037.4662 |  | 1228.8032
| CV (GAR) |  | 6193.9879 | 6105.8162 | 6211.2744 | 6152.0829 | 6133.0399 | 6095.5899 | 6027.0339 | 6323.4648 | 6478.2496 | 6399.4105 | 6201.4116 | 6250.5272 | 6182.1892 | 6182.1892 | 6169.7769
| TS |  | 0.61678 | 0.68122 | 0.59906 | 0.64019 | 0.77254 | 0.68499 | 0.88431 | 0.87125 | 0.99071 | 0.98924 | 0.9886 | 0.85267 | 0.7606 | 0.7606 | 0.8108
| Ash |  | 8.4183 | 8.3936 | 8.4815 | 7.987 | 8.4695 | 7.7685 | 8.2569 | 6.1981 | 6.1102 | 6.7219 | 8.7931 | 8.3003 | 8.0263 | 8.0263 | 8.3746
| Moist |  | 8.6372 | 9.4242 | 8.7142 | 9.2339 | 8.7193 | 9.902 | 9.7313 | 8.8104 | 7.4341 | 7.6935 | 7.0524 | 7.206 | 8.7645 | 8.7645 | 8.0403
| TM |  | 11.4895 | 12.3252 | 11.1339 | 12.344 | 12.3701 | 12.7314 | 12.953 | 12.0547 | 10.9611 | 11.147 | 11.5355 | 12.2314 | 12.0092 | 12.0092 | 13.0657
| IMM-WB.HCV.HS |  | 57.6598 | 65.6986 | 46.0767 | 30.4062 | 42.8234 | 47.4977 | 71.1537 | 54.9754 | 53.3498 | 83.4133 | 69 | 71.9152 | 693.9698 |  | 633.6968
| CV (GAR) |  | 5947.3932 | 5939.4465 | 6026.7648 | 5928.2234 | 6043.0525 | 6015.1688 | 6025.5954 | 6219.9241 | 6110.0715 | 6170.7695 | 5850.5941 | 5828.5375 | 6008.6343 | 6008.6343 | 5965.7827
| TS |  | 1.9789 | 2.2887 | 2.171 | 1.9301 | 2.0258 | 2.5172 | 2.5175 | 2.3313 | 2.673 | 2.3581 | 2.8023 | 2.6944 | 2.3967 | 2.3967 | 2.579
| Ash |  | 12.3989 | 11.629 | 11.3803 | 12.1525 | 11.4907 | 11.721 | 11.2745 | 8.2056 | 10.6652 | 9.899 | 15.6816 | 16.3858 | 12.0035 | 12.0035 | 13.9606
| Moist |  | 7.8249 | 7.5595 | 6.9977 | 7.2613 | 7.0928 | 7.1803 | 7.4286 | 7.7994 | 6.8074 | 6.9103 | 6.8629 | 7.2635 | 7.2462 | 7.2462 | 6.744
| TM |  | 10.9111 | 11.827 | 11.262 | 11.6423 | 10.9592 | 10.8715 | 10.6652 | 11.3035 | 10.576 | 10.8847 | 10.9844 | 12.2888 | 11.1804 | 11.1804 | 11.7694
| IMM-EB.MCV.LS |  | 4.1512 | 4.8753 | 8.9721 | 7.4826 | 9.8667 | 5.2659 | 0 | 0 | 0 | 0 | 0 | 0 | 40.6138 |  | 13.6399
| CV (GAR) |  | 5768.2424 | 5970.6107 | 5842.9196 | 6060.3315 | 5981.1886 | 5851.139 | 0 | 0 | 0 | 0 | 0 | 0 | 5925.3273 | 5925.3273 | 5822.4314
| TS |  | 0.90471 | 0.97326 | 0.8997 | 0.91618 | 0.86187 | 1.0314 | 0 | 0 | 0 | 0 | 0 | 0 | 0.91996 | 0.91996 | 0.90072
| Ash |  | 8.498 | 6.4547 | 6.9734 | 5.5177 | 5.7561 | 6.6075 | 0 | 0 | 0 | 0 | 0 | 0 | 6.4556 | 6.4556 | 8.5978
| Moist |  | 10.8615 | 11.3343 | 10.9152 | 11.1195 | 11.7179 | 11.4638 | 0 | 0 | 0 | 0 | 0 | 0 | 11.2638 | 11.2638 | 11.3544
| TM |  | 14.3085 | 13.9608 | 14.8854 | 13.9345 | 14.5185 | 15.4912 | 0 | 0 | 0 | 0 | 0 | 0 | 14.5297 | 14.5297 | 16.3544
| IMM-EB.MCV.MS |  | 16.3857 | 4.2319 | 27.4815 | 41.3212 | 24.2579 | 32.4906 | 33.6604 | 63.5008 | 68.4852 | 121.3845 | 90 | 66.2397 | 589.4394 |  | 422.7155
| CV (GAR) |  | 6095.6967 | 5702.0802 | 5950.0061 | 5974.4204 | 6089.8148 | 6004.3095 | 6212.717 | 6104.6147 | 6209.1597 | 6155.1716 | 5955.9123 | 6034.9946 | 6077.2061 | 6077.2061 | 6013.6725
| TS |  | 1.5214 | 1.2568 | 1.4098 | 1.484 | 1.5036 | 1.4015 | 1.4871 | 1.5743 | 1.6603 | 1.7148 | 1.7449 | 1.5778 | 1.6045 | 1.6045 | 1.5595
| Ash |  | 5.1476 | 7.9573 | 6.2815 | 5.8971 | 5.4007 | 5.6631 | 4.2812 | 4.8911 | 4.1354 | 4.6429 | 5.6329 | 5.2446 | 5.0984 | 5.0984 | 5.3287
| Moist |  | 11.5254 | 13.0173 | 11.4442 | 12.1489 | 11.2413 | 12.0093 | 11.373 | 11.0992 | 10.8545 | 10.6793 | 10.7965 | 9.8295 | 10.9823 | 10.9823 | 10.2792
| TM |  | 13.6454 | 15.0827 | 14.2922 | 14.1446 | 13.5812 | 14.3611 | 13.137 | 13.8212 | 13.3538 | 13.4388 | 15.828 | 14.8295 | 14.1375 | 14.1375 | 15.2792
| IMM-EB.MCV.HS |  | 388.3038 | 362.6484 | 313.481 | 329.7748 | 426.41 | 418.2421 | 407.9615 | 419.315 | 396.2059 | 390.948 | 440.75 | 467.4917 | 4761.5322 |  | 4673.6446
| CV (GAR) |  | 5993.4453 | 6000.7559 | 5998.3259 | 5980.6624 | 6016.1816 | 6037.4357 | 6026.8584 | 6058.0917 | 6116.4858 | 6067.558 | 5908.1969 | 5911.5936 | 6008.2899 | 6008.2899 | 5913.433
| TS |  | 2.2774 | 2.2808 | 2.3122 | 2.3366 | 2.2917 | 2.3283 | 2.4293 | 2.3307 | 2.3996 | 2.3971 | 2.3348 | 2.411 | 2.3459 | 2.3459 | 2.4113
| Ash |  | 5.9664 | 5.886 | 6.2337 | 5.9769 | 5.734 | 5.8093 | 5.9733 | 5.2092 | 4.4746 | 5.0722 | 6.0399 | 5.684 | 5.6594 | 5.6594 | 5.7202
| Moist |  | 11.4322 | 11.4905 | 11.1144 | 11.4873 | 11.5079 | 11.274 | 10.928 | 11.1602 | 10.971 | 11.0054 | 10.7209 | 10.5871 | 11.123 | 11.123 | 10.5583
| TM |  | 13.742 | 13.586 | 13.4706 | 13.7887 | 13.7274 | 13.4627 | 13.439 | 13.806 | 13.8763 | 13.8259 | 15.7312 | 15.5871 | 14.0527 | 14.0527 | 15.5583
| Fine Coal |  | 0 | 0 | 0 | 0.19187 | 0.0095 | 0 | 3.0632 | 0.13444 | 0 | 0.079692 | 4.25 | 4.25 | 11.9787 |  | 127.5
| CV (GAR) |  | Apr: 3966.2693; May: 4270.5018; Jul: 3378.667; Aug: 3635.6911; Oct: 3838.5829; Nov: 3146.0674; Dec: 3146.0674 | 3229.6792 | 3229.6792 | 3146.0674
| TS |  | Apr: 0.95; May: 1.2; Jul: 0.80705; Aug: 0.95; Oct: 1.08; Nov: 2; Dec: 2 | 1.6596 | 1.6596 | 2
| Ash |  | Apr: 24.4; May: 21.1; Jul: 24.0365; Aug: 26.6; Oct: 25.38; Nov: 40; Dec: 40 | 35.4053 | 35.4053 | 40
| Moist |  | Apr: 12; May: 12.38; Jul: 10.8654; Aug: 11.3; Oct: 11.1; Nov: 11; Dec: 11 | 10.9867 | 10.9867 | 11
| TM |  | Apr: 22.9; May: 20.37; Jul: 21.3124; Aug: 24.6; Oct: 23.93; Nov: 20; Dec: 20 | 20.4601 | 20.4601 | 20
| ROM Stock | 151.5811 | 86.1871 | 48.4439 | 39.3229 | 22.4953 | 74.686 | 73.4504 | 131.7096 | 51.0707 | 42.7074 | 42.769 | 61.0751 | 24.754 | 24.754 |  | 227.289
| FC Stock | 69.6059 | 117.7491 | 151.43 | 327.2447 | 170.3377 | 222.2517 | 354.151 | 293.8158 | 189.0236 | 86.0521 | 284.7467 | 271.2467 | 228.8932 | 228.8932 |  | 122.6977
ok | TCM |  | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Total |  | Total
| Pama |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
| Bas |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
| Map |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
| Rml |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
| ROM Production |  | 197.2844 | 200.7536 | 248.6888 | 198.2023 | 259.7856 | 238.8222 | 189.416 | 310.5942 | 303.6293 | 309.0575 | 375.3 | 383.4661 | 3215 |  | 3300.387 | Done
| FC Production TCM (Kton) |  | 236.9432 | 220.6496 | 280.3218 | 200.3136 | 238.3063 | 285.541 | 129.7022 | 280.2099 | 217.0357 | 364.6963 | 370 | 371.2803 | 3195 |  | 3230
| TCM.HCV.LS |  | 162.6798 | 131.4776 | 143.7703 | 110.8186 | 152.7335 | 123.5704 | 108.0993 | 134.759 | 176.1082 | 193.3817 | 220 | 232.6017 | 1890 |  | 1630
| TCM.HCV.HS |  | 74.2634 | 89.172 | 136.5515 | 89.495 | 85.5729 | 161.9707 | 21.603 | 145.4509 | 40.9275 | 171.3146 | 150 | 138.6785 | 1305 |  | 1480
| TCM.LCV.MS.HA | [15 empty] | 120 | bar: Jan to Oct
| EBH.HCV.LS | [13 empty] | 0 |  | 671.5 | bar: Jan to Oct
| EBH 6000 | [13 empty] | 0 |  | 0 | bar: Jan to Oct
| MBL 5800 | [13 empty] | 0 |  | 0 | bar: Jan to Oct
| MBL.MCV.MS | [13 empty] | 0 |  | 1005 | bar: Jan to Oct
| FC Loading |  | 275.2816 | 178.8671 | 256.2678 | 175.8204 | 238.3307 | 281.8357 | 119.7376 | 337.8606 | 197.4039 | 366.8401 | 363.9193 | 363.8351 | 3156 |  | 2849.5
| FC Product CP (TCM all) |  | 236.9432 | 220.6496 | 280.3218 | 200.3136 | 238.3063 | 285.541 | 129.7022 | 280.2099 | 217.0357 | 364.6963 | 370 | 371.2803 | 3195 |  | 4626.5
| FC Product CP (TCM only) |  | 236.9432 | 220.6496 | 280.3218 | 200.3136 | 238.3063 | 285.541 | 129.7022 | 280.2099 | 217.0357 | 364.6963 | 370 | 371.2803 | 3195 | 285.4632 | 2950
| TCM.HCV.LS |  | 162.6798 | 131.4776 | 143.7703 | 110.8186 | 152.7335 | 123.5704 | 108.0993 | 134.759 | 176.1082 | 193.3817 | 220 | 232.6017 | 1890 | 165.8929 | 1630
| CV (GAR) |  | 6732.4288 | 6572.6205 | 6596.2445 | 6621.4349 | 6741.0993 | 6692.9195 | 6521.9355 | 6479.9531 | 6507 | 6584.8979 | 6588.8107 | 6554.5441 | 6597.8108 | 6599.4562 | 6355.6513
| Sul < 0.7 |  | 0.62137 | 0.63583 | 0.77706 | 0.69371 | 0.7093 | 0.60986 | 0.77535 | 0.58304 | 0.69 | 0.65662 | 0.64 | 0.63 | 0.66412 | 0.66083 | 0.60341
| ASH < 5.0 |  | 3.4667 | 4.5743 | 4.3675 | 4.7704 | 3.7542 | 3.8464 | 4.6288 | 5.2588 | 5.68 | 4.47 | 4.67 | 4.06 | 4.453 | 4.4369 | 4.8411
| IM |  | 6.8418 | 7.5669 | 6.8218 | 6.8812 | 6.8542 | 6.8497 | 6.8642 | 7.4687 | 6.87 | 6.8371 | 6.24 | 6.59 | 6.8416 |  | 7.3863
| TM |  | 11.1733 | 12.0917 | 12.4658 | 11.343 | 11.0393 | 11.0674 | 12.118 | 11.4246 | 11.3 | 11.3393 | 12.51 | 12.12 | 11.7005 | 140.9177 | 13.8465
| TCM.HCV.HS |  | 74.2634 | 89.172 | 136.5515 | 89.495 | 85.5729 | 161.9707 | 21.603 | 145.4509 | 40.9275 | 171.3146 | 150 | 138.6785 | 1305 | 1310.0912 | 1480
| CV (GAR) |  | 6697.6812 | 6682.5379 | 6375.2052 | 6514.9911 | 6575.1364 | 6545.7939 | 6373.7282 | 6538.1038 | 6606 | 6571.5856 | 6528.2238 | 6351.2055 | 6524.6135 | 78943.3552 | 6482.812
| Sul < 2.0 |  | 1.6302 | 1.4797 | 1.6016 | 1.6141 | 1.5958 | 1.6294 | 1.3355 | 1.5875 | 1.45 | 1.4021 | 1.73 | 1.72 | 1.5893 | 18.882 | 1.8762
| ASH < 5.0 |  | 2.9843 | 3.6683 | 5.3381 | 5.334 | 5.1498 | 6.3739 | 5.0945 | 5.004 | 5.56 | 7.96 | 4.33 | 7.45 | 5.6244 | 64.5067 | 10.2546
| IM |  | 6.3755 | 6.3149 | 6.5134 | 6.5208 | 6.2533 | 6.2533 | 6.524 | 6.6362 | 6.29 | 6.4427 | 5.81 | 6.26 | 6.333 |  | 6.6258
| TM |  | 11.045 | 10.871 | 11.7658 | 12.1103 | 11.2862 | 10.0871 | 11.8564 | 10.7679 | 10.29 | 10.833 | 11.78 | 11.14 | 11.1041 | 134.1918 | 11.2522
| TCM.LCV.MS.HA | [15 empty] | 120
| CV (GAR) | [15 empty] | 4963.5346 | bar: Jan to Oct
| Sul | [15 empty] | 1.3582 | bar: Jan to Oct
| Ash | [15 empty] | 11.1647 | bar: Jan to Oct
| IM | [15 empty] | 6.3891 | bar: Jan to Oct
| TM | [15 empty] | 13.8507 | bar: Jan to Oct
| EBH.HCV.LS |  | 56.6 | 56.9 | 56.1 | 55.6 | 56.5 | 55.8 | 56 | 55.2 | 55.6 | 56.2 | 55.8 | 55.2 | 671.5 | #REF! | 630
| CV (GAR) |  | 6322 | 6322 | 6322 | 6322 | 6322 | 6322 | 6322 | 6322 | 6322 | 6322 | 6322 | 6322 | 6322 | #REF! | 6322
| Sul 0.6 |  | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | #REF! | 0.6
| ASH |  | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | #REF! | 7
| IM |  | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 |  | 12
| TM |  | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 168 | 14
| EBH 6000 | [13 empty] | 0 | 0 | 172.5
| CV (GAR) |  | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 72000 | 6000
| Sul 0.6 |  | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 7.2 | 0.6
| ASH 9.0 |  | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 108 | 9
| IM |  | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 |  | 12
| TM |  | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 168 | 14
| MBL 5800 | [13 empty] | 0 | #REF! | 172.5
| CV (GAR) |  | 5800 | 5800 | 5800 | 5800 | 5800 | 5800 | 5800 | 5800 | 5800 | 5800 | 5800 | 5800 | 5800 | #REF! | 5800
| Sul 1.0 | [13 empty] | 1 | #REF! | 1 | bar: Jan to Dec
| ASH 6.0 |  | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | #REF! | 6
| IM |  | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 |  | 13
| TM |  | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 |  | 19
| MBL.MCV.MS |  | 82.5 | 82.5 | 82.5 | 82.5 | 82.5 | 82.5 | 82.5 | 82.5 | 90 | 90 | 82.5 | 82.5 | 1005 | 1005 | 540
| CV (GAR) |  | 5400 | 5400 | 5400 | 5400 | 5400 | 5400 | 5400 | 5400 | 5400 | 5400 | 5400 | 5400 | 5400 | 64800 | 5400
| Sul 1.2 | [13 empty] | 1 | 12 | 1 | bar: Jan to Dec
| ASH |  | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 72 | 6
| IM 14.00-15.00 |  | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 |  | 15
| TM 22.00-24.00 |  | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 |  | 24
| ROM Stock | 269.2473 | 249.8006 | 241.1899 | 323.2816 | 239.9324 | 279.4862 | 249.5403 | 312.0912 | 354.0109 | 447.3904 | 411.1464 | 405.2801 | 417.466 | 417.466 |  | 352.6185
| FC Stock | 64.3059 | 20.3816 | 55.7136 | 81.2937 | 94.7508 | 83.7812 | 70.0021 | 82.8688 | 23.687 | 44.6412 | 39.6777 | 45.7584 | 53.2035 | 53.2035 |  | 230.5978
ok | JBG |  | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Total |  | Total | Done
| ROM Production |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 448
| JBG FC Product (Kton) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 433
| Cv (GAR) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 4423.7946
| TS |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0.36899
| Ash |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 4.4323
| IM |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 16.9259
| TM |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 30.2366
| Loading Barge | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 52.5 | 0 | 52.5 |  | 430.7
| ROM Stock | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 14.4802
| FC Stock | 54.8398 | 54.8105 | 54.8014 | 54.8014 | 54.8014 | 54.8014 | 54.8014 | 54.8014 | 54.8014 | 54.8014 | 54.8014 | 2.3014 | 2.2784 | 2.2784 |  | 52.7432
ok | BEK |  | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Total |  | Total | Done
| ROM Production |  | 737.0865 | 743.2998 | 904.2769 | 705.0239 | 817.6832 | 480.0651 | 330.8926 | 581.1533 | 846.0155 | 1032.1493 | 835 | 737.3541 | 8750.0003 |  | 8000
| FC Product (KTons) |  | 746.5015 | 686.976 | 708.8848 | 675.859 | 810.3971 | 601.4072 | 291.2126 | 711.8981 | 702.719 | 769.2163 | 790 | 809.9283 | 8305 |  | 8100
| BEK.HCV.LS |  | 625.8496 | 567.9555 | 547.067 | 503.7176 | 489.6375 | 461.795 | 225.7667 | 453.7957 | 556.3072 | 563.008 | 580 | 580.1 | 6155 |  | 5560
| Cv (GAR) |  | 6097.4967 | 6119.1856 | 6220.8649 | 6062.7439 | 6140.1294 | 6191.6877 | 6195.1282 | 6159.7149 | 6206.2441 | 6254.5596 | 6262.2752 | 6222.1146 | 6177.7141 | 6177.7141 | 5915.2264
| TS |  | 0.54477 | 0.56824 | 0.47738 | 0.62875 | 0.59201 | 0.56239 | 0.6128 | 0.63108 | 0.62077 | 0.5461 | 0.54608 | 0.57036 | 0.57128 | 0.57128 | 0.5772
| Ash |  | 4.6247 | 4.6318 | 3.9165 | 4.3087 | 4.0161 | 3.8465 | 4.0756 | 4.305 | 4.4117 | 3.6582 | 3.6809 | 3.9957 | 4.1301 | 4.1301 | 4.8848
| IM |  | 10.4598 | 10.574 | 10.5752 | 11.1112 | 11.0859 | 10.9708 | 10.3728 | 10.2014 | 10.114 | 9.9435 | 10.6167 | 10.9355 | 10.5809 | 10.5809 | 11.4694
| TM |  | 16.139 | 16.0366 | 15.5041 | 16.8779 | 16.1084 | 15.2831 | 14.9014 | 15.5389 | 15.2528 | 15.1047 | 14.6874 | 15.2573 | 15.5827 | 15.5827 | 15.2419
| BEK.HCV.HS |  | 120.6519 | 119.0205 | 161.8178 | 172.1413 | 320.7595 | 139.6122 | 65.446 | 258.1024 | 146.4118 | 206.2083 | 210 | 229.8284 | 2150 |  | 2540
| Cv (GAR) |  | 6099.469 | 6066.5599 | 6046.9118 | 6012.6397 | 6083.696 | 6162.7207 | 6086.3943 | 6043.6024 | 6006.1758 | 6205.0535 | 6161.7701 | 6147.4385 | 6096.3756 | 6096.3756 | 5792.8232
| TS |  | 1.9961 | 1.995 | 1.9374 | 1.9318 | 1.8618 | 1.9218 | 1.8723 | 1.9325 | 1.9491 | 1.8117 | 1.8426 | 1.8537 | 1.8991 | 1.8991 | 1.7606
| Ash |  | 4.8307 | 4.7802 | 6.309 | 6.1221 | 6.1221 | 5.6906 | 6.1909 | 6.3841 | 6.2868 | 4.9451 | 5.2185 | 5.5778 | 5.7468 | 5.7468 | 5.7572
| IM |  | 10.559 | 11.003 | 10.0774 | 10.2964 | 10.2377 | 9.8856 | 9.0084 | 9.7062 | 10.3072 | 9.1836 | 10.231 | 10.9878 | 10.1498 | 10.1498 | 10.7369
| TM |  | 15.5418 | 16.161 | 15.2644 | 15.4267 | 15.2786 | 14.3926 | 14.5459 | 14.5497 | 15.21 | 14.6851 | 14.0276 | 14.347 | 14.9023 | 14.9023 | 14.5518
| ROM Stock | 429.4579 | 447.1646 | 498.4481 | 703.1846 | 738.3579 | 763.5538 | 677.0446 | 699.7859 | 593.7834 | 704.1542 | 911.3427 | 952.1677 | 875.9068 | 875.9068 |  | 184.0681
| FC Stock | 39.3768 | 28.6538 | 7.6678 | 9.2986 | 134.3833 | 110.5524 | 40.6607 | 50.4792 | 7.7845 | 26.7671 | 162.7239 | 148.7739 | 162.3707 | 162.3707 |  | 50.741
ok | GPK |  | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Total |  | Total
| ROM Production |  | 202.9475 | 206.0717 | 193.2873 | 202.809 | 197.4591 | 174.3256 | 189.8315 | 125.8537 | 186.4315 | 143.3794 | 220 | 227.6039 | 2270 |  | 2100 | Done
| FC Product (Kton) |  | 268.4669 | 173.22 | 180.692 | 210.9939 | 174.0629 | 168.0224 | 132.2818 | 135.1953 | 127.9932 | 178.0774 | 240 | 240.9941 | 2230 |  | 2050
| Cv (GAR) |  | 3724.8809 | 3770.9785 | 3744.4236 | 3734.7558 | 3761.5128 | 3721.5417 | 3690.9129 | 3692.9814 | 3728.2209 | 3710.7819 | 3668.7469 | 3708.6622 | 3720.91 | 3720.91 | 3727.504
| TS |  | 0.18179 | 0.1619 | 0.15271 | 0.18618 | 0.1849 | 0.20676 | 0.1737 | 0.17634 | 0.17509 | 0.16483 | 0.17591 | 0.16951 | 0.17592 | 0.17592 | 0.15227
| Ash |  | 9.388 | 9.0395 | 7.3286 | 7.4295 | 6.5335 | 7.3269 | 7.7195 | 8.0676 | 7.8672 | 9.5092 | 9.2254 | 8.3431 | 8.2436 | 8.2436 | 7.9761
| IM |  | 21.0636 | 19.2873 | 18.6168 | 20.3173 | 19.9803 | 28.5884 | 20.4597 | 18.7138 | 17.1728 | 16.7946 | 21.2537 | 21.7694 | 20.4934 | 20.4934 | 27.2546
| TM |  | 38.3472 | 38.2059 | 39.1151 | 39.3409 | 39.2721 | 38.778 | 39.7708 | 39.2567 | 39.6956 | 38.2023 | 38.0909 | 37.8458 | 38.7208 | 38.7208 | 38.2852
| FC Load/Ready Sale (Kton) |  | 263.7363 | 173.7399 | 195.5285 | 187.631 | 135.0487 | 177.7801 | 117.7529 | 150.4788 | 120.061 | 174.2495 | 240 | 240 | 2176.0069 |  | 2037
| ROM Stock | 98.2116 | 27.8175 | 52.0458 | 69.1389 | 78.6512 | 106.0549 | 109.2652 | 167.3919 | 163.7823 | 217.9929 | 183.1556 | 163.1556 | 149.7655 | 149.7655 |  | 88
| FC Stock | 7.1453 | 14.5338 | 22.0184 | 2.4608 | 8.0072 | 43.9221 | 37.1 | 52.0072 | 28.8118 | 38.2873 | 42.2926 | 42.2926 | 43.2867 | 43.2867 |  | 63
ok | TIS |  | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Total |  | Total
| ROM Production |  | 36.6685 | 40.4296 | 41.2222 | 46.5491 | 48.0715 | 50.9448 | 51.1317 | 49.6962 | 48.9121 | 32.9306 | 21 | 27.2017 | 494.7581 |  | 606 | Done
| FC Product (Kton) |  | 9.4982 | 5.9345 | 23.6335 | 25.6495 | 42.9772 | 46.1752 | 72.1767 | 13.8445 | 0 | 47.1958 | 0 | 0 | 287.0849 |  | 591
| Cv (GAR) |  | 6571.5022 | 6870.6132 | 6804.7599 | 6863.1036 | 6917.9129 | 6963.7003 | 6950.4047 | 6984 |  | 7009.4203 |  |  | 6925.0262 | 6925.0262 | 6914.9248
| TS |  | 1.7712 | 0.82 | 1.1687 | 1.2244 | 1.1903 | 1.2474 | 1.2028 | 1.356 |  | 1.1337 |  |  | 1.2141 | 1.2141 | 0.97968
| Ash |  | 4.8216 | 2.98 | 3.3931 | 3.002 | 2.8749 | 2.7396 | 2.5228 | 2.6026 |  | 1.9932 |  |  | 2.7271 | 2.7271 | 3.7674
| IM |  | 5.7298 | 6.25 | 6.5933 | 5.0621 | 5.506 | 5.0076 | 5.1434 | 4.9609 |  | 4.8733 |  |  | 5.277 | 5.277 | 8.6903
| TM |  | 10.0619 | 11.07 | 11.3529 | 10.8902 | 10.731 | 10.3596 | 9.3476 | 9.6325 |  | 10.1689 |  |  | 10.2283 | 10.2283 | 4.7342
| FC Load/Ready Sale (Kton) |  | 7.6255 | 8.4607 | 7.5842 | 14.9085 | 60.0365 | 30.3666 | 45.3397 | 49.8839 | 7.5401 | 7.5029 | 37.5 | 0 | 276.7486 |  | 560
| ROM Stock | 31.6102 | 56.7406 | 88.9214 | 108.6258 | 129.4267 | 130.3049 | 138.6125 | 118.9005 | 150.7716 | 197.1148 | 186.3655 | 207.3655 | 234.5672 | 234.5672 |  | 14.9999
| FC Stock | 1.4476 | 3.2149 | 0.71205 | 16.5674 | 25.389 | 6.5416 | 21.596 | 49.4866 | 10.5976 | 3.0886 | 38.2993 | 0.79927 | 0.79927 | 0.79927 |  | 31
ok | NPR |  | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Total |  | Total
| ROM Production |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 450
| FC Product (Kton) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 300
| NPR.MCV.MS |  | Oct: 0; Nov: 0; Dec: 0 | 0 |  | 300
| Cv (GAR) |  | Jun: 0; Jul: 0; Aug: 0; Sep: 0; Oct: 0; Nov: 0; Dec: 0 | 0 | #DIV/0! | 6578.0649
| TS |  | Jun: 0; Jul: 0; Aug: 0; Sep: 0; Oct: 0; Nov: 0; Dec: 0 | 0 | #DIV/0! | 1.108
| Ash |  | Jun: 0; Jul: 0; Aug: 0; Sep: 0; Oct: 0; Nov: 0; Dec: 0 | 0 | #DIV/0! | 6.0164
| IM |  | Jun: 0; Jul: 0; Aug: 0; Sep: 0; Oct: 0; Nov: 0; Dec: 0 | 0 | #DIV/0! | 7.5822
| TM |  | Jun: 0; Jul: 0; Aug: 0; Sep: 0; Oct: 0; Nov: 0; Dec: 0 | 0 | #DIV/0! | 14.6874
| FC Load/barges (Kton) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
| ROM Stock | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 150
| FC Stock | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 300
| ITM GRAND TOTAL | EO Y24 | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | TOTAL |  | TOTAL
| ROM Production |  | 1716.8206 | 1744.6741 | 1870.2619 | 1597.0963 | 1962.7996 | 1526.0738 | 1461.8422 | 1568.9929 | 1935.7108 | 2168.0833 | 2119.8186 | 2005.7013 | 21677.8754 |  | 21854.387
| FC Production |  | 1874.0927 | 1671.6951 | 1694.5429 | 1592.1209 | 1853.642 | 1689.9575 | 1260.7813 | 1736.6799 | 1610.4538 | 2010.2697 | 2065 | 2092.8492 | 21152.0849 |  | 21524
| FC + EBH + MBL |  | 1874.0927 | 1671.6951 | 1694.5429 | 1592.1209 | 1853.642 | 1689.9575 | 1260.7813 | 1736.6799 | 1610.4538 | 2010.2697 | 2065 | 2092.8492 | 21152.0849 |  | 22609.5
| ROM Stock | 980.1081 | 867.7104 | 929.0492 | 1243.5538 | 1208.8635 | 1354.0859 | 1247.913 | 1429.8791 | 1313.4188 | 1609.3597 | 1734.7793 | 1789.0441 | 1702.4594 | 1702.4594 |  | 1031.4556
| FC Stock | 236.7214 | 239.3437 | 292.3432 | 491.6666 | 487.6695 | 521.8505 | 578.3111 | 583.459 | 314.7059 | 253.6377 | 622.5416 | 511.1723 | 490.8318 | 490.8318 |  | 850.7797
Notes :
Note on B45: Belfry Parulian Pandiangan: Exclude High ash stock and exclude fine coal stock
Note on B46: Belfry Parulian Pandiangan: MSY + PSY
Note on A145: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Still using budget for outlook 2024

## Pro Outlook (Quarterly)
[7 empty] | A |  | A
FINAL DRAFT OF ITM PLANBASE
ITM MINE PLAN YEAR 2025
|  |  | Act | Out | Out | Out | 2025-11-07 |  | Y2025 Bgt
ok | IMM | EO Y24 | Q1 | Q2 | Q3 | Q4 |  |  | Total
| ROM Production |  | 1579.7398 | 1666.2283 | 1752.9883 | 1949.1605 | 6948.1169 |  | 6950 | Done | ROM exclude fine coal
| FC Product (Kton) |  | 1698.6086 | 1656.015 | 1793.646 | 1986.7304 | 6957.9916 |  | 7100
| FC Ready to Haul Product (Kton) |  | 1683.7648 | 1639.8948 | 1810.9713 | 2000.3691 | 7135 |  | 7100
| IMM-WB.HCV.LS |  | 398.6428 | 239.9743 | 221.8407 | 177.0084 | 860.4578 |  | 1228.8032
| CV (GAR) |  | 6165.9257 | 6125.2907 | 6194.8564 | 6280.0794 | 6182.1892 | 6162.0518 | 6169.7769
| TS |  | 0.63595 | 0.70274 | 0.90234 | 0.94215 | 0.7606 | 0.72326 | 0.8108
| Ash |  | 8.4258 | 8.0793 | 7.29 | 7.9774 | 8.0263 | 8.0364 | 8.3746
| Moist |  | 8.9486 | 9.2901 | 9.0296 | 7.3053 | 8.7645 | 9.0647 | 8.0403
| TM |  | 11.705 | 12.4909 | 12.3187 | 11.6531 | 12.0092 | 12.0824 | 13.0657
| IMM-WB.HCV.HS |  | 169.4351 | 120.7274 | 179.479 | 224.3284 | 693.9698 |  | 633.6968
| CV (GAR) |  | 5965.8964 | 6003.1615 | 6110.2298 | 5962.5758 | 6008.6343 | 4081.2085 | 5965.7827
| TS |  | 2.1513 | 2.195 | 2.5067 | 2.6026 | 2.3967 | 1.5554 | 2.579
| Ash |  | 11.8233 | 11.748 | 10.1534 | 13.7572 | 12.0035 | 7.5564 | 13.9606
| Moist |  | 7.4971 | 7.1697 | 7.3575 | 7.0089 | 7.2462 | 4.9806 | 6.744
| TM |  | 11.3616 | 11.0967 | 10.8342 | 11.3655 | 11.1804 | 7.5065 | 11.7694
| IMM-EB.MCV.LS |  | 17.9985 | 22.6152 | 0 | 0 | 40.6138 |  | 13.6399
| CV (GAR) |  | 5860.2842 | 5977.0925 | 0 | 0 | 5925.3273 | 5925.3273 | 5822.4314
| TS |  | 0.92078 | 0.91931 | 0 | 0 | 0.91996 | 0.91996 | 0.90072
| Ash |  | 7.1846 | 5.8755 | 0 | 0 | 6.4556 | 6.4556 | 8.5978
| Moist |  | 11.0164 | 11.4607 | 0 | 0 | 11.2638 | 11.2638 | 11.3544
| TM |  | 14.5019 | 14.5518 | 0 | 0 | 14.5297 | 14.5297 | 16.3544
| IMM-EB.MCV.MS |  | 48.099 | 98.0697 | 165.6464 | 277.6242 | 589.4394 |  | 422.7155
| CV (GAR) |  | 5977.8247 | 6012.8659 | 6169.8051 | 6061.9023 | 6077.2061 | 3222.0679 | 6013.6725
| TS |  | 1.4343 | 1.4615 | 1.5921 | 1.6919 | 1.6045 | 0.80763 | 1.5595
| Ash |  | 6.0427 | 5.6968 | 4.4548 | 5.1074 | 5.0984 | 2.6928 | 5.3287
| Moist |  | 11.6102 | 11.8781 | 11.0537 | 10.5145 | 10.9823 | 6.03 | 10.2792
| TM |  | 14.1414 | 14.077 | 13.4889 | 14.5452 | 14.1375 | 7.2868 | 15.2792
| IMM-EB.MCV.HS |  | 1064.4332 | 1174.427 | 1223.4824 | 1299.1897 | 4761.5322 |  | 4673.6446
| CV (GAR) |  | 5997.3733 | 6013.777 | 6066.5872 | 5957.3736 | 6008.2899 | 4382.8135 | 5913.433
| TS |  | 2.2888 | 2.3173 | 2.3859 | 2.381 | 2.3459 | 1.6963 | 2.4113
| Ash |  | 6.0178 | 5.829 | 5.2261 | 5.6206 | 5.6594 | 4.1258 | 5.7202
| Moist |  | 11.3584 | 11.4189 | 11.0215 | 10.7583 | 11.123 | 8.1876 | 10.5583
| TM |  | 13.6089 | 13.6503 | 13.7064 | 15.106 | 14.0527 | 9.931 | 15.5583
| Fine Coal |  | 0 | 0.20137 | 3.1976 | 8.5797 | 11.9787 |  | 127.5
| CV (GAR) |  | 3146.0674 | 3980.6221 | 3389.4737 | 3152.4998 | 3229.6792 | 971.7068 | 3146.0674
| TS |  | 2 | 0.96179 | 0.81306 | 1.9915 | 1.6596 | 0.23321 | 2
| Ash |  | 40 | 24.2443 | 24.1443 | 39.8642 | 35.4053 | 6.8527 | 40
| Moist |  | 11 | 12.0179 | 10.8837 | 11.0009 | 10.9867 | 3.1073 | 11
| TM |  | 20 | 22.7806 | 21.4507 | 20.0365 | 20.4601 | 6.109 | 20
| ROM Stock | 151.5811 | 39.3229 | 73.4504 | 42.7074 | 24.754 | 24.754 |  | 227.289
| FC Stock | 69.6059 | 327.2447 | 354.151 | 86.0521 | 228.8932 | 228.8932 |  | 122.6977
ok | TCM |  | Q1 | Q2 | Q3 | Q4 | Total |  | Total
| Pama | [5 empty] | #REF! |  | #REF!
| Bas | [5 empty] | #REF! |  | #REF!
| Map | [5 empty] | #REF! |  | #REF!
| Rml | [5 empty] | #REF! |  | #REF!
| ROM Production |  | 646.7268 | 696.8101 | 803.6395 | 1067.8236 | 3215 |  | 3300.387 | Done
| FC Production TCM (Kton) |  | 737.9146 | 724.161 | 626.9479 | 1105.9765 | 3195 |  | 3230
| TCM.HCV.LS |  | 437.9277 | 387.1224 | 418.9665 | 645.9834 | 1890 |  | 1630
| TCM.HCV.HS |  | 299.9869 | 337.0386 | 207.9814 | 459.9931 | 1305 |  | 1480
| TCM.LCV.MS.HA |  | 0 | 0 | 0 | 0 | 0 |  | 120
| EBH.HCV.LS |  | 0 | 0 | 0 | 0 | 0 |  | 671.5
| EBH 6000 |  | 0 | 0 | 0 | 0 | 0 |  | 0
| MBL 5800 |  | 0 | 0 | 0 | 0 | 0 |  | 0
| MBL.MCV.MS |  | 0 | 0 | 0 | 0 | 0 |  | 1005
| FC Loading |  | 710.4165 | 695.9868 | 655.0021 | 1094.5946 | 3156 |  | 2849.5
| FC Product CP (TCM all) | [5 empty] | 0 |  | 4626.5
| FC Product CP (TCM only) |  | 737.9146 | 724.161 | 626.9479 | 1105.9765 | 3195 | #DIV/0! | 2950
| TCM.HCV.LS |  | 437.9277 | 387.1224 | 418.9665 | 645.9834 | 1890 | #DIV/0! | 1630
| CV (GAR) |  | 6639.7412 | 6691.4648 | 6502.154 | 6575.3008 | 6597.8108 | #DIV/0! | 6355.6513
| Sul < 0.7 |  | 0.67682 | 0.67309 | 0.67762 | 0.64137 | 0.66412 | #DIV/0! | 0.60341
| ASH < 5.0 |  | 4.095 | 4.0745 | 5.2733 | 4.3905 | 4.453 | #DIV/0! | 4.8411
| IM |  | 7.0529 | 6.8605 | 7.0611 | 6.5448 | 6.8416 |  | 7.3863
| TM |  | 11.8734 | 11.1352 | 11.5511 | 12.0191 | 11.7005 | 35.3276 | 13.8465
| TCM.HCV.HS |  | 299.9869 | 337.0386 | 207.9814 | 459.9931 | 1305 | 861.8716 | 1480
| CV (GAR) |  | 6546.3914 | 6545.0647 | 6534.391 | 6491.0056 | 6524.6135 | 20055.6504 | 6482.812
| Sul < 2.0 |  | 1.5725 | 1.6168 | 1.5342 | 1.6049 | 1.5893 | 4.8258 | 1.8762
| ASH < 5.0 |  | 4.2591 | 5.787 | 5.1228 | 6.6225 | 5.6244 | 15.4807 | 10.2546
| IM |  | 6.4203 | 6.3243 | 6.5564 | 6.1813 | 6.333 |  | 6.6258
| TM |  | 11.3214 | 10.9288 | 10.7869 | 11.2344 | 11.1041 | 33.5589 | 11.2522
| TCM.LCV.MS.HA |  | 0 | 0 | 0 | 0 |  |  | 120
| CV (GAR) | [7 empty] | 4963.5346
| Sul | [7 empty] | 1.3582
| Ash | [7 empty] | 11.1647
| IM | [7 empty] | 6.3891
| TM | [7 empty] | 13.8507
| EBH.HCV.LS | [5 empty] | 0 | #REF! | 630
| CV (GAR) | [5 empty] | 6322 | #REF! | 6322
| Sul 0.6 | [5 empty] | 0.6 | #REF! | 0.6
| ASH | [5 empty] | 7 | #REF! | 7
| IM | [5 empty] | 12 |  | 12
| TM | [5 empty] | 14 | 0 | 14
| EBH 6000 | [5 empty] | 0 | 0 | 172.5
| CV (GAR) | [5 empty] | 6000 | 0 | 6000
| Sul 0.6 | [5 empty] | 0.6 | 0 | 0.6
| ASH 9.0 | [5 empty] | 9 | 0 | 9
| IM | [5 empty] | 12 |  | 12
| TM | [5 empty] | 14 | 0 | 14
| MBL 5800 | [5 empty] | 0 | #REF! | 172.5
| CV (GAR) | [5 empty] | 5800 | #REF! | 5800
| Sul 1.0 | [5 empty] | 1 | #REF! | 1
| ASH 6.0 | [5 empty] | 6 | #REF! | 6
| IM | [5 empty] | 13 |  | 13
| TM | [5 empty] | 19 |  | 19
| MBL.MCV.MS | [5 empty] | 0 | 0 | 540
| CV (GAR) | [5 empty] | 5400 | 0 | 5400
| Sul 1.2 | [5 empty] | 1 | 0 | 1
| ASH | [5 empty] | 6 | 0 | 6
| IM 14.00-15.00 | [5 empty] | 15 |  | 15
| TM 22.00-24.00 | [5 empty] | 24 |  | 24
| ROM Stock | 269.2473 | 323.2816 | 249.5403 | 447.3904 | 417.466 | 417.466 |  | 352.6185
| FC Stock | 64.3059 | 81.2937 | 70.0021 | 44.6412 | 53.2035 | 53.2035 |  | 230.5978
ok | JBG |  | Q1 | Q2 | Q3 | Q4 | Total |  | Total | Done
| ROM Production |  | 0 | 0 | 0 | 0 | 0 | 0 | 448
| JBG FC Product (Kton) |  | 0 | 0 | 0 | 0 | 0 | 0 | 433
| Cv (GAR) |  | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 4423.7946
| TS |  | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0.36899
| Ash |  | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 4.4323
| IM |  | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 16.9259
| TM |  | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 30.2366
| Loading Barge | 0 | 0 | 0 | 0 | 52.5 | 52.5 |  | 430.7
| ROM Stock | 0 | 0 | 0 | 0 | 0 | 0 |  | 14.4802
| FC Stock | 54.8398 | 54.8014 | 54.8014 | 54.8014 | 2.2784 | 2.2784 |  | 52.7432
ok | BEK |  | Q1 | Q2 | Q3 | Q4 | Total |  | Total | Done
| ROM Production |  | 2384.6632 | 2002.7722 | 1758.0615 | 2604.5034 | 8750.0003 |  | 8000
| FC Product (KTons) |  | 2142.3624 | 2087.6633 | 1705.8297 | 2369.1446 | 8305 |  | 8100
| BEK.HCV.LS |  | 1740.8722 | 1455.1502 | 1235.8697 | 1723.108 | 6155 |  | 5560
| Cv (GAR) |  | 6143.341 | 6129.7036 | 6187.1285 | 6246.2338 | 6177.7141 | 4429.065 | 5915.2264
| TS |  | 0.53125 | 0.59533 | 0.6231 | 0.55426 | 0.57128 | 0.41612 | 0.5772
| Ash |  | 4.4045 | 4.0636 | 4.3111 | 3.7794 | 4.1301 | 3.0721 | 4.8848
| IM |  | 10.5333 | 11.0581 | 10.1934 | 10.5041 | 10.5809 | 7.6403 | 11.4694
| TM |  | 15.9061 | 16.1129 | 15.2937 | 15.0156 | 15.5827 | 11.3791 | 15.2419
| BEK.HCV.HS |  | 401.4902 | 632.5131 | 469.9601 | 646.0367 | 2150 |  | 2540
| Cv (GAR) |  | 6068.5304 | 6081.8005 | 6037.9016 | 6170.4873 | 6096.3756 | 4242.2542 | 5792.8232
| TS |  | 1.9721 | 1.8941 | 1.9293 | 1.8367 | 1.8991 | 1.3472 | 1.7606
| Ash |  | 5.4116 | 6.0269 | 6.3269 | 5.2591 | 5.7468 | 4.1666 | 5.7572
| IM |  | 10.4965 | 10.1759 | 9.7963 | 10.1659 | 10.1498 | 7.0951 | 10.7369
| TM |  | 15.6136 | 15.1234 | 14.7549 | 14.3511 | 14.9023 | 10.5901 | 14.5518
| ROM Stock | 429.4579 | 703.1846 | 677.0446 | 704.1542 | 875.9068 | 875.9068 |  | 184.0681
| FC Stock | 39.3768 | 9.2986 | 40.6607 | 26.7671 | 162.3707 | 162.3707 |  | 50.741
ok | GPK |  | Q1 | Q2 | Q3 | Q4 | Total |  | Total
| ROM Production |  | 602.3065 | 574.5936 | 502.1166 | 590.9833 | 2270 |  | 2100 | Done
| FC Product (Kton) |  | 622.379 | 553.0792 | 395.4703 | 659.0715 | 2230 |  | 2050
| Cv (GAR) |  | 3743.3845 | 3739.1623 | 3703.6947 | 3694.6998 | 3720.91 | 2628.9498 | 3727.504
| TS |  | 0.16781 | 0.19203 | 0.17505 | 0.17058 | 0.17592 | 0.12551 | 0.15227
| Ash |  | 8.6931 | 7.1164 | 7.8863 | 8.9795 | 8.2436 | 5.5897 | 7.9761
| IM |  | 19.8588 | 22.724 | 18.799 | 20.2374 | 20.4934 | 14.5122 | 27.2546
| TM |  | 38.5308 | 39.1483 | 39.5707 | 38.0314 | 38.7208 | 27.4807 | 38.2852
| FC Load/Ready Sale (Kton) |  | 633.0047 | 500.4598 | 388.2928 | 654.2495 | 2176.0069 |  | 2037
| ROM Stock | 98.2116 | 69.1389 | 109.2652 | 217.9929 | 149.7655 | 149.7655 |  | 88
| FC Stock | 7.1453 | 2.4608 | 37.1 | 38.2873 | 43.2867 | 43.2867 |  | 63
ok | TIS |  | Q1 | Q2 | Q3 | Q4 | Total |  | Total
| ROM Production |  | 118.3203 | 145.5654 | 149.74 | 81.1324 | 494.7581 |  | 606 | Done
| FC Product (Kton) |  | 39.0661 | 114.8019 | 86.0211 | 47.1958 | 287.0849 |  | 591
| Cv (GAR) |  | 6758.0516 | 6924.0836 | 6955.8116 | 7009.4203 | 6925.0262 | 5772.7007 | 6914.9248
| TS |  | 1.2622 | 1.2209 | 1.2274 | 1.1337 | 1.2141 | 1.0278 | 0.97968
| Ash |  | 3.6776 | 2.8489 | 2.5357 | 1.9932 | 2.7271 | 2.3995 | 3.7674
| IM |  | 6.3312 | 5.2064 | 5.1141 | 4.8733 | 5.277 | 4.4759 | 8.6903
| TM |  | 10.996 | 10.6172 | 9.3934 | 10.1689 | 10.2283 | 8.5566 | 4.7342
| FC Load/Ready Sale (Kton) |  | 23.6703 | 105.3116 | 102.7638 | 45.0029 | 276.7486 |  | 560
| ROM Stock | 31.6102 | 108.6258 | 138.6125 | 197.1148 | 234.5672 | 234.5672 |  | 14.9999
| FC Stock | 1.4476 | 16.5674 | 21.596 | 3.0886 | 0.79927 | 0.79927 |  | 31
ok | NPR |  | Q1 | Q2 | Q3 | Q4 | Total |  | Total
| ROM Production |  | 0 | 0 | 0 | 0 | 0 |  | 450
| FC Product (Kton) |  | 0 | 0 | 0 | 0 | 0 |  | 300
| NPR.MCV.HS |  | 0 | 0 | 0 | 0 | 0 |  | 300
| Cv (GAR) |  |  | 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0! | 6578.0649
| TS |  | 0 | 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0! | 1.108
| Ash |  | 0 | 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0! | 6.0164
| IM |  | 0 | 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0! | 7.5822
| TM |  | 0 | 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0! | 14.6874
| FC Load/barges (Kton) |  | 0 | 0 | 0 | 0 | 0 |  | 0
| ROM Stock | 0 | 0 | 0 | 0 | 0 | 0 |  | 150
| FC Stock | 0 | 0 | 0 | 0 | 0 | 0 |  | 300
| ITM GRAND TOTAL | EO Y24 | Q1 | Q2 | Q3 | Q4 | TOTAL |  | TOTAL
| ROM Production |  | 5331.7566 | 5085.9697 | 4966.5459 | 6293.6032 | 21677.8754 |  | 21854.387
| FC Production |  | 5240.3306 | 5135.7203 | 4607.915 | 6168.1189 | 21152.0849 |  | 21524
| FC + EBH + MBL |  | 4502.4161 | 4411.5593 | 3980.9672 | 5062.1423 | 12894.9425 |  | 22609.5
| ROM Stock | 980.1081 | 1243.5538 | 1247.913 | 1609.3597 | 1702.4594 | 1702.4594 |  | 1031.4556
| FC Stock | 236.7214 | 491.6666 | 578.3111 | 253.6377 | 490.8318 | 490.8318 |  | 850.7797
Notes :
Note on B45: Belfry Parulian Pandiangan: Exclude High ash stock and exclude fine coal stock
Note on B46: Belfry Parulian Pandiangan: MSY + PSY
Note on A145: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Still using budget for outlook 2024

## IMM 2025 (hidden)
IMM 2025 Production Plan - 2nd Draft Year 2025
Draft file | 1st Draft 2025 OPT5 email
Draft date | 2024-10-11
2025
Mine | Unit | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Total
IMM
OB removal | KBCM | 7619.4483 | 7224.3023 | 6870.0231 | 7815.9147 | 8233.4755 | 7596.8792 | 8769.11 | 8498.0492 | 8442.1757 | 8242.1086 | 7836.3005 | 7566.691 | 94714.4782
ROM production | Kton | 550 | 545 | 550 | 550 | 550 | 550 | 622.5 | 637.5 | 637.5 | 637.5 | 637.5 | 632.5 | 7100 | Include Fine Coal 150 KT
FC production | Kton | 541.75 | 536.75 | 541.75 | 551.75 | 551.75 | 551.75 | 635.75 | 637.75 | 637.75 | 637.75 | 637.75 | 637.75 | 7100 | Include Fine Coal 127.5 KT
SR (OB:ROM) | BCM/Ton | 13.8535 | 13.2556 | 12.491 | 14.2108 | 14.97 | 13.8125 | 14.0869 | 13.3303 | 13.2426 | 12.9288 | 12.2922 | 11.9631 | 13.3401
SR (OB:FC) | BCM/Ton | 14.0645 | 13.4593 | 12.6812 | 14.1657 | 14.9225 | 13.7687 | 13.7933 | 13.325 | 13.2374 | 12.9237 | 12.2874 | 11.8647 | 13.3401
Product type
IMM WB HCV LS | KTon | 154.9822 | 150.1922 | 153.4446 | 142.7318 | 131.892 | 90.2567 | 45.0528 | 60.1041 | 62.6233 | 73.6379 | 78.4656 | 85.4199 | 1228.8032
CV (ADB) | Kcal/kg | 6419.2447 | 6413.7544 | 6426.1701 | 6467.5963 | 6460.924 | 6575.6487 | 6763.3802 | 6738.8545 | 6733.8335 | 6761.7471 | 6563.4722 | 6582.7854 | 6526.4022
CV (GAR) | Kcal/kg | 6066.6995 | 6061.099 | 6072.9614 | 6113.1737 | 6106.3251 | 6216.0563 | 6397.4706 | 6374.5335 | 6369.463 | 6395.7374 | 6207.9868 | 6224.9984 | 6169.7769
TS | % | 0.79939 | 0.7996 | 0.80631 | 0.80238 | 0.79513 | 0.79814 | 0.80006 | 0.80071 | 0.80424 | 0.87778 | 0.89103 | 0.79705 | 0.8108
Ash | % | 8.5932 | 8.5723 | 8.4653 | 8.3497 | 8.4545 | 8.0612 | 8.0877 | 8.0139 | 8.0939 | 8.3113 | 8.6583 | 8.1212 | 8.3746
IM | % | 8.4968 | 8.6036 | 8.5701 | 8.2959 | 8.436 | 8.1042 | 7.1125 | 7.0457 | 7.1276 | 7.1603 | 7.2147 | 7.5403 | 8.0403
TM | % | 13.5221 | 13.629 | 13.5955 | 13.3212 | 13.4614 | 13.1296 | 12.1378 | 12.0711 | 12.153 | 12.1857 | 12.24 | 12.5656 | 13.0657
IMM WB HCV HS | KTon | 37.5178 | 37.3078 | 39.0554 | 47.2682 | 53.108 | 64.7433 | 84.9472 | 74.8959 | 82.3767 | 36.3621 | 41.5344 | 34.5801 | 633.6968
CV (ADB) | Kcal/kg | 6334.2014 | 6447.6669 | 6352.6384 | 6292.9167 | 6234.5184 | 6241.3054 | 6292.6616 | 6274.0003 | 6337.0578 | 6315.7415 | 6317.778 | 6314.7744 | 6305.5853
CV (GAR) | Kcal/kg | 5995.4058 | 6102.8668 | 6012.8803 | 5956.2491 | 5900.982 | 5903.8514 | 5953.1501 | 5935.2903 | 5994.0694 | 5972.607 | 5974.5067 | 5973.0938 | 5965.7827
TS | % | 2.4296 | 2.4051 | 2.5319 | 2.5966 | 2.6453 | 2.7647 | 2.7578 | 2.7055 | 2.6432 | 2.4887 | 2.3842 | 1.9722 | 2.579
Ash | % | 13.6503 | 13.0727 | 13.5362 | 14.1977 | 14.7482 | 14.5558 | 13.6829 | 14.4235 | 13.8303 | 13.8021 | 13.9633 | 13.2396 | 13.9606
IM | % | 6.0447 | 6.0271 | 6.0381 | 6.067 | 6.0651 | 7.0545 | 6.8576 | 6.9141 | 7.1513 | 7.5031 | 7.5101 | 7.1237 | 6.744
TM | % | 11.07 | 11.0525 | 11.0635 | 11.0924 | 11.0904 | 12.0799 | 11.883 | 11.9395 | 12.1767 | 12.5284 | 12.5355 | 12.1491 | 11.7694
IMM EB MCV LS | KTon | 3.3846 | 2.1986 | 2.3031 | 2.7672 | 1.8759 | 1.1106 | 0 | 0 | 0 | 0 | 0 | 0 | 13.6399
CV (ADB) | Kcal/kg | 6169.8029 | 6164.1006 | 6172.431 | 6174.4728 | 6169.8042 | 6172.235 | 0 | 0 | 0 | 0 | 0 | 0 | 6170.4731
CV (GAR) | Kcal/kg | 5821.883 | 5816.4871 | 5824.2204 | 5826.2223 | 5821.6228 | 5824.0809 | 0 | 0 | 0 | 0 | 0 | 0 | 5822.4314
TS | % | 0.89813 | 0.89994 | 0.9013 | 0.90153 | 0.90292 | 0.90326 | 0 | 0 | 0 | 0 | 0 | 0 | 0.90072
Ash | % | 8.6642 | 8.6538 | 8.6424 | 8.5289 | 8.516 | 8.5015 | 0 | 0 | 0 | 0 | 0 | 0 | 8.5978
IM | % | 11.333 | 11.3369 | 11.3693 | 11.3501 | 11.3996 | 11.3577 | 0 | 0 | 0 | 0 | 0 | 0 | 11.3544
TM | % | 16.333 | 16.3369 | 16.3693 | 16.3501 | 16.3996 | 16.3577 | 0 | 0 | 0 | 0 | 0 | 0 | 16.3544
IMM EB MCV MS | KTon | 2.5219 | 7.2155 | 26.7201 | 6.3272 | 12.6302 | 4.8088 | 12.095 | 14.9981 | 83.6973 | 94.4006 | 71.3353 | 85.9656 | 422.7155
CV (ADB) | Kcal/kg | 6368.0243 | 6310.0428 | 6367.3626 | 6390.1986 | 6342.5849 | 6357.9317 | 6392.812 | 6360.8597 | 6350.9993 | 6367.4084 | 6382.1767 | 6381.7919 | 6368.5845
CV (GAR) | Kcal/kg | 6013.744 | 5958.5719 | 6011.5142 | 6033.7912 | 5987.1311 | 6002.8141 | 6036.2059 | 6005.6296 | 5996.4183 | 6012.5832 | 6026.6617 | 6027.4417 | 6013.6725
TS | % | 1.5719 | 1.5705 | 1.5645 | 1.5541 | 1.5514 | 1.5491 | 1.5706 | 1.5667 | 1.5493 | 1.5533 | 1.5598 | 1.5724 | 1.5595
Ash | % | 6.0748 | 6.1531 | 6.1792 | 5.1976 | 5.2946 | 5.2369 | 5.1053 | 5.3674 | 5.3569 | 5.1697 | 5.1649 | 5.301 | 5.3287
Moist | % | 10.1273 | 10.2338 | 10.5326 | 10.3526 | 10.7819 | 10.4813 | 10.3659 | 10.4684 | 10.4436 | 10.274 | 10.2404 | 9.9508 | 10.2792
TM | % | 15.1273 | 15.2338 | 15.5326 | 15.3526 | 15.7819 | 15.4813 | 15.3659 | 15.4684 | 15.4436 | 15.274 | 15.2404 | 14.9508 | 15.2792
IMM EB MCV HS | KTon | 178.2096 | 221.9021 | 210.4737 | 176.8817 | 222.7749 | 272.7021 | 271.2697 | 244.6601 | 229.9673 | 242.725 | 308.9361 | 237.5396 | 2818.0417
CV (ADB) | Kcal/kg | 6347.1222 | 6317.8199 | 6324.5409 | 6328.8713 | 6320.3105 | 6319.0347 | 6315.784 | 6317.1884 | 6327.2604 | 6324.5739 | 6335.8606 | 6317.2306 | 6324.2125
CV (GAR) | Kcal/kg | 5993.2207 | 5964.4137 | 5970.1133 | 5975.1579 | 5966.157 | 5964.7264 | 5962.5027 | 5963.7526 | 5973.9264 | 5971.3799 | 5981.7772 | 5963.6088 | 5970.4742
TS | % | 2.2163 | 2.1721 | 2.1581 | 2.1819 | 2.1504 | 2.1399 | 2.1349 | 2.1452 | 2.1377 | 2.1623 | 2.1242 | 2.1498 | 2.1529
Ash | % | 5.3144 | 5.2652 | 5.2665 | 5.2347 | 5.2287 | 5.3139 | 5.2132 | 5.1545 | 5.2188 | 5.2236 | 5.2352 | 5.3535 | 5.2505
IM | % | 10.3264 | 10.6153 | 10.7781 | 10.5367 | 10.7688 | 10.8258 | 10.6125 | 10.6317 | 10.4635 | 10.466 | 10.5315 | 10.6782 | 10.6088
TM | % | 15.3264 | 15.6153 | 15.7781 | 15.5367 | 15.7688 | 15.8258 | 15.6125 | 15.6317 | 15.4635 | 15.466 | 15.5315 | 15.6782 | 15.6088
IMM EB MCV HS Extreme | KTon | 160.884 | 113.6838 | 105.5031 | 163.0239 | 116.7191 | 105.3786 | 209.6354 | 230.3419 | 166.3354 | 177.8744 | 124.7286 | 181.4948 | 1855.6029
CV (ADB) | Kcal/kg | 6176.1673 | 6195.2236 | 6154.2215 | 6191.1364 | 6191.7838 | 6165.3606 | 6174.2516 | 6144.4754 | 6173.2311 | 6175.1568 | 6151.3106 | 6175.3918 | 6171.5136
CV (GAR) | Kcal/kg | 5832.1439 | 5849.3501 | 5810.4272 | 5845.5186 | 5845.7233 | 5821.08 | 5828.8234 | 5801.558 | 5828.3648 | 5830.0236 | 5807.2612 | 5830.3912 | 5826.8063
TS | % | 2.8072 | 2.8086 | 2.8099 | 2.7984 | 2.8018 | 2.7983 | 2.8022 | 2.8018 | 2.8024 | 2.8091 | 2.807 | 2.8004 | 2.8037
Ash | % | 6.7263 | 6.4491 | 6.8046 | 6.2034 | 6.233 | 6.7521 | 6.3379 | 6.749 | 6.2944 | 6.2013 | 6.4695 | 6.1392 | 6.4335
IM | % | 10.2362 | 10.4409 | 10.4956 | 10.4338 | 10.539 | 10.4602 | 10.629 | 10.4088 | 10.4982 | 10.5395 | 10.6042 | 10.5017 | 10.4817
TM | % | 15.2362 | 15.4409 | 15.4956 | 15.4338 | 15.539 | 15.4602 | 15.629 | 15.4088 | 15.4982 | 15.5395 | 15.6042 | 15.5017 | 15.4817
FINE COAL | KTon | 4.25 | 4.25 | 4.25 | 12.75 | 12.75 | 12.75 | 12.75 | 12.75 | 12.75 | 12.75 | 12.75 | 12.75 | 127.5
CV (ADB) | Kcal/kg | 3500 | 3500 | 3500 | 3500 | 3500 | 3500 | 3500 | 3500 | 3500 | 3500 | 3500 | 3500 | 3500
CV (GAR) | Kcal/kg | 3146.0674 | 3146.0674 | 3146.0674 | 3146.0674 | 3146.0674 | 3146.0674 | 3146.0674 | 3146.0674 | 3146.0674 | 3146.0674 | 3146.0674 | 3146.0674 | 3146.0674
TS | % | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Ash | % | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40
IM | % | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11
TM | % | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20
0

## TCM 2025 (hidden)
TCM 2025 Production Plan - 2nd Draft
Draft file | Draft Production Plan Year 2025 TCM (12 Oct 2024)_V2.1
Draft date | 2024-10-12
2025
Mine | Unit | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Total
TCM
OB removal | KBCM | 4195 | 4015 | 4020 | 4250 | 4410 | 4660 | 4720 | 5055 | 4740 | 3990 | 3805 | 3790 | 51650
ROM production | Kton | 200 | 215 | 217 | 255 | 285 | 315 | 310 | 335.387 | 307 | 300 | 281 | 280 | 3300.387
FC production | Kton | 217 | 235 | 258 | 257 | 290 | 305 | 315 | 320 | 285 | 253 | 242 | 253 | 3230
SR (OB:ROM) | BCM/Ton | 20.975 | 18.6744 | 18.5253 | 16.6667 | 15.4737 | 14.7937 | 15.2258 | 15.0721 | 15.4397 | 13.3 | 13.5409 | 13.5357 | 15.6497
SR (OB:FC) | BCM/Ton | 19.3318 | 17.0851 | 15.5814 | 16.537 | 15.2069 | 15.2787 | 14.9841 | 15.7969 | 16.6316 | 15.7708 | 15.7231 | 14.9802 | 15.9907
Product type
TCM HCV LS | KTon | 110 | 130 | 130 | 140 | 150 | 170 | 170 | 150 | 155 | 115 | 115 | 95 | 1630 | 50.46%
CV (ADB) | Kcal/kg | 6736.8284 | 6845.675 | 6855.2974 | 6799.3995 | 6851.0847 | 6896.7899 | 6784.1768 | 6817.3511 | 6897.6838 | 6835.9324 | 6832.8721 | 6795.1116 | 6832.3388
CV (GAR) | Kcal/kg | 6331.7794 | 6327.6426 | 6345.3425 | 6327.8237 | 6373.2296 | 6243.3002 | 6268.7387 | 6402.2298 | 6455.744 | 6429.1851 | 6453.9309 | 6360.7189 | 6355.6513
TS | % | 0.63239 | 0.69248 | 0.652 | 0.6548 | 0.61487 | 0.6376 | 0.63464 | 0.55063 | 0.52383 | 0.52786 | 0.54698 | 0.54361 | 0.60341
Ash | % | 5.14 | 4.5591 | 4.5963 | 5.1237 | 4.8279 | 4.5406 | 5.4694 | 4.9514 | 4.2318 | 4.7988 | 4.93 | 4.9975 | 4.8411
IM | % | 7.9684 | 7.5074 | 7.3053 | 7.3142 | 7.2934 | 7.0845 | 7.3044 | 7.5576 | 7.1827 | 7.4775 | 7.325 | 7.6231 | 7.3863
TM | % | 13.5018 | 14.5066 | 14.2007 | 13.7425 | 13.7596 | 15.8885 | 14.3471 | 13.1866 | 13.1296 | 12.9827 | 12.4646 | 13.5285 | 13.8465
TCM HCV HS | KTon | 100 | 100 | 120 | 110 | 130 | 120 | 130 | 150 | 120 | 130 | 120 | 150 | 1480 | 45.82%
CV (ADB) | Kcal/kg | 6866.5729 | 6778.7713 | 6894.8648 | 6822.1779 | 6836.7655 | 6757.1099 | 6815.116 | 6823.9609 | 6790.9747 | 6843.9084 | 6814.7913 | 6804.9311 | 6820.7361
CV (GAR) | Kcal/kg | 6528.8013 | 6523.441 | 6602.1856 | 6481.0855 | 6487.5274 | 6515.5714 | 6445.0323 | 6472.1448 | 6412.4032 | 6476.7335 | 6460.6228 | 6423.2952 | 6482.812
TS | % | 1.8419 | 2.1454 | 1.7213 | 1.772 | 1.7758 | 2.0871 | 1.8138 | 1.8287 | 1.8482 | 1.8968 | 1.819 | 1.9905 | 1.8762
Ash | % | 6.7257 | 7.6729 | 55.9656 | 5.9371 | 5.2918 | 7.3265 | 5.9375 | 5.9832 | 6.008 | 6.0191 | 6.0931 | 5.979 | 10.2546
IM | % | 7.2396 | 7.118 | 6.7065 | 6.8833 | 6.7129 | 6.6877 | 6.6455 | 6.3583 | 6.7264 | 6.4663 | 6.2063 | 6.1537 | 6.6258
TM | % | 11.8026 | 10.6165 | 10.6667 | 11.5389 | 11.4782 | 10.0232 | 11.715 | 11.1861 | 11.926 | 11.4844 | 11.0808 | 11.4168 | 11.2522
TCM.LCV.MS.HA | KTon | 7 | 5 | 8 | 7 | 10 | 15 | 15 | 20 | 10 | 8 | 7 | 8 | 120 | 3.715%
CV (ADB) | Kcal/kg | 3851.3 | 3874.3 | 4709.15 | 3863.65 | 3953.65 | 6126.55 | 6034.4 | 5942.25 | 5918.25 | 5969.25 | 5910.25 | 5938.25 | 5397.1613
CV (GAR) | Kcal/kg | 3581.7631 | 3599.0009 | 4341.3047 | 3587.2263 | 3651.2002 | 5641.0449 | 5567.1958 | 5442.6121 | 5422.5222 | 5471.7948 | 5388.109 | 5438.9485 | 4963.5346
TS | % | 1.16 | 1.15 | 1.44 | 0.51 | 0.5 | 1.45 | 1.5217 | 1.5933 | 1.6133 | 1.5833 | 1.5533 | 1.6133 | 1.3582
Ash | % | 13.6 | 13.18 | 12.69 | 14.445 | 14.2 | 6.835 | 8.9933 | 11.1517 | 11.1417 | 11.0117 | 11.1717 | 11.9817 | 11.1647
IM | % | 7.41 | 7.54 | 7.16 | 6.52 | 6.43 | 6.09 | 6.1267 | 6.1633 | 6.1633 | 6.1633 | 6.1633 | 6.1633 | 6.3891
TM | % | 13.89 | 14.11 | 14.412 | 13.208 | 13.588 | 13.532 | 13.3947 | 14.0533 | 14.0233 | 13.9833 | 14.4533 | 14.0533 | 13.8507

## BEK 2025 (hidden)
BEK 2025 Production Plan - 2nd Draft
Draft file | 00. BEK Production Budget Y25_ver2.2_08Oct24_rwsp
Draft date | 2024-10-08
2025
Mine | Unit | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Total
BEK
OB removal | KBCM | 7995 | 7084 | 7619 | 7232 | 7571 | 7593 | 8097 | 8330 | 7698 | 7482 | 6860 | 7389 | 90950
ROM production | Kton | 684 | 658 | 685.5 | 564 | 663 | 712 | 745 | 752 | 704 | 627.5 | 589 | 616 | 8000
FC production | Kton | 700 | 700 | 700 | 650 | 650 | 650 | 700 | 710 | 700 | 660 | 640 | 640 | 8100
SR (OB:ROM) | BCM/Ton | 11.6886 | 10.766 | 11.1145 | 12.8227 | 11.4193 | 10.6643 | 10.8685 | 11.0771 | 10.9347 | 11.9235 | 11.6469 | 11.9951 | 11.3688
SR (OB:FC) | BCM/Ton | 11.4214 | 10.12 | 10.8843 | 11.1262 | 11.6477 | 11.6815 | 11.5671 | 11.7324 | 10.9971 | 11.3364 | 10.7188 | 11.5453 | 11.2284
Product type
BEK MCV LS | KTon | 400 | 480 | 480 | 465 | 465 | 460 | 500 | 490 | 480 | 460 | 440 | 440 | 5560
CV (ADB) | Kcal/kg | 6356.6925 | 6211.4538 | 6164.5544 | 6166.0095 | 6215.11 | 6171.0497 | 6202.3209 | 6155.9114 | 6139.5186 | 6134.6756 | 6109.9273 | 6139.0823 | 6178.9758
CV (GAR) | Kcal/kg | 6030.4358 | 5774.2277 | 5860.9708 | 5868.1864 | 5954.6027 | 5916.1255 | 5984.187 | 5944.3266 | 5921.0085 | 5916.7362 | 5898.291 | 5928.9325 | 5915.2264
TS | % | 0.53158 | 0.52889 | 0.5114 | 0.47877 | 0.51889 | 0.54684 | 0.6156 | 0.65164 | 0.57083 | 0.61028 | 0.68843 | 0.67517 | 0.5772
Ash | % | 4.5798 | 4.3819 | 4.7059 | 4.7159 | 4.47 | 4.6727 | 5.1675 | 5.2807 | 5.3764 | 5.2082 | 4.9555 | 5.0376 | 4.8848
IM | % | 11.5325 | 12.1617 | 11.7688 | 10.9822 | 11.9963 | 11.3734 | 10.8514 | 11.2599 | 11.1283 | 11.3129 | 11.8103 | 11.5197 | 11.4694
TM | % | 16.0731 | 18.3447 | 16.1139 | 15.2818 | 15.685 | 15.0345 | 13.9867 | 14.31 | 14.2913 | 14.4636 | 14.865 | 14.5485 | 15.2419
BEK MCV MS | KTon | 300 | 220 | 220 | 185 | 185 | 190 | 200 | 220 | 220 | 200 | 200 | 200 | 2540
CV (ADB) | Kcal/kg | 6236.9634 | 6049.986 | 6043.243 | 6018.0484 | 5964.0677 | 5984.9901 | 5967.3108 | 6020.9507 | 6068.0016 | 6040.4014 | 5983.9188 | 6135.5256 | 6051.3543
CV (GAR) | Kcal/kg | 5978.3055 | 5788.4874 | 5780.4749 | 5757.1239 | 5689.0306 | 5723.4269 | 5710.0663 | 5767.3036 | 5816.7184 | 5783.944 | 5714.3882 | 5899.7671 | 5792.8232
TS | % | 1.787 | 1.8051 | 1.7535 | 1.753 | 1.7123 | 1.7854 | 1.8239 | 1.742 | 1.7014 | 1.7606 | 1.7678 | 1.7233 | 1.7606
Ash | % | 4.7301 | 5.5271 | 5.5458 | 5.7433 | 6.1338 | 6.4532 | 6.4437 | 6.2121 | 5.7608 | 5.8895 | 6.1089 | 5.112 | 5.7572
IM | % | 11.0894 | 10.939 | 11.1033 | 10.7531 | 10.9318 | 10.5429 | 10.9263 | 10.5327 | 10.5196 | 10.609 | 10.4098 | 10.3006 | 10.7369
TM | % | 14.7767 | 14.7885 | 14.9686 | 14.6226 | 15.0392 | 14.4524 | 14.7662 | 14.3018 | 14.2251 | 14.4043 | 14.4451 | 13.7474 | 14.5518

## JBG 2025 (hidden)
JBG 2025 Production Plan - 2nd draft
Draft file | JBG Production Budget 2025 update 16112024
Draft date | 2024-11-16
2025
Mine | Unit | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Total
JBG
OB removal | KBCM | 103.007 | 93.07 | 98.059 | 280.6245 | 579.3785 | 448.889 | 536.383 | 575.345 | 590.094 | 632.103 | 557.72 | 543.935 | 5038.608
ROM production | Kton | 0 | 0 | 0 | 0 | 20 | 37 | 51 | 60 | 70 | 75 | 68 | 67 | 448
FC production | Kton | 0 | 0 | 0 | 0 | 18 | 35 | 50 | 58 | 68 | 72 | 66 | 66 | 433
SR (OB:ROM) | BCM/Ton | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 28.9689 | 12.1321 | 10.5173 | 9.5891 | 8.4299 | 8.428 | 8.2018 | 8.1184 | 11.2469
SR (OB:FC) | BCM/Ton | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 32.1877 | 12.8254 | 10.7277 | 9.9197 | 8.6779 | 8.7792 | 8.4503 | 8.2414 | 11.6365
Product type
JBG | KTon | 0 | 0 | 0 | 0 | 18 | 35 | 50 | 58 | 68 | 72 | 66 | 66 | 433
CV (ADB) | Kcal/kg | 0 | 0 | 0 | 0 | 5253.8295 | 5240.7986 | 5259.589 | 5280.4872 | 5246.6256 | 5280.3769 | 5298.5008 | 5258.6221 | 5267.8346
CV (GAR) | Kcal/kg | 0 | 0 | 0 | 0 | 4442.3525 | 4414.0197 | 4416.3842 | 4432.5862 | 4408.926 | 4423.0872 | 4453.786 | 4407.9045 | 4423.7946
TS | % | 0 | 0 | 0 | 0 | 0.38874 | 0.35403 | 0.38864 | 0.37486 | 0.36433 | 0.35476 | 0.35693 | 0.38386 | 0.36899
Ash | % | 0 | 0 | 0 | 0 | 4.3469 | 4.2775 | 4.5772 | 4.4107 | 4.3138 | 4.438 | 4.3733 | 4.6218 | 4.4323
IM | % | 0 | 0 | 0 | 0 | 17.434 | 17.2038 | 17.034 | 16.8716 | 16.9773 | 16.7251 | 16.9357 | 16.7621 | 16.9259
TM | % | 0 | 0 | 0 | 0 | 30.1867 | 30.2656 | 30.3349 | 30.2198 | 30.2331 | 30.2451 | 30.1783 | 30.2279 | 30.2366
Note on A8: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Include Mud and Sliding

## GPK 2025 (hidden)
GPK 2025 Production Plan - 2nd Draft
Draft file | Draft GPK Production Plan 2025 Ver.1.3 (2.1 MTon) (22 Sept'24_)
Draft date | 2024-09-22
| Mine | Unit | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Total
GPK
| OB Removal | KBCM | 630 | 580 | 630 | 610 | 700 | 675 | 745 | 790 | 785 | 880 | 705 | 770 | 8500
| ROM Production | Kton | 184 | 166 | 182 | 175 | 180 | 175 | 160 | 160 | 160 | 196 | 175 | 187 | 2100
| FC Production | Kton | 200 | 180 | 190 | 175 | 180 | 175 | 90 | 50 | 90 | 210 | 260 | 250 | 2050
| SR (OB:ROM) | BCM/Ton | 3.4239 | 3.494 | 3.4615 | 3.4857 | 3.8889 | 3.8571 | 4.6562 | 4.9375 | 4.9062 | 4.4898 | 4.0286 | 4.1176 | 4.0476
| SR (OB:FC) | BCM/Ton | 3.15 | 3.2222 | 3.3158 | 3.4857 | 3.8889 | 3.8571 | 8.2778 | 15.8 | 8.7222 | 4.1905 | 2.7115 | 3.08 | 4.1463
Product type
| GPK LCV LS | Kton | 200 | 180 | 190 | 175 | 180 | 175 | 90 | 50 | 90 | 210 | 260 | 250 | 2050
| CV (ADB) | Kcal/Kg | 4214.9372 | 4210.4116 | 4317.487 | 4512.7819 | 4537.3358 | 4602.8515 | 4588.206 | 4598.3567 | 4627.3989 | 4548.2078 | 4445.7477 | 4421.1064 | 4443.2962
| CV (GAR) | Kcal/Kg | 3597.7504 | 3594.5296 | 3663.6762 | 3731.5323 | 3747.0877 | 3753.0309 | 3709.9842 | 3710.8591 | 3754.9789 | 3802.469 | 3810.8052 | 3790.9104 | 3727.504
| TS | % | 0.11569 | 0.11701 | 0.15581 | 0.15133 | 0.15302 | 0.14876 | 0.16964 | 0.1691 | 0.15833 | 0.16553 | 0.17248 | 0.16287 | 0.15227
| Ash | % | 10.1457 | 10.2139 | 9.4792 | 8.2664 | 7.972 | 8.1087 | 9.7175 | 9.7409 | 8.5788 | 6.4456 | 5.4512 | 5.9086 | 7.9761
| IM | % | 27.2738 | 27.292 | 26.9771 | 25.1243 | 25.0639 | 24.2542 | 31.6027 | 31.4781 | 27.5216 | 26.4417 | 28.9143 | 29.0422 | 27.2546
| TM | % | 37.9185 | 37.923 | 38.043 | 37.9509 | 37.979 | 38.0738 | 37.7175 | 37.7338 | 37.8637 | 38.4165 | 39.0685 | 39.1676 | 38.2852

## TIS 2025 (hidden)
TIS 2025 Production Plan - 2nd Draft
Draft file | TIS_Draft Plan Production Y2025_R03 (18Nov24)
Draft date | 2024-11-18
2025
Mine | Unit | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Total
TIS
OB removal | KBCM | 982.5 | 833.26 | 955 | 979.8 | 1028.75 | 1131.36 | 1343.54 | 1450.15 | 1249.8 | 960.24 | 867.28 | 919 | 12700.68
ROM production | Kton | 30 | 35 | 42 | 45 | 57 | 56 | 62 | 65 | 60 | 54 | 50 | 50 | 606
FC production | Kton | 30 | 30 | 40 | 45 | 50 | 50 | 60 | 60 | 55 | 55 | 55 | 60 | 590
SR (OB:ROM) | BCM/Ton | 32.75 | 23.8074 | 22.7381 | 21.7733 | 18.0482 | 20.2029 | 21.67 | 22.31 | 20.83 | 17.7822 | 17.3456 | 18.38 | 20.9582
SR (OB:FC) | BCM/Ton | 32.75 | 27.7753 | 23.875 | 21.7733 | 20.575 | 22.6272 | 22.3923 | 24.1692 | 22.7236 | 17.4589 | 15.7687 | 15.3167 | 21.5266
Product type
TIS | KTon | 30 | 30 | 40 | 45 | 50 | 50 | 60 | 60 | 55 | 55 | 55 | 60 | 590
CV (ADB) | Kcal/kg | 7190.3485 | 7200.3485 | 7180.3485 | 7181.199 | 7192.7045 | 7244.7561 | 7393.4564 | 7312.7855 | 7299.2735 | 7232.9742 | 7341.3072 | 7323.6173 | 7269.1507
CV (GAR) | Kcal/kg | 6824.4902 | 6820.347 | 6806.1231 | 6833.9324 | 6994.3648 | 7027.769 | 7159.1562 | 7071.2557 | 6895.4537 | 6801.9028 | 6932.8199 | 6909.6969 | 6937.7795
TS | % | 1.4308 | 1.514 | 1.5556 | 1.5556 | 1.5556 | 1.2556 | 1.2556 | 1.2956 | 1.1556 | 1.2556 | 1.1826 | 1.2556 | 1.3342
Ash | % | 2.9538 | 3.1342 | 3.1952 | 3.3935 | 3.2981 | 2.807 | 2.8034 | 3.0056 | 2.6377 | 2.8831 | 2.5935 | 2.6437 | 2.9184
IM | % | 4.4328 | 4.5235 | 4.5521 | 4.5577 | 4.7566 | 4.5533 | 4.6037 | 4.8186 | 4.569 | 4.9642 | 4.6397 | 4.7277 | 4.6608
TM | % | 9.2954 | 9.5623 | 9.5267 | 9.173 | 7.383 | 7.412 | 7.6268 | 7.9623 | 9.8486 | 10.6281 | 9.9458 | 10.1123 | 9.0079

## NPR 2025 (hidden)
NPR 2025 Production Plan - 2nd Draft
Draft file | Draft NPR Production Plan 2025 - 450 Kton ROM
Draft date | 2024-11-17
2025
Mine | Unit | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Total
NPR
OB removal | KBCM | 0 | 0 | 129 | 535 | 542 | 543 | 586 | 594 | 578 | 752 | 682 | 742.5 | 5683.5
ROM production | KTon | 0 | 0 | 0 | 0 | 25 | 55 | 60 | 60 | 55 | 65 | 65 | 65 | 450
FC production | KTon | 0 | 0 | 0 | 0 | 17 | 37 | 40 | 40 | 37 | 43 | 43 | 43 | 300
SR (OB:ROM) | BCM/Ton | 0 | 0 | 0 | 0 | 21.68 | 9.8727 | 9.7667 | 9.9 | 10.5091 | 11.5692 | 10.4923 | 11.4231 | 12.63
SR (OB:FC) | BCM/Ton | 0 | 0 | 0 | 0 | 31.8824 | 14.6757 | 14.65 | 14.85 | 15.6216 | 17.4884 | 15.8605 | 17.2674 | 18.945
Product type
MCV-LS | Ton | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43 | 43
CV (ADB) | Kcal/kg | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6514.6914 | 6514.6914
CV (GAR) | Kcal/kg | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6041.8217 | 6041.8217
TS | % | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.99869 | 0.99869
Ash | % | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5.9413 | 5.9413
IM | % | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.45 | 8.45
TM | % | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15.0952 | 15.0952
MCV-HS | Ton | 0 | 0 | 0 | 0 | 17 | 37 | 40 | 40 | 37 | 43 | 43 | 0 | 257
CV (ADB) | Kcal/kg | 0 | 0 | 0 | 0 | 6479.8736 | 6587.4532 | 6598.4997 | 6640.8571 | 6546.9132 | 6622.5542 | 6577.0752 | 0 | 6588.6683
CV (GAR) | Kcal/kg | 0 | 0 | 0 | 0 | 6043.42 | 6088.4834 | 6058.6886 | 6088.0129 | 6082.5631 | 6087.883 | 6074.4841 | 0 | 6077.4969
TS | % | 0 | 0 | 0 | 0 | 1.1963 | 1.2298 | 1.1899 | 1.1598 | 1.0431 | 1.0999 | 1.0172 | 0 | 1.1263
Ash | % | 0 | 0 | 0 | 0 | 6.1898 | 6.1677 | 6.5217 | 6.2198 | 5.498 | 6.2002 | 5.4953 | 0 | 6.0289
IM | % |  |  |  | 0 | 8.626 | 7.4 | 6.7387 | 6.6266 | 8.5113 | 6.8655 | 8.0495 | 0 | 7.437
TM | % | 0 | 0 | 0 | 0 | 14.7805 | 14.414 | 14.3683 | 14.3998 | 15.0003 | 14.3847 | 15.0759 | 0 | 14.6192