## Budget 2025
ITM plan year 2024
As of 18 Nov'24
IMM | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Total
OB Removal (KBcm) | 7619.4483 | 7224.3023 | 6870.0231 | 7815.9147 | 8233.4755 | 7596.8792 | 8769.11 | 8498.0492 | 8442.1757 | 8242.1086 | 7836.3005 | 7566.691 | 94714.4782 | Done
PAMA (WB) | 2904.786 | 2754.4503 | 2424.321 | 2767.1447 | 2927.6178 | 2460.4194 | 3157.9028 | 3107.2173 | 2899.6426 | 2829.8233 | 2690.1553 | 2609.1784 | 33532.659
PAMA (EB) | 4714.6622 | 4469.852 | 4445.7021 | 5048.77 | 5305.8577 | 5136.4598 | 5611.2072 | 5390.8319 | 5542.5331 | 5412.2853 | 5146.1452 | 4957.5126 | 61181.8192
ROM Production (Kton) | 537.5 | 532.5 | 537.5 | 537.5 | 537.5 | 537.5 | 610 | 625 | 625 | 625 | 625 | 620 | 6950
PAMA (WB) | 192.5 | 187.5 | 192.5 | 190 | 185 | 155 | 130 | 135 | 145 | 110 | 120 | 120 | 1862.5
PAMA (EB) | 345 | 345 | 345 | 347.5 | 352.5 | 382.5 | 480 | 490 | 480 | 515 | 505 | 500 | 5087.5
Fine Coal | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SR ROM Total | 14.1757 | 13.5668 | 12.7814 | 14.5412 | 15.3181 | 14.1337 | 14.3756 | 13.5969 | 13.5075 | 13.1874 | 12.5381 | 12.2043 | 13.628
FC Product (Kton) | 541.75 | 536.75 | 541.75 | 551.75 | 551.75 | 551.75 | 635.75 | 637.75 | 637.75 | 637.75 | 637.75 | 637.75 | 7100
PAMA (WB) | 192.5 | 187.5 | 192.5 | 190 | 185 | 155 | 130 | 135 | 145 | 110 | 120 | 120 | 1862.5
PAMA (EB) | 345 | 345 | 345 | 349 | 354 | 384 | 493 | 490 | 480 | 515 | 505 | 505 | 5110
Fine Coal | 4.25 | 4.25 | 4.25 | 12.75 | 12.75 | 12.75 | 12.75 | 12.75 | 12.75 | 12.75 | 12.75 | 12.75 | 127.5
SR FC Total | 14.0645 | 13.4593 | 12.6812 | 14.1657 | 14.9225 | 13.7687 | 13.7933 | 13.325 | 13.2374 | 12.9237 | 12.2874 | 11.8647 | 13.3401
IMM-WB.HCV.LS | 154.9822 | 150.1922 | 153.4446 | 142.7318 | 131.892 | 90.2567 | 45.0528 | 60.1041 | 62.6233 | 73.6379 | 78.4656 | 85.4199 | 1228.8032
CV(GAR) | 6066.6995 | 6061.099 | 6072.9614 | 6113.1737 | 6106.3251 | 6216.0563 | 6397.4706 | 6374.5335 | 6369.463 | 6395.7374 | 6207.9868 | 6224.9984 | 6169.7769
TS | 0.79939 | 0.7996 | 0.80631 | 0.80238 | 0.79513 | 0.79814 | 0.80006 | 0.80071 | 0.80424 | 0.87778 | 0.89103 | 0.79705 | 0.8108
Ash | 8.5932 | 8.5723 | 8.4653 | 8.3497 | 8.4545 | 8.0612 | 8.0877 | 8.0139 | 8.0939 | 8.3113 | 8.6583 | 8.1212 | 8.3746
Moist | 8.4968 | 8.6036 | 8.5701 | 8.2959 | 8.436 | 8.1042 | 7.1125 | 7.0457 | 7.1276 | 7.1603 | 7.2147 | 7.5403 | 8.0403
TM | 13.5221 | 13.629 | 13.5955 | 13.3212 | 13.4614 | 13.1296 | 12.1378 | 12.0711 | 12.153 | 12.1857 | 12.24 | 12.5656 | 13.0657
IMM-WB.HCV.HS | 37.5178 | 37.3078 | 39.0554 | 47.2682 | 53.108 | 64.7433 | 84.9472 | 74.8959 | 82.3767 | 36.3621 | 41.5344 | 34.5801 | 633.6968
CV(GAR) | 5995.4058 | 6102.8668 | 6012.8803 | 5956.2491 | 5900.982 | 5903.8514 | 5953.1501 | 5935.2903 | 5994.0694 | 5972.607 | 5974.5067 | 5973.0938 | 5965.7827
TS | 2.4296 | 2.4051 | 2.5319 | 2.5966 | 2.6453 | 2.7647 | 2.7578 | 2.7055 | 2.6432 | 2.4887 | 2.3842 | 1.9722 | 2.579
Ash | 13.6503 | 13.0727 | 13.5362 | 14.1977 | 14.7482 | 14.5558 | 13.6829 | 14.4235 | 13.8303 | 13.8021 | 13.9633 | 13.2396 | 13.9606
Moist | 6.0447 | 6.0271 | 6.0381 | 6.067 | 6.0651 | 7.0545 | 6.8576 | 6.9141 | 7.1513 | 7.5031 | 7.5101 | 7.1237 | 6.744
TM | 11.07 | 11.0525 | 11.0635 | 11.0924 | 11.0904 | 12.0799 | 11.883 | 11.9395 | 12.1767 | 12.5284 | 12.5355 | 12.1491 | 11.7694
IMM-EB.MCV.LS | 3.3846 | 2.1986 | 2.3031 | 2.7672 | 1.8759 | 1.1106 | 0 | 0 | 0 | 0 | 0 | 0 | 13.6399
CV(GAR) | 5821.883 | 5816.4871 | 5824.2204 | 5826.2223 | 5821.6228 | 5824.0809 | 0 | 0 | 0 | 0 | 0 | 0 | 5822.4314
TS | 0.89813 | 0.89994 | 0.9013 | 0.90153 | 0.90292 | 0.90326 | 0 | 0 | 0 | 0 | 0 | 0 | 0.90072
Ash | 8.6642 | 8.6538 | 8.6424 | 8.5289 | 8.516 | 8.5015 | 0 | 0 | 0 | 0 | 0 | 0 | 8.5978
Moist | 11.333 | 11.3369 | 11.3693 | 11.3501 | 11.3996 | 11.3577 | 0 | 0 | 0 | 0 | 0 | 0 | 11.3544
TM | 16.333 | 16.3369 | 16.3693 | 16.3501 | 16.3996 | 16.3577 | 0 | 0 | 0 | 0 | 0 | 0 | 16.3544
IMM-EB.MCV.MS | 2.5219 | 7.2155 | 26.7201 | 6.3272 | 12.6302 | 4.8088 | 12.095 | 14.9981 | 83.6973 | 94.4006 | 71.3353 | 85.9656 | 422.7155
CV(GAR) | 6013.744 | 5958.5719 | 6011.5142 | 6033.7912 | 5987.1311 | 6002.8141 | 6036.2059 | 6005.6296 | 5996.4183 | 6012.5832 | 6026.6617 | 6027.4417 | 6013.6725
TS | 1.5719 | 1.5705 | 1.5645 | 1.5541 | 1.5514 | 1.5491 | 1.5706 | 1.5667 | 1.5493 | 1.5533 | 1.5598 | 1.5724 | 1.5595
Ash | 6.0748 | 6.1531 | 6.1792 | 5.1976 | 5.2946 | 5.2369 | 5.1053 | 5.3674 | 5.3569 | 5.1697 | 5.1649 | 5.301 | 5.3287
Moist | 10.1273 | 10.2338 | 10.5326 | 10.3526 | 10.7819 | 10.4813 | 10.3659 | 10.4684 | 10.4436 | 10.274 | 10.2404 | 9.9508 | 10.2792
TM | 15.1273 | 15.2338 | 15.5326 | 15.3526 | 15.7819 | 15.4813 | 15.3659 | 15.4684 | 15.4436 | 15.274 | 15.2404 | 14.9508 | 15.2792
IMM-EB.MCV.HS | 339.0935 | 335.5859 | 315.9768 | 339.9056 | 339.494 | 378.0807 | 480.905 | 475.0019 | 396.3027 | 420.5994 | 433.6647 | 419.0344 | 4673.6446
CV(GAR) | 5916.7973 | 5925.4345 | 5916.7949 | 5912.981 | 5924.7515 | 5924.6893 | 5904.2294 | 5885.0998 | 5912.8315 | 5911.5994 | 5931.5837 | 5905.9088 | 5914.4155
TS | 2.4966 | 2.3878 | 2.3758 | 2.4776 | 2.3743 | 2.3234 | 2.4258 | 2.4636 | 2.4167 | 2.4358 | 2.3206 | 2.4316 | 2.4107
Ash | 5.9843 | 5.6663 | 5.7801 | 5.6993 | 5.574 | 5.7147 | 5.7035 | 5.9277 | 5.6702 | 5.6371 | 5.5902 | 5.6939 | 5.72
Moist | 10.2836 | 10.5562 | 10.6838 | 10.4873 | 10.6898 | 10.7239 | 10.6197 | 10.5236 | 10.4781 | 10.4971 | 10.5525 | 10.6017 | 10.5582
TM | 15.2836 | 15.5562 | 15.6838 | 15.4873 | 15.6898 | 15.7239 | 15.6197 | 15.5236 | 15.4781 | 15.4971 | 15.5525 | 15.6017 | 15.5582
Fine Coal | 4.25 | 4.25 | 4.25 | 12.75 | 12.75 | 12.75 | 12.75 | 12.75 | 12.75 | 12.75 | 12.75 | 12.75 | 127.5
CV(GAR) | 3146.0674 | 3146.0674 | 3146.0674 | 3146.0674 | 3146.0674 | 3146.0674 | 3146.0674 | 3146.0674 | 3146.0674 | 3146.0674 | 3146.0674 | 3146.0674 | 3146.0674
TS | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Ash | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40
Moist | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11
TM | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20
TCM | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Total
OB Removal (KBcm) | 4195 | 4015 | 4020 | 4250 | 4410 | 4660 | 4720 | 5055 | 4740 | 3990 | 3805 | 3790 | 51650 | Done
PAMA | 2025 | 1905 | 1870 | 2010 | 2110 | 2210 | 2320 | 2305 | 2240 | 1890 | 1745 | 1770 | 24400
MAP | 890 | 810 | 750 | 940 | 950 | 950 | 1000 | 1050 | 950 | 900 | 860 | 950 | 11000
PJPN | 1280 | 1300 | 1400 | 1300 | 1350 | 1500 | 1400 | 1700 | 1550 | 1200 | 1200 | 1070 | 16250
ROM Production (Kton) | 200 | 215 | 217 | 255 | 285 | 315 | 310 | 335.387 | 307 | 300 | 281 | 280 | 3300.387
PAMA | 130 | 145 | 150 | 160 | 170 | 200 | 195 | 210 | 210 | 195 | 180 | 185 | 2130
MAP | 45 | 40 | 37 | 45 | 50 | 50 | 50 | 55 | 47 | 45 | 41 | 45 | 550
PJPN | 25 | 30 | 30 | 50 | 65 | 65 | 65 | 70.387 | 50 | 60 | 60 | 50 | 620.387
SR ROM with void | 20.975 | 18.6744 | 18.5253 | 16.6667 | 15.4737 | 14.7937 | 15.2258 | 15.0721 | 15.4397 | 13.3 | 13.5409 | 13.5357 | 15.6497
FC Product CP (Kton) | 217 | 235 | 258 | 257 | 290 | 305 | 315 | 320 | 285 | 253 | 242 | 253 | 3230
TCM.HCV.LS | 110 | 130 | 130 | 140 | 150 | 170 | 170 | 150 | 155 | 115 | 115 | 95 | 1630
TCM.HCV.HS | 100 | 100 | 120 | 110 | 130 | 120 | 130 | 150 | 120 | 130 | 120 | 150 | 1480
TCM.HCV.MS | 7 | 5 | 8 | 7 | 10 | 15 | 15 | 20 | 10 | 8 | 7 | 8 | 120
FC Product 3rd party (Kton) | 139.1 | 139.4 | 138.6 | 138.1 | 139 | 138.3 | 138.5 | 137.7 | 145.6 | 146.2 | 138.3 | 137.7 | 1676.5
EBH.HCV.LS | 56.6 | 56.9 | 56.1 | 55.6 | 56.5 | 55.8 | 56 | 55.2 | 55.6 | 56.2 | 55.8 | 55.2 | 671.5
MBL.MCV.MS | 82.5 | 82.5 | 82.5 | 82.5 | 82.5 | 82.5 | 82.5 | 82.5 | 90 | 90 | 82.5 | 82.5 | 1005
SR FC | 19.3318 | 17.0851 | 15.5814 | 16.537 | 15.2069 | 15.2787 | 14.9841 | 15.7969 | 16.6316 | 15.7708 | 15.7231 | 14.9802 | 15.9907
TCM.HCV.LS | 110 | 130 | 130 | 140 | 150 | 170 | 170 | 150 | 155 | 115 | 115 | 95 | 1630
CV(GAR) | 6331.7794 | 6327.6426 | 6345.3425 | 6327.8237 | 6373.2296 | 6243.3002 | 6268.7387 | 6402.2298 | 6455.744 | 6429.1851 | 6453.9309 | 6360.7189 | 6355.6513
Sul < 0.7 | 0.63239 | 0.69248 | 0.652 | 0.6548 | 0.61487 | 0.6376 | 0.63464 | 0.55063 | 0.52383 | 0.52786 | 0.54698 | 0.54361 | 0.60341
ASH < 5.0 | 5.14 | 4.5591 | 4.5963 | 5.1237 | 4.8279 | 4.5406 | 5.4694 | 4.9514 | 4.2318 | 4.7988 | 4.93 | 4.9975 | 4.8411
IM | 7.9684 | 7.5074 | 7.3053 | 7.3142 | 7.2934 | 7.0845 | 7.3044 | 7.5576 | 7.1827 | 7.4775 | 7.325 | 7.6231 | 7.3863
TM | 13.5018 | 14.5066 | 14.2007 | 13.7425 | 13.7596 | 15.8885 | 14.3471 | 13.1866 | 13.1296 | 12.9827 | 12.4646 | 13.5285 | 13.8465
TCM.HCV.HS | 100 | 100 | 120 | 110 | 130 | 120 | 130 | 150 | 120 | 130 | 120 | 150 | 1480
CV(GAR) | 6528.8013 | 6523.441 | 6602.1856 | 6481.0855 | 6487.5274 | 6515.5714 | 6445.0323 | 6472.1448 | 6412.4032 | 6476.7335 | 6460.6228 | 6423.2952 | 6482.812
Sul < 2.0 | 1.8419 | 2.1454 | 1.7213 | 1.772 | 1.7758 | 2.0871 | 1.8138 | 1.8287 | 1.8482 | 1.8968 | 1.819 | 1.9905 | 1.8762
ASH < 5.0 | 6.7257 | 7.6729 | 55.9656 | 5.9371 | 5.2918 | 7.3265 | 5.9375 | 5.9832 | 6.008 | 6.0191 | 6.0931 | 5.979 | 10.2546
IM | 7.2396 | 7.118 | 6.7065 | 6.8833 | 6.7129 | 6.6877 | 6.6455 | 6.3583 | 6.7264 | 6.4663 | 6.2063 | 6.1537 | 6.6258
TM | 11.8026 | 10.6165 | 10.6667 | 11.5389 | 11.4782 | 10.0232 | 11.715 | 11.1861 | 11.926 | 11.4844 | 11.0808 | 11.4168 | 11.2522
TCM.LCV.MS.HA | 7 | 5 | 8 | 7 | 10 | 15 | 15 | 20 | 10 | 8 | 7 | 8 | 120
CV(GAR) | 3581.7631 | 3599.0009 | 4341.3047 | 3587.2263 | 3651.2002 | 5641.0449 | 5567.1958 | 5442.6121 | 5422.5222 | 5471.7948 | 5388.109 | 5438.9485 | 4963.5346
Sul < 1.2 | 1.16 | 1.15 | 1.44 | 0.51 | 0.5 | 1.45 | 1.5217 | 1.5933 | 1.6133 | 1.5833 | 1.5533 | 1.6133 | 1.3582
ASH < 5.0 | 13.6 | 13.18 | 12.69 | 14.445 | 14.2 | 6.835 | 8.9933 | 11.1517 | 11.1417 | 11.0117 | 11.1717 | 11.9817 | 11.1647
IM | 7.41 | 7.54 | 7.16 | 6.52 | 6.43 | 6.09 | 6.1267 | 6.1633 | 6.1633 | 6.1633 | 6.1633 | 6.1633 | 6.3891
TM | 13.89 | 14.11 | 14.412 | 13.208 | 13.588 | 13.532 | 13.3947 | 14.0533 | 14.0233 | 13.9833 | 14.4533 | 14.0533 | 13.8507
EBH.HCV.LS | 56.6 | 56.9 | 56.1 | 55.6 | 56.5 | 55.8 | 56 | 55.2 | 55.6 | 56.2 | 55.8 | 55.2 | 671.5
CV(GAR) | 6322 | 6322 | 6322 | 6322 | 6322 | 6322 | 6322 | 6322 | 6322 | 6322 | 6322 | 6322 | 6322
Sul < 1 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6
ASH | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7
IM | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12
TM | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14
MBL.MCV.MS | 82.5 | 82.5 | 82.5 | 82.5 | 82.5 | 82.5 | 82.5 | 82.5 | 90 | 90 | 82.5 | 82.5 | 1005
CV(GAR) | 5400 | 5400 | 5400 | 5400 | 5400 | 5400 | 5400 | 5400 | 5400 | 5400 | 5400 | 5400 | 5400
Sul < 1.2 | [12 empty] | 1 | bar: Jan to Dec
ASH | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6
IM | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15
TM | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24
BEK | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Total
OB Removal (KBcm) | 7995 | 7084 | 7619 | 7232 | 7571 | 7593 | 8097 | 8330 | 7698 | 7482 | 6860 | 7389 | 90950 | Done
TRUST | 2085 | 1784 | 1974 | 1997 | 1991 | 1968 | 2132 | 2305 | 2063 | 2062 | 1755 | 1884 | 24000
PAMA | 4250 | 3810 | 4105 | 4235 | 4480 | 4475 | 4785 | 4825 | 4495 | 4420 | 4115 | 4455 | 52450
SNS | 1660 | 1490 | 1540 | 1000 | 1100 | 1150 | 1180 | 1200 | 1140 | 1000 | 990 | 1050 | 14500
ROM Production (Kton) | 684 | 658 | 685.5 | 564 | 663 | 712 | 745 | 752 | 704 | 627.5 | 589 | 616 | 8000
TRUST | 194 | 188 | 185.5 | 156 | 196 | 212 | 245 | 252 | 234 | 192.5 | 169 | 176 | 2400
PAMA | 360 | 350 | 375 | 335 | 380 | 415 | 375 | 400 | 370 | 350 | 340 | 350 | 4400
SNS | 130 | 120 | 125 | 73 | 87 | 85 | 125 | 100 | 100 | 85 | 80 | 90 | 1200
SR ROM | 11.6886 | 10.766 | 11.1145 | 12.8227 | 11.4193 | 10.6643 | 10.8685 | 11.0771 | 10.9347 | 11.9235 | 11.6469 | 11.9951 | 11.3688
SR FC | 11.4214 | 10.12 | 10.8843 | 11.1262 | 11.6477 | 11.6815 | 11.5671 | 11.7324 | 10.9971 | 11.3364 | 10.7188 | 11.5453 | 11.2284
FC Product (KTons) | 700 | 700 | 700 | 650 | 650 | 650 | 700 | 710 | 700 | 660 | 640 | 640 | 8100
BEK.HCV.LS | 400 | 480 | 480 | 465 | 465 | 460 | 500 | 490 | 480 | 460 | 440 | 440 | 5560
CV(GAR) | 6030.4358 | 5774.2277 | 5860.9708 | 5868.1864 | 5954.6027 | 5916.1255 | 5984.187 | 5944.3266 | 5921.0085 | 5916.7362 | 5898.291 | 5928.9325 | 5915.2264
TS | 0.53158 | 0.52889 | 0.5114 | 0.47877 | 0.51889 | 0.54684 | 0.6156 | 0.65164 | 0.57083 | 0.61028 | 0.68843 | 0.67517 | 0.5772
Ash | 4.5798 | 4.3819 | 4.7059 | 4.7159 | 4.47 | 4.6727 | 5.1675 | 5.2807 | 5.3764 | 5.2082 | 4.9555 | 5.0376 | 4.8848
IM | 11.5325 | 12.1617 | 11.7688 | 10.9822 | 11.9963 | 11.3734 | 10.8514 | 11.2599 | 11.1283 | 11.3129 | 11.8103 | 11.5197 | 11.4694
TM | 16.0731 | 18.3447 | 16.1139 | 15.2818 | 15.685 | 15.0345 | 13.9867 | 14.31 | 14.2913 | 14.4636 | 14.865 | 14.5485 | 15.2419
BEK.HCV.HS | 300 | 220 | 220 | 185 | 185 | 190 | 200 | 220 | 220 | 200 | 200 | 200 | 2540
CV(GAR) | 5978.3055 | 5788.4874 | 5780.4749 | 5757.1239 | 5689.0306 | 5723.4269 | 5710.0663 | 5767.3036 | 5816.7184 | 5783.944 | 5714.3882 | 5899.7671 | 5792.8232
TS | 1.787 | 1.8051 | 1.7535 | 1.753 | 1.7123 | 1.7854 | 1.8239 | 1.742 | 1.7014 | 1.7606 | 1.7678 | 1.7233 | 1.7606
Ash | 4.7301 | 5.5271 | 5.5458 | 5.7433 | 6.1338 | 6.4532 | 6.4437 | 6.2121 | 5.7608 | 5.8895 | 6.1089 | 5.112 | 5.7572
IM | 11.0894 | 10.939 | 11.1033 | 10.7531 | 10.9318 | 10.5429 | 10.9263 | 10.5327 | 10.5196 | 10.609 | 10.4098 | 10.3006 | 10.7369
TM | 14.7767 | 14.7885 | 14.9686 | 14.6226 | 15.0392 | 14.4524 | 14.7662 | 14.3018 | 14.2251 | 14.4043 | 14.4451 | 13.7474 | 14.5518
JBG | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Total
OB Removal (KBcm) | 103.007 | 93.07 | 98.059 | 280.6245 | 579.3785 | 448.889 | 536.383 | 575.345 | 590.094 | 632.103 | 557.72 | 543.935 | 5038.608 | Done
Contractor Pit UCE ext | 103.007 | 93.07 | 98.059 | 280.6245 | 579.3785 | 448.889 | 536.383 | 575.345 | 590.094 | 632.103 | 557.72 | 543.935 | 5038.608
ROM Production (Kton) | 0 | 0 | 0 | 0 | 20 | 37 | 51 | 60 | 70 | 75 | 68 | 67 | 448
Contractor Pit UCE ext | 0 | 0 | 0 | 0 | 20 | 37 | 51 | 60 | 70 | 75 | 68 | 67 | 448
SR ROM | 0 | 0 | 0 | 0 | 28.9689 | 12.1321 | 10.5173 | 9.5891 | 8.4299 | 8.428 | 8.2018 | 8.1184 | 11.2469
SR FC | 0 | 0 | 0 | 0 | 32.1877 | 12.8254 | 10.7277 | 9.9197 | 8.6779 | 8.7792 | 8.4503 | 8.2414 | 11.6365
JBG Coal Loading | 14.6 | 14.6 | 7.3 | 7.3 | 21.9 | 36.5 | 43.8 | 58.4 | 58.4 | 58.4 | 58.4 | 51.1 | 430.7
JBG FC Product (Kton) / JBG | 0 | 0 | 0 | 0 | 18 | 35 | 50 | 58 | 68 | 72 | 66 | 66 | 433
CV(GAR) | 0 | 0 | 0 | 0 | 4442.3525 | 4414.0197 | 4416.3842 | 4432.5862 | 4408.926 | 4423.0872 | 4453.786 | 4407.9045 | 4423.7946
TS | 0 | 0 | 0 | 0 | 0.38874 | 0.35403 | 0.38864 | 0.37486 | 0.36433 | 0.35476 | 0.35693 | 0.38386 | 0.36899
Ash | 0 | 0 | 0 | 0 | 4.3469 | 4.2775 | 4.5772 | 4.4107 | 4.3138 | 4.438 | 4.3733 | 4.6218 | 4.4323
IM | 0 | 0 | 0 | 0 | 17.434 | 17.2038 | 17.034 | 16.8716 | 16.9773 | 16.7251 | 16.9357 | 16.7621 | 16.9259
TM | 0 | 0 | 0 | 0 | 30.1867 | 30.2656 | 30.3349 | 30.2198 | 30.2331 | 30.2451 | 30.1783 | 30.2279 | 30.2366
GPK | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Total
OB Removal (KBcm) | 630 | 580 | 630 | 610 | 700 | 675 | 745 | 790 | 785 | 880 | 705 | 770 | 8500 | Done
ARKA | 630 | 580 | 630 | 610 | 700 | 675 | 745 | 790 | 785 | 880 | 705 | 770 | 8500
ROM Production (Kton) | 184 | 166 | 182 | 175 | 180 | 175 | 160 | 160 | 160 | 196 | 175 | 187 | 2100
ARKA | 119 | 108 | 118 | 114 | 131 | 127 | 125 | 124 | 126 | 139 | 114 | 122 | 1467
SLS | 65 | 58 | 64 | 61 | 49 | 48 | 35 | 36 | 34 | 57 | 61 | 65 | 633
SR ROM | 3.4239 | 3.494 | 3.4615 | 3.4857 | 3.8889 | 3.8571 | 4.6562 | 4.9375 | 4.9062 | 4.4898 | 4.0286 | 4.1176 | 4.0476
SR FC | 3.15 | 3.2222 | 3.3158 | 3.4857 | 3.8889 | 3.8571 | 8.2778 | 15.8 | 8.7222 | 4.1905 | 2.7115 | 3.08 | 4.1463
FC Production (Ktons) | 200 | 180 | 190 | 175 | 180 | 175 | 90 | 50 | 90 | 210 | 260 | 250 | 2050
CV(GAR) | 3597.7504 | 3594.5296 | 3663.6762 | 3731.5323 | 3747.0877 | 3753.0309 | 3709.9842 | 3710.8591 | 3754.9789 | 3802.469 | 3810.8052 | 3790.9104 | 3727.504
TS | 0.11569 | 0.11701 | 0.15581 | 0.15133 | 0.15302 | 0.14876 | 0.16964 | 0.1691 | 0.15833 | 0.16553 | 0.17248 | 0.16287 | 0.15227
Ash | 10.1457 | 10.2139 | 9.4792 | 8.2664 | 7.972 | 8.1087 | 9.7175 | 9.7409 | 8.5788 | 6.4456 | 5.4512 | 5.9086 | 7.9761
IM | 27.2738 | 27.292 | 26.9771 | 25.1243 | 25.0639 | 24.2542 | 31.6027 | 31.4781 | 27.5216 | 26.4417 | 28.9143 | 29.0422 | 27.2546
TM | 37.9185 | 37.923 | 38.043 | 37.9509 | 37.979 | 38.0738 | 37.7175 | 37.7338 | 37.8637 | 38.4165 | 39.0685 | 39.1676 | 38.2852
TIS | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Total
OB Removal (KBcm) | 767.6336 | 734.7931 | 815.1462 | 831.0273 | 859.4709 | 916.3581 | 1023.2017 | 1020.3858 | 1007.9939 | 961.3227 | 867.198 | 903.6556 | 10708.1867 | Done
Contractor | 767.6336 | 734.7931 | 815.1462 | 831.0273 | 859.4709 | 916.3581 | 1023.2017 | 1020.3858 | 1007.9939 | 961.3227 | 867.198 | 903.6556 | 10708.1867
ROM Production (Kton) | 40.6021 | 37.5931 | 41.6296 | 45.5535 | 50.2535 | 55.2541 | 61.4542 | 61.231 | 61.1144 | 55.8895 | 46.816 | 48.6088 | 605.9999
Contractor | 40.6021 | 37.5931 | 41.6296 | 45.5535 | 50.2535 | 55.2541 | 61.4542 | 61.231 | 61.1144 | 55.8895 | 46.816 | 48.6088 | 605.9999
SR ROM | 18.9063 | 19.5459 | 19.5809 | 18.2429 | 17.1027 | 16.5844 | 16.6498 | 16.6645 | 16.4936 | 17.2004 | 18.5235 | 18.5904 | 17.6703
SR FC | 23.9885 | 26.2426 | 20.3787 | 20.7757 | 17.1894 | 16.6611 | 17.0534 | 17.0064 | 17.9999 | 16.022 | 15.7672 | 16.4301 | 18.1188
FC Production (Ktons) | 32 | 28 | 40 | 40 | 50 | 55 | 60 | 60 | 56 | 60 | 55 | 55 | 591
CV(GAR) | 6898.8055 | 6898.8055 | 6898.8055 | 7061.2455 | 7061.2455 | 7061.2455 | 6892.9578 | 6892.9578 | 6930.9674 | 6803.0068 | 6804.9228 | 6822.1666 | 6914.9248
TS | 1.2251 | 1.1251 | 1.0112 | 0.95955 | 0.95955 | 0.91395 | 0.84903 | 0.85955 | 0.8749 | 1.0751 | 1.0129 | 1.0815 | 0.97968
Ash | 3.7895 | 3.7895 | 3.7895 | 3.6003 | 3.6003 | 3.6003 | 3.8711 | 3.8711 | 3.8711 | 3.7895 | 3.7895 | 3.7895 | 3.7674
TM | 8.7195 | 8.7195 | 8.7195 | 7.3393 | 7.3393 | 7.3393 | 9.7585 | 9.7585 | 9.7585 | 8.7195 | 8.7195 | 8.7195 | 8.6903
IM | 4.7164 | 4.7164 | 4.7164 | 4.4047 | 4.4047 | 4.4047 | 5.0329 | 5.0329 | 5.0329 | 4.7164 | 4.7164 | 4.7164 | 4.7342
NPR | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Total
OB Removal (KBcm) | 0 | 0 | 129 | 535 | 542 | 543 | 586 | 594 | 578 | 752 | 682 | 742.5 | 5683.5 | Done
Contractor | 0 | 0 | 129 | 535 | 542 | 543 | 586 | 594 | 578 | 752 | 682 | 742.5 | 5683.5
ROM Production (Kton) | 0 | 0 | 0 | 0 | 25 | 55 | 60 | 60 | 55 | 65 | 65 | 65 | 450
Contractor | 0 | 0 | 0 | 0 | 25 | 55 | 60 | 60 | 55 | 65 | 65 | 65 | 450
SR ROM | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 21.68 | 9.8727 | 9.7667 | 9.9 | 10.5091 | 11.5692 | 10.4923 | 11.4231 | 12.63
SR FC | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 31.8824 | 14.6757 | 14.65 | 14.85 | 15.6216 | 17.4884 | 15.8605 | 17.2674 | 18.945
FC Production (Ktons) | 0 | 0 | 0 | 0 | 17 | 37 | 40 | 40 | 37 | 43 | 43 | 43 | 300
CV(GAD) | 0 | 0 | 0 | 0 | 6479.8736 | 6587.4532 | 6598.4997 | 6640.8571 | 6546.9132 | 6622.5542 | 6577.0752 | 6514.6914 | 5016.4003
TS | 0 | 0 | 0 | 0 | 1.1963 | 1.2298 | 1.1899 | 1.1598 | 1.0431 | 1.0999 | 1.0172 | 0.99869 | 0.85231
Ash | 0 | 0 | 0 | 0 | 6.1898 | 6.1677 | 6.5217 | 6.2198 | 5.498 | 6.2002 | 5.4953 | 5.9413 | 4.606
IM |  |  |  | 0 | 8.626 | 7.4 | 6.7387 | 6.6266 | 8.5113 | 6.8655 | 8.0495 | 8.45 | 5.8143
TM | 0 | 0 | 0 | 0 | 14.7805 | 14.414 | 14.3683 | 14.3998 | 15.0003 | 14.3847 | 15.0759 | 15.0952 | 11.202

## Outlook 4+8
ITM outlook 2025 (4+8)
| Act. | Act. | Act. | Act. | Out. | Out. | Out. | Out. | Out. | Out. | Out. | Out. | Out.
IMM | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Total | Budget 2025
OB Removal (KBcm) | 6763.0376 | 7421.6153 | 6667.0223 | 6380.9103 | 8427.9132 | 7640.614 | 8789.2468 | 8512.679 | 8487.7924 | 8759.4618 | 8814.2806 | 8533.4634 | 95198.0366 | 94714.4782 | 100.5%
PAMA (WB) | 2244.6941 | 2827.069 | 2295.7418 | 1946.6079 | 2953.7157 | 2717.2507 | 3223.0037 | 3121.8471 | 2945.2593 | 3171.8912 | 3162.2305 | 3070.0459 | 33679.357 | 33532.659
PAMA (EB) | 4518.3435 | 4594.5463 | 4371.2805 | 4434.3024 | 5474.1975 | 4923.3633 | 5566.2431 | 5390.8319 | 5542.5331 | 5587.5705 | 5652.0501 | 5463.4174 | 61518.6796 | 61181.8192
ROM Production (Kton) | 542.8336 | 554.1195 | 482.7867 | 444.512 | 570.0206 | 582.5 | 610 | 660 | 660 | 660 | 660 | 620.7276 | 7047.5 | 6950 | 101.4%
PAMA (WB) | 158.4259 | 192.5857 | 141.1236 | 88.5606 | 165.152 | 140 | 165 | 165 | 130 | 130 | 130 | 126.6522 | 1732.5 | 1862.5
PAMA (EB) | 384.4077 | 361.5338 | 341.6631 | 355.9514 | 404.8685 | 442.5 | 445 | 495 | 530 | 530 | 530 | 494.0754 | 5315 | 5087.5
Fine Coal (WB) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SR ROM Total | 12.4588 | 13.3935 | 13.8095 | 14.3549 | 14.7853 | 13.1169 | 14.4086 | 12.898 | 12.8603 | 13.2719 | 13.355 | 13.7475 | 13.5081 | 13.628
FC Product (Kton) | 612.6829 | 584.9149 | 501.0107 | 479.3049 | 584.25 | 584.25 | 625.75 | 672.75 | 672.75 | 642 | 642 | 533.3364 | 7135 | 7100
PAMA (WB) | 203.8423 | 213.1594 | 151.0762 | 100.5344 | 165 | 148.5 | 175 | 165 | 130 | 115 | 115 | 47.8877 | 1730 | 1862.5
PAMA (EB) | 408.8406 | 371.7556 | 349.9345 | 378.5787 | 415 | 431.5 | 446.5 | 495 | 530 | 514.25 | 514.25 | 472.6988 | 5328.3081 | 5110
Fine Coal | 0 | 0 | 0 | 0.19187 | 4.25 | 4.25 | 4.25 | 12.75 | 12.75 | 12.75 | 12.75 | 12.75 | 76.6919 | 127.5
SR FC Total | 11.0384 | 12.6884 | 13.3071 | 13.3128 | 14.4252 | 13.0776 | 14.0459 | 12.6536 | 12.6166 | 13.644 | 13.7294 | 16.0002 | 13.3424 | 13.3401
IMM-WB.HCV.LS | 146.1825 | 147.4608 | 104.9995 | 70.1282 | 130 | 71.0619 | 103.4687 | 88.9543 | 60.5097 | 66.0955 | 66.4529 | 47.8877 | 1103.2017 | 1228.8032
CV(GAR) | 6193.9879 | 6105.8162 | 6211.2744 | 6152.0829 | 6008.2957 | 6195.4139 | 6259.4326 | 6230.9729 | 6374.9065 | 6400.56 | 6233.1866 | 6244.1353 | 6195.3516 | 6169.7769
TS | 0.61678 | 0.68122 | 0.59906 | 0.64019 | 0.88607 | 0.79807 | 0.80275 | 0.80158 | 0.79961 | 0.84667 | 0.86801 | 0.75912 | 0.74606 | 0.8108
Ash | 8.4183 | 8.3936 | 8.4815 | 7.987 | 8.9675 | 8.2745 | 8.4062 | 8.2506 | 7.9679 | 8.2594 | 8.309 | 7.7957 | 8.3666 | 8.3746
Moist | 8.6372 | 9.4242 | 8.7142 | 9.2339 | 8.8975 | 8.467 | 8.164 | 7.8479 | 7.1238 | 7.1464 | 7.0761 | 7.6334 | 8.3894 | 8.0403
TM | 11.4895 | 12.3252 | 11.1339 | 12.344 | 13.7912 | 13.4923 | 13.1894 | 12.8732 | 12.1492 | 12.1718 | 12.1015 | 12.6588 | 12.4576 | 13.0657
IMM-WB.HCV.HS | 57.6598 | 65.6986 | 46.0767 | 30.4062 | 35 | 77.4381 | 71.5313 | 76.0457 | 69.4903 | 48.9045 | 48.5471 | 0 | 626.7983 | 633.6968
CV(GAR) | 5947.3932 | 5939.4465 | 6026.7648 | 5928.2234 | 5964.604 | 5905.9183 | 5962.1308 | 5928.4411 | 6005.5198 | 5894.1649 | 5910.574 | 0 | 5946.124 | 5965.7827
TS | 1.9789 | 2.2887 | 2.171 | 1.9301 | 2.5412 | 2.7715 | 2.7609 | 2.6979 | 2.6091 | 2.6713 | 2.6349 | 0 | 2.5036 | 2.579
Ash | 12.3989 | 11.629 | 11.3803 | 12.1525 | 13.2349 | 14.5102 | 13.5097 | 14.3705 | 13.3246 | 14.7718 | 14.8917 | 0 | 13.3857 | 13.9606
Moist | 7.8249 | 7.5595 | 6.9977 | 7.2613 | 6.2777 | 7.0495 | 6.8342 | 6.8425 | 6.831 | 7.4057 | 7.4333 | 0 | 7.1213 | 6.744
TM | 10.9111 | 11.827 | 11.262 | 11.6423 | 10.7856 | 12.0748 | 11.8596 | 11.8679 | 11.8564 | 12.4311 | 12.4587 | 0 | 11.7727 | 11.7694
IMM-EB.MCV.LS | 4.1512 | 4.8753 | 8.9721 | 7.4826 | 10 | 1.9295 | 0 | 0 | 0 | 0 | 0 | 0 | 37.4106 | 13.6399
CV(GAR) | 5768.2424 | 5970.6107 | 5842.9196 | 6060.3315 | 5833.2311 | 5811.3441 | 0 | 0 | 0 | 0 | 0 | 0 | 5890.5407 | 5822.4314
TS | 0.90471 | 0.97326 | 0.8997 | 0.91618 | 0.95115 | 0.8603 | 0 | 0 | 0 | 0 | 0 | 0 | 0.92486 | 0.90072
Ash | 8.498 | 6.4547 | 6.9734 | 5.5177 | 8.82 | 8.7157 | 0 | 0 | 0 | 0 | 0 | 0 | 7.3673 | 8.5978
Moist | 10.8615 | 11.3343 | 10.9152 | 11.1195 | 12.2149 | 11.4231 | 0 | 0 | 0 | 0 | 0 | 0 | 11.3783 | 11.3544
TM | 14.3085 | 13.9608 | 14.8854 | 13.9345 | 16.7849 | 16.4231 | 0 | 0 | 0 | 0 | 0 | 0 | 15.0977 | 16.3544
IMM-EB.MCV.MS | 16.3857 | 4.2319 | 27.4815 | 41.3212 | 25 | 7.8203 | 35.3326 | 27.6624 | 80.2627 | 89.7771 | 74.1699 | 71.809 | 501.2543 | 422.7155
CV(GAR) | 6095.6967 | 5702.0802 | 5950.0061 | 5974.4204 | 5852.0766 | 5991.2837 | 6020.8684 | 6013.3215 | 6007.8378 | 5999.9701 | 6040.3584 | 6028.6326 | 6001.7792 | 6013.6725
TS | 1.5214 | 1.2568 | 1.4098 | 1.484 | 1.5988 | 1.5415 | 1.5694 | 1.5854 | 1.5745 | 1.5672 | 1.5888 | 1.5739 | 1.5553 | 1.5595
Ash | 5.1476 | 7.9573 | 6.2815 | 5.8971 | 6.9774 | 5.2092 | 5.1963 | 5.2393 | 5.4473 | 5.4664 | 5.2139 | 5.2948 | 5.532 | 5.3287
Moist | 11.5254 | 13.0173 | 11.4442 | 12.1489 | 10.9109 | 10.5748 | 10.5074 | 10.4847 | 10.3495 | 10.2463 | 10.1288 | 9.9378 | 10.5588 | 10.2792
TM | 13.6454 | 15.0827 | 14.2922 | 14.1446 | 15.8146 | 15.5748 | 15.5074 | 15.4847 | 15.3495 | 15.2463 | 15.1288 | 14.9378 | 15.0694 | 15.2792
IMM-EB.MCV.HS | 388.3038 | 362.6484 | 313.481 | 329.7748 | 380 | 421.7502 | 411.1674 | 467.3376 | 449.7373 | 424.4729 | 440.0801 | 400.8898 | 4789.6432 | 4673.6446
CV(GAR) | 5993.4453 | 6000.7559 | 5998.3259 | 5980.6624 | 5838.9038 | 5913.6481 | 5902.4244 | 5889.7173 | 5919.1858 | 5911.1331 | 5937.8865 | 5904.955 | 5929.4369 | 5914.4155
TS | 2.2774 | 2.2808 | 2.3122 | 2.3366 | 2.3188 | 2.3515 | 2.437 | 2.4882 | 2.4458 | 2.4624 | 2.3389 | 2.454 | 2.3807 | 2.4107
Ash | 5.9664 | 5.886 | 6.2337 | 5.9769 | 6.4546 | 5.7142 | 5.706 | 5.9168 | 5.6774 | 5.7574 | 5.6849 | 5.7057 | 5.8745 | 5.72
Moist | 11.4322 | 11.4905 | 11.1144 | 11.4873 | 10.891 | 10.7495 | 10.6283 | 10.4952 | 10.4502 | 10.4732 | 10.4745 | 10.5754 | 10.8192 | 10.5582
TM | 13.742 | 13.586 | 13.4706 | 13.7887 | 15.8069 | 15.7495 | 15.6283 | 15.4952 | 15.4502 | 15.4732 | 15.4745 | 15.5754 | 15.0157 | 15.5582
Fine Coal | 0 | 0 | 0 | 0.19187 | 4.25 | 4.25 | 4.25 | 12.75 | 12.75 | 12.75 | 12.75 | 12.75 | 76.6919 | 127.5
CV(GAR) | 0 | 0 | 0 | 3966.2693 | 3146.0674 | 3146.0674 | 3146.0674 | 3146.0674 | 3146.0674 | 3146.0674 | 3146.0674 | 3146.0674 | 3148.1194 | 3146.0674
TS | 0 | 0 | 0 | 0.95 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 1.9974 | 2
Ash | 0 | 0 | 0 | 24.4 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 39.961 | 40
Moist | 0 | 0 | 0 | 12 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11.0025 | 11
TM | 0 | 0 | 0 | 22.9 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20.0073 | 20
TCM | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Total | Budget 2025
OB Removal (KBcm) | 3736.1074 | 3365.8927 | 3574.4767 | 2859.5105 | 3690 | 3824 | 4516.933 | 4711.933 | 4533.5683 | 4111.933 | 4046.1928 | 3929.4527 | 46900 | 51650 | 90.8%
PAMA | 1350.2909 | 1037.3669 | 1287.9434 | 1083.7445 | 1880 | 2078.03 | 2660.963 | 2755.963 | 2745.963 | 2555.963 | 2520.2228 | 2443.5497 | 24400 | 24400
MAP | 1111.151 | 916.3988 | 928.1686 | 747.5562 | 910 | 900 | 1000 | 1050 | 950 | 850 | 830 | 806.7254 | 11000 | 11000
PJPN | 1274.6654 | 1412.127 | 1358.3647 | 1028.2098 | 900 | 845.97 | 855.97 | 905.97 | 837.6054 | 705.97 | 695.97 | 679.1776 | 11500 | 16250
ROM Production (Kton) | 197.2844 | 200.7536 | 248.6888 | 198.2023 | 250 | 294.8496 | 338.8496 | 361.8496 | 367.9619 | 332.8496 | 336.8496 | 336.8609 | 3465 | 3300.387 | 105%
PAMA | 128.1928 | 118.2278 | 164.3541 | 128.7862 | 155 | 192.4591 | 208.4591 | 213.4591 | 220.4591 | 198.4591 | 202.4591 | 199.6844 | 2130 | 2130
MAP | 31.1921 | 36.3972 | 40.6248 | 29.6651 | 45 | 51.905 | 51.905 | 54.905 | 54.905 | 49.905 | 49.905 | 53.691 | 550 | 550
PJPN | 37.8996 | 46.1285 | 39.3617 | 35.6014 | 50 | 50.4855 | 78.4855 | 93.4855 | 92.5978 | 84.4855 | 84.4855 | 83.4855 | 776.5021 | 620.387
SNS | 0 | 0 | 4.3483 | 4.1496 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.4979
SR ROM with void | 18.9377 | 16.7663 | 14.3733 | 14.4272 | 14.76 | 12.9693 | 13.3302 | 13.0218 | 12.3208 | 12.3537 | 12.0119 | 11.6649 | 13.5354 | 15.6497
FC Product CP (Kton) | 236.9432 | 220.6496 | 280.3218 | 200.3136 | 250 | 260 | 330 | 335 | 335 | 325 | 320 | 307.1702 | 3400.3985 | 3230
TCM.HCV.LS | 162.6798 | 131.4776 | 143.7703 | 110.8186 | 110 | 120 | 180 | 180 | 185 | 180 | 175 | 171.6522 | 1850.3985 | 1630
TCM.HCV.HS | 74.2634 | 89.172 | 136.5515 | 89.495 | 140 | 140 | 150 | 155 | 150 | 145 | 145 | 135.5181 | 1550 | 1480
TCM.HCV.MS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 120
FC Product 3rd party (Kton) | 57.1257 | 53.4973 | 58.8103 | 75.2631 | 125.3982 | 94.7562 | 83.1464 | 58.1837 | 37.1395 | 68.7549 | 52.9974 | 55 | 820.0726 | 1676.5
EBH.HCV.LS | 7.1098 | 40.5275 | 51.9524 | 50.1264 | 109.9789 | 87.8438 | 83.1464 | 58.1837 | 37.1395 | 60.3145 | 52.9974 | 45 | 684.3203 | 671.5
MBL.MCV.MS | 50.0159 | 12.9697 | 6.8579 | 25.1368 | 15.4192 | 6.9123 | 0 | 0 | 0 | 8.4404 | 0 | 10 | 135.7523 | 1005
SR FC | 15.7679 | 15.2545 | 12.7513 | 14.2752 | 14.76 | 14.7077 | 13.6877 | 14.0655 | 13.533 | 12.6521 | 12.6444 | 12.7924 | 13.7925 | 15.9907
TCM.HCV.LS | 162.6798 | 131.4776 | 143.7703 | 110.8186 | 110 | 120 | 180 | 180 | 185 | 180 | 175 | 171.6522 | 1850.3985 | 1630
CV(GAR) | 6732.4288 | 6572.6205 | 6596.2445 | 6621.4349 | 6585.4026 | 6524.7531 | 6513.6397 | 6527.2252 | 6521.3878 | 6410.0402 | 6420.6604 | 6410.3431 | 6528.5689 | 6355.6513
Sul < 0.7 | 0.62137 | 0.63583 | 0.77706 | 0.69371 | 0.73323 | 0.73548 | 0.76765 | 0.74717 | 0.73759 | 0.73053 | 0.6509 | 0.73149 | 0.71459 | 0.60341
ASH < 5.0 | 3.4667 | 4.5743 | 4.3675 | 4.7704 | 4.9854 | 4.85 | 5.0106 | 4.7204 | 4.8351 | 4.7284 | 4.783 | 4.8392 | 4.6569 | 4.8411
IM | 6.8418 | 7.5669 | 6.8218 | 6.8812 | 7.4455 | 7.5769 | 7.885 | 7.8674 | 8.0963 | 8.1519 | 7.9598 | 7.89 | 7.6348 | 7.3863
TM | 11.1733 | 12.0917 | 12.4658 | 11.343 | 12.2446 | 12.3221 | 11.4381 | 11.5304 | 11.7779 | 12.8808 | 12.696 | 12.6651 | 12.0568 | 13.8465
TCM.HCV.HS | 74.2634 | 89.172 | 136.5515 | 89.495 | 140 | 140 | 150 | 155 | 150 | 145 | 145 | 135.5181 | 1550 | 1480
CV(GAR) | 6697.6812 | 6682.5379 | 6375.2052 | 6514.9911 | 6527.6345 | 6544.5483 | 6519.0094 | 6529.4146 | 6531.4619 | 6451.36 | 6501.0864 | 6440.0574 | 6514.5003 | 6482.812
Sul < 2.0 | 1.6302 | 1.4797 | 1.6016 | 1.6141 | 1.6886 | 1.7173 | 1.7417 | 1.7264 | 1.7656 | 1.7641 | 1.7521 | 1.7407 | 1.6983 | 1.8762
ASH < 5.0 | 2.9843 | 3.6683 | 5.3381 | 5.334 | 5.6882 | 5.7928 | 5.8244 | 5.5827 | 6.0944 | 6.1 | 5.8409 | 5.9154 | 5.5152 | 10.2546
IM | 6.3755 | 6.3149 | 6.5134 | 6.5208 | 6.6367 | 6.5179 | 6.4661 | 6.6478 | 6.3886 | 6.1949 | 5.7972 | 5.7873 | 6.3439 | 6.6258
TM | 11.045 | 10.871 | 11.7658 | 12.1103 | 11.2167 | 10.9549 | 11.3215 | 11.3206 | 10.6484 | 11.7453 | 11.4974 | 11.7896 | 11.3563 | 11.2522
EBH.HCV.LS | 7.1098 | 40.5275 | 51.9524 | 50.1264 | 109.9789 | 87.8438 | 83.1464 | 58.1837 | 37.1395 | 60.3145 | 52.9974 | 45 | 684.3203 | 671.5
CV(GAR) | 6322 | 6322 | 6322 | 6322 | 6322 | 6322 | 6322 | 6322 | 6322 | 6322 | 6322 | 6322 | 6322 | 6322
Sul < 1.2 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6
ASH < 5.0 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7
IM | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12
TM | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14
MBL.MCV.MS | 50.0159 | 12.9697 | 6.8579 | 25.1368 | 15.4192 | 6.9123 | 0 | 0 | 0 | 8.4404 | 0 | 10 | 135.7523 | 1005
CV(GAR) | 5400 | 5400 | 5400 | 5400 | 5400 | 5400 | 5400 | 5400 | 5400 | 5400 | 5400 | 5400 | 5400 | 5400
Sul < 1.2 | [12 empty] | 1 | 1 | bar: Jan to Dec
ASH < 5.0 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6
IM | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15
TM | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24
BEK | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Total | Budget 2025
OB Removal (KBcm) | 7740.8131 | 6674.4387 | 7334.0009 | 6431.8589 | 8585 | 9076.6297 | 8165.9727 | 8225 | 8295 | 8114 | 7610 | 7247.2861 | 93500.0002 | 90950 | 102.8%
TRUST | 1657.8774 | 1407.4207 | 1552.9195 | 1926.5002 | 2455 | 2627.0273 | 1945.9727 | 2005 | 2070 | 2240 | 2100 | 2012.2824 | 24000.0002 | 24000
PAMA | 4075.4608 | 3313.976 | 3758.0614 | 3301.263 | 4450 | 4929.6024 | 5220 | 5320 | 5270 | 5029 | 5160 | 5172.6364 | 55000 | 52450
SNS | 2007.4749 | 1953.042 | 2023.02 | 1204.0958 | 1680 | 1520 | 1000 | 900 | 955 | 845 | 350 | 62.3673 | 14500 | 14500
ROM Production (Kton) | 737.0865 | 743.2998 | 904.2769 | 705.0239 | 675 | 705 | 670 | 780 | 600 | 580 | 565 | 585.313 | 8250 | 8000 | 103.1%
TRUST | 144.008 | 216.6716 | 291.6349 | 238.8466 | 185 | 190 | 205 | 205 | 195 | 190 | 190 | 148.8389 | 2400 | 2400
PAMA | 410.2388 | 366.3467 | 418.9281 | 215.2214 | 310 | 400 | 430 | 540 | 370 | 360 | 355 | 424.2649 | 4600 | 4400
SNS | 182.8397 | 160.2815 | 193.7138 | 250.9558 | 180 | 115 | 35 | 35 | 35 | 30 | 20 | 12.2092 | 1250 | 1200
SR ROM | 10.5019 | 8.9795 | 8.1103 | 9.1229 | 12.7185 | 12.8747 | 12.188 | 10.5449 | 13.825 | 13.9897 | 13.469 | 12.3819 | 11.3333 | 11.3688
SR FC | 10.3695 | 9.7157 | 10.3458 | 9.5166 | 11.7603 | 12.9666 | 11.6657 | 11.75 | 11.85 | 11.5914 | 10.8714 | 10.9512 | 11.1177 | 11.2284
FC Product (KTons) | 746.5015 | 686.976 | 708.8848 | 675.859 | 730 | 700 | 700 | 700 | 700 | 700 | 700 | 661.7787 | 8410 | 8100
BEK.HCV.LS | 625.8496 | 567.9555 | 547.067 | 503.7176 | 420 | 470 | 500 | 500 | 500 | 500 | 500 | 465.4102 | 6100 | 5560
CV(GAR) | 6097.4967 | 6119.1856 | 6220.8649 | 6062.7439 | 6113.846 | 6109.2478 | 6218.3684 | 6271.0916 | 6289.6838 | 6259.7799 | 6207.0516 | 6251.1722 | 6183.6379 | 5915.2264
TS | 0.54477 | 0.56824 | 0.47738 | 0.62875 | 0.55916 | 0.5477 | 0.54806 | 0.5538 | 0.54717 | 0.54796 | 0.56235 | 0.56137 | 0.55324 | 0.5772
Ash | 4.6247 | 4.6318 | 3.9165 | 4.3087 | 3.6523 | 4.1371 | 3.9835 | 3.9858 | 4.0173 | 3.9348 | 3.8864 | 3.8865 | 4.1031 | 4.8848
IM | 10.4598 | 10.574 | 10.5752 | 11.1112 | 11.0531 | 10.7037 | 10.8663 | 10.5674 | 10.4622 | 10.5045 | 10.9366 | 10.7539 | 10.7017 | 11.4694
TM | 16.139 | 16.0366 | 15.5041 | 16.8779 | 16.3488 | 16.536 | 14.8285 | 14.3716 | 14.2271 | 14.715 | 15.0441 | 14.632 | 15.4481 | 15.2419
BEK.HCV.HS | 120.6519 | 119.0205 | 161.8178 | 172.1413 | 310 | 230 | 200 | 200 | 200 | 200 | 200 | 196.3685 | 2310 | 2540
CV(GAR) | 6099.469 | 6066.5599 | 6046.9118 | 6012.6397 | 6168.2756 | 6167.3973 | 6186.8347 | 6185.692 | 6188.2345 | 6188.3072 | 6201.3227 | 6210.5538 | 6152.2863 | 5792.8232
TS | 1.9961 | 1.995 | 1.9374 | 1.9318 | 1.9381 | 1.8846 | 1.8745 | 1.8704 | 1.8628 | 1.8721 | 1.8856 | 1.8888 | 1.9059 | 1.7606
Ash | 4.8307 | 4.7802 | 6.309 | 6.1221 | 5.054 | 4.9337 | 4.5325 | 4.5642 | 4.5446 | 4.5876 | 4.6028 | 4.5658 | 4.9312 | 5.7572
IM | 10.559 | 11.003 | 10.0774 | 10.2964 | 10.0708 | 10.1287 | 10.6099 | 10.6057 | 10.6246 | 10.6147 | 10.5202 | 10.5331 | 10.4336 | 10.7369
TM | 15.5418 | 16.161 | 15.2644 | 15.4267 | 13.9557 | 14.3676 | 14.518 | 14.482 | 14.4505 | 14.3859 | 14.2407 | 14.1873 | 14.6132 | 14.5518
JBG | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Total | Budget 2025
OB Removal (KBcm) | 0 | 0 | 0 | 0 | 0 | 160 | 183 | 355 | 366 | 394 | 348 | 313 | 2119 | 5038.608 | 42.06%
Pit UCE-Extend | 0 | 0 | 0 | 0 | 0 | 160 | 183 | 355 | 366 | 394 | 348 | 313 | 2119 | 5038.608
ROM Production (Kton) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 24 | 59 | 57 | 58 | 200 | 448 | 44.64%
Pit UCE-Extend | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 24 | 59 | 57 | 58 | 200 | 448
SR ROM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 177.5 | 15.25 | 6.678 | 6.1053 | 5.3966 | 10.595 | 11.2469
SR FC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 177.5 | 16.6364 | 7.0357 | 6.3273 | 5.2167 | 10.8667 | 11.6365
JBG Coal Loading | 0 | 0 | 0 | 0 | 0 | 18.1 | 18.1 | 7.5 | 29.8 | 59.4 | 30.5 | 59.1 | 222.5 | 430.7
JBG FC Product (Kton) / JBG | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 22 | 56 | 55 | 60 | 195 | 433
CV(GAR) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4486.6141 | 4432.8755 | 4380.2803 | 4389.5884 | 4258.1278 | 4352.3447 | 4423.7946
TS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.39501 | 0.4259 | 0.39214 | 0.38833 | 0.32217 | 0.37337 | 0.36899
Ash | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5.0567 | 4.8165 | 5.5125 | 5.082 | 5.3704 | 5.2642 | 4.4323
IM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18.0309 | 16.9178 | 16.5652 | 16.4508 | 15.5682 | 16.281 | 16.9259
TM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29.4063 | 29.7121 | 30.3939 | 30.2747 | 29.4248 | 29.975 | 30.2366
GPK | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Total | Budget 2025
OB Removal (KBcm) | 534.7729 | 568.3212 | 598.8463 | 615.7375 | 655 | 720 | 790 | 825 | 800 | 820 | 780 | 792.3221 | 8500 | 8500 | 100%
ARKA | 534.7729 | 568.3212 | 598.8463 | 615.7375 | 655 | 720 | 790 | 825 | 800 | 820 | 780 | 792.3221 | 8500 | 8500
ROM Production (Kton) | 202.9475 | 206.0717 | 193.2873 | 202.809 | 205 | 200 | 130 | 137 | 135 | 150 | 170 | 167.8846 | 2100 | 2100 | 100%
ARKA | 159.0138 | 158.0398 | 150.5687 | 160.3724 | 157.5 | 157.5 | 94.308 | 97.8571 | 106.3125 | 110 | 109 | 107.8236 | 1568.296 | 1467
SLS | 43.9337 | 48.0318 | 42.7186 | 42.4366 | 47.5 | 42.5 | 35.692 | 39.1429 | 28.6875 | 40 | 61 | 60.061 | 531.704 | 633
Other Contractor | [12 empty] | 0
SR ROM | 2.635 | 2.7579 | 3.0982 | 3.036 | 3.1951 | 3.6 | 6.0769 | 6.0219 | 5.9259 | 5.4667 | 4.5882 | 4.7194 | 4.0476 | 4.0476
SR FC | 1.992 | 3.2809 | 3.3142 | 2.9183 | 3.119 | 4 | 9.875 | 11.7857 | 8 | 5.4114 | 3.6279 | 3.7713 | 4.1463 | 4.1463
FC Production (Ktons) | 268.4669 | 173.22 | 180.692 | 210.9939 | 210 | 180 | 80 | 70 | 100 | 151.5331 | 215 | 210.0941 | 2050 | 2050
CV(GAR) | 3724.8809 | 3770.9785 | 3744.4236 | 3734.7558 | 3687.7042 | 3655.6699 | 3642.6522 | 3693.462 | 3706.0959 | 3725.6167 | 3731.9834 | 3735.014 | 3718.2692 | 3727.504
TS | 0.18179 | 0.1619 | 0.15271 | 0.18618 | 0.16137 | 0.15574 | 0.1558 | 0.14698 | 0.14625 | 0.14906 | 0.15983 | 0.1611 | 0.16284 | 0.15227
Ash | 9.388 | 9.0395 | 7.3286 | 7.4295 | 8.4398 | 8.8319 | 8.9677 | 8.8085 | 8.9534 | 7.5211 | 7.0687 | 6.951 | 8.1411 | 7.9761
IM | 21.0636 | 19.2873 | 18.6168 | 20.3173 | 23.4217 | 23.4721 | 23.6544 | 22.2027 | 22.2537 | 21.2034 | 21.8874 | 21.7277 | 21.4369 | 27.2546
TM | 38.3472 | 38.2059 | 39.1151 | 39.3409 | 38.4486 | 38.551 | 38.5877 | 38.0074 | 37.8355 | 37.8818 | 38.0863 | 38.0565 | 38.4148 | 38.2852
TIS | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Total | Budget 2025
OB Removal (KBcm) | 661.7443 | 587.5763 | 862.7898 | 732.0436 | 983.4198 | 927.0163 | 1069.1564 | 1066.3405 | 1036.3004 | 989.6291 | 877.8563 | 914.3139 | 10708.1867 | 10708.1867 | 100%
PJPN | 661.7443 | 587.5763 | 862.7898 | 732.0436 | 983.4198 | 927.0163 | 1069.1564 | 1066.3405 | 1036.3004 | 989.6291 | 877.8563 | 914.3139 | 10708.1867 | 10708.1867
ROM Production (Kton) | 36.6685 | 40.4296 | 41.2222 | 46.5491 | 50.6199 | 55 | 60 | 60 | 60 | 54.7553 | 50.7553 | 50 | 606 | 605.9999 | 100%
PJPN | 36.6685 | 40.4296 | 17.4196 | 19.5691 | 7.6199 | 55 | 40 | 45 | 40 | 54.7553 | 50.7553 | 50 | 457.2174 | 605.9999
ROM PIT I |  |  | 23.8026 | 26.98 | 43 | 0 | 20 | 15 | 20 | 0 | 0 | 0 | 148.7826
SR ROM | 18.0466 | 14.5333 | 20.9302 | 15.7263 | 19.4275 | 16.8548 | 17.8193 | 17.7723 | 17.2717 | 18.0737 | 17.2958 | 18.2863 | 17.6703 | 17.6703
SR FC | 69.6709 | 99.0111 | 36.5071 | 28.5403 | 32.7807 | 18.5403 | 26.7289 | 23.6965 | 25.9075 | 21.9918 | 8.7671 | 5.1904 | 18.1188 | 18.1188
FC Production (Ktons) | 9.4982 | 5.9345 | 23.6335 | 25.6495 | 30 | 50 | 40 | 45 | 40 | 45 | 100.131 | 176.1535 | 591 | 591
TIS.HCV.HS | 9.4982 | 5.9345 | 23.6335 | 25.6495 | 30 | 50 | 40 | 45 | 40 | 45 | 100.131 | 176.1535 | 591 | 591
CV(GAR) | 6571.5022 | 6870.6132 | 6805.4517 | 6863.1036 | 6975.7068 | 6876.5343 | 7170.0218 | 7132.9658 | 7117.8839 | 7078.4354 | 7127.0083 | 7098.6992 | 7052.9339 | 6914.9248
TS | 1.7712 | 0.82 | 1.1687 | 1.2244 | 1.5602 | 1.17 | 1.2556 | 1.0695 | 1.017 | 1.0528 | 1.0755 | 1.1872 | 1.1662 | 0.97968
Ash | 4.8216 | 2.98 | 3.3931 | 3.002 | 3.4133 | 2.36 | 3.3955 | 3.0756 | 3.1532 | 3.1174 | 3.2647 | 3.2769 | 3.1909 | 3.7674
IM | 5.7298 | 6.25 | 6.5933 | 5.0621 | 4.9947 | 6.31 | 5.0174 | 4.7331 | 4.7791 | 4.7242 | 4.7122 | 4.8271 | 5.0458 | 8.6903
TM | 10.0619 | 11.07 | 11.3529 | 10.8902 | 7.8609 | 12.5 | 7.8879 | 7.696 | 7.6996 | 7.6897 | 7.7495 | 7.9056 | 8.5519 | 4.7342
NPR | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Total | Budget 2025
OB Removal (KBcm) | 0 | 0 | 0 | 110 | 354 | 565 | 722 | 847 | 823 | 782 | 709 | 771.5 | 5683.5 | 5683.5
PAMA | 0 | 0 | 0 | 110 | 354 | 565 | 722 | 847 | 823 | 782 | 709 | 771.5 | 5683.5 | 5683.5
ROM Production (Kton) | 0 | 0 | 0 | 0 | 0 | 25 | 50 | 60 | 60 | 97 | 86 | 72 | 450 | 450
PAMA | 0 | 0 | 0 | 0 | 0 | 25 | 50 | 60 | 60 | 97 | 86 | 72 | 450 | 450
SR ROM | 0 | 0 | 0 | 0 | 0 | 22.6 | 14.44 | 14.1167 | 13.7167 | 8.0619 | 8.2442 | 10.7153 | 12.63 | 12.63
SR FC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22.8919 | 11.7571 | 11.6716 | 11.8167 | 11.6894 | 18.945 | 18.945
FC Production (Ktons) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 37 | 70 | 67 | 60 | 66 | 300 | 300
CV(GAR) | Jun: 5756.0052; Jul: 5622.3539; Aug: 5864.0557; Sep: 5996.2951; Oct: 5894.1972; Nov: 5911.0858; Dec: 5944.2132 | 5928.6838 | 5016.4003
TS | 0 | 0 | 0 | 0 | 0 | 1.2141 | 1.1045 | 1.2843 | 1.4995 | 1.3579 | 1.4164 | 1.4017 | 1.4032 | 0.85231
Ash | 0 | 0 | 0 | 0 | 0 | 6.132 | 6.7552 | 7.4159 | 6.7139 | 7.6324 | 7.5064 | 7.1789 | 7.2664 | 4.606
IM | 0 | 0 | 0 | 0 | 0 | 11.1428 | 11.3561 | 10.9176 | 10.2883 | 10.4652 | 10.7083 | 11.0625 | 10.6597 | 5.8143
TM | 0 | 0 | 0 | 0 | 0 | 16.8753 | 16.6217 | 16.4533 | 15.748 | 15.9415 | 15.9184 | 15.9779 | 15.9628 | 11.202
| Q1 | Q1 | Q1 | Q2 | Q2 | Q2 | Q3 | Q3 | Q3 | Q4 | Q4 | Q4
Note on A8: Belfry Parulian Pandiangan: include high ash
Note on A86: Belfry Parulian Pandiangan: incoming coal volume (quality is not as actual but as range in contract)
Note on A92: Belfry Parulian Pandiangan: incoming coal volume (quality is not as actual but as range in contract)
Note on A100: Belfry Parulian Pandiangan: include Mud
Note on A125: Belfry Parulian Pandiangan: include Mud and sliding volume

## Outlook Quarterly 4+8
ITM outlook 2025 (4+8)
| Act. | Out. | Out. | Out. | Out.
IMM | Q1 | Q2 | Q3 | Q4 | Total | Budget 2025
OB Removal (KBcm) | 20851.6751 | 22449.4375 | 25789.7182 | 26107.2057 | 95198.0366 | 94714.4782 | 100.5%
PAMA (WB) | 7367.5048 | 7617.5744 | 9290.1101 | 9404.1677 | 33679.357 | 33532.659
PAMA (EB) | 13484.1703 | 14831.8631 | 16499.6081 | 16703.0381 | 61518.6796 | 61181.8192
ROM Production (Kton) | 1579.7398 | 1597.0326 | 1930 | 1940.7276 | 7047.5 | 6950 | 101.4%
PAMA (WB) | 492.1351 | 393.7127 | 460 | 386.6522 | 1732.5 | 1862.5
PAMA (EB) | 1087.6047 | 1203.3199 | 1470 | 1554.0754 | 5315 | 5087.5
Fine Coal (WB) | 0 | 0 | 0 | 0 | 0 | 0
SR ROM Total | 13.1994 | 14.057 | 13.3625 | 13.4523 | 13.5081 | 13.628
FC Product (Kton) | 1698.6086 | 1647.8049 | 1971.25 | 1817.3364 | 7135 | 7100
PAMA (WB) | 568.0779 | 414.0344 | 470 | 277.8877 | 1730 | 1862.5
PAMA (EB) | 1130.5307 | 1225.0787 | 1471.5 | 1501.1988 | 5328.3081 | 5110
Fine Coal | 0 | 8.6919 | 29.75 | 38.25 | 76.6919 | 127.5
SR FC Total | 12.2757 | 13.6238 | 13.0829 | 14.3656 | 13.3424 | 13.3401
IMM-WB.HCV.LS | 398.6428 | 271.1901 | 252.9327 | 180.4361 | 1103.2017 | 1228.8032
CV(GAR) | 6165.9257 | 6094.5101 | 6277.0487 | 6297.4028 | 6195.3516 | 6169.7769
TS | 0.63595 | 0.79943 | 0.80159 | 0.83129 | 0.74606 | 0.8108
Ash | 8.4258 | 8.5323 | 8.2466 | 8.1546 | 8.3666 | 8.3746
Moist | 8.9486 | 8.8717 | 7.804 | 7.2498 | 8.3894 | 8.0403
TM | 11.705 | 13.3386 | 12.8293 | 12.2751 | 12.4576 | 13.0657
IMM-WB.HCV.HS | 169.4351 | 142.8443 | 217.0673 | 97.4516 | 626.7983 | 633.6968
CV(GAR) | 5965.8964 | 5925.0455 | 5964.2184 | 5902.3394 | 5946.124 | 5965.7827
TS | 2.1513 | 2.536 | 2.6903 | 2.6532 | 2.5036 | 2.579
Ash | 11.8233 | 13.6958 | 13.752 | 14.8316 | 13.3857 | 13.9606
Moist | 7.4971 | 6.9055 | 6.8361 | 7.4195 | 7.1213 | 6.744
TM | 11.3616 | 11.6669 | 11.8615 | 12.4448 | 11.7727 | 11.7694
IMM-EB.MCV.LS | 17.9985 | 19.4121 | 0 | 0 | 37.4106 | 13.6399
CV(GAR) | 5860.2842 | 5918.594 | 0 | 0 | 5890.5407 | 5822.4314
TS | 0.92078 | 0.92864 | 0 | 0 | 0.92486 | 0.90072
Ash | 7.1846 | 7.5367 | 0 | 0 | 7.3673 | 8.5978
Moist | 11.0164 | 11.714 | 0 | 0 | 11.3783 | 11.3544
TM | 14.5019 | 15.6502 | 0 | 0 | 15.0977 | 16.3544
IMM-EB.MCV.MS | 48.099 | 74.1416 | 143.2577 | 235.756 | 501.2543 | 422.7155
CV(GAR) | 5977.8247 | 5934.9456 | 6012.1105 | 6021.4067 | 6001.7792 | 6013.6725
TS | 1.4343 | 1.5288 | 1.5754 | 1.576 | 1.5553 | 1.5595
Ash | 6.0427 | 6.1888 | 5.3453 | 5.3347 | 5.532 | 5.3287
Moist | 11.6102 | 11.5654 | 10.4146 | 10.1153 | 10.5588 | 10.2792
TM | 14.1414 | 14.8586 | 15.4146 | 15.1153 | 15.0694 | 15.2792
IMM-EB.MCV.HS | 1064.4332 | 1131.525 | 1328.2423 | 1265.4427 | 4789.6432 | 4673.6446
CV(GAR) | 5997.3733 | 5908.0775 | 5903.6288 | 5918.4799 | 5929.4369 | 5914.4155
TS | 2.2888 | 2.3362 | 2.458 | 2.4168 | 2.3807 | 2.4107
Ash | 6.0178 | 6.0394 | 5.7705 | 5.7158 | 5.8745 | 5.72
Moist | 11.3584 | 11.0121 | 10.5212 | 10.506 | 10.8192 | 10.5582
TM | 13.6089 | 15.1973 | 15.5212 | 15.506 | 15.0157 | 15.5582
Fine Coal | 0 | 8.6919 | 29.75 | 38.25 | 76.6919 | 127.5
CV(GAR) | 0 | 3164.173 | 3146.0674 | 3146.0674 | 3148.1194 | 3146.0674
TS | 0 | 1.9768 | 2 | 2 | 1.9974 | 2
Ash | 0 | 39.6556 | 40 | 40 | 39.961 | 40
Moist | 0 | 11.0221 | 11 | 11 | 11.0025 | 11
TM | 0 | 20.064 | 20 | 20 | 20.0073 | 20
TCM | Q1 | Q2 | Q3 | Q4 | Total | Budget 2025
OB Removal (KBcm) | 10676.4767 | 10373.5105 | 13762.4343 | 12087.5784 | 46900 | 51650 | 90.8%
PAMA | 3675.6012 | 5041.7745 | 8162.8889 | 7519.7354 | 24400 | 24400
MAP | 2955.7184 | 2557.5562 | 3000 | 2486.7254 | 11000 | 11000
PJPN | 4045.1571 | 2774.1799 | 2599.5454 | 2081.1176 | 11500 | 16250
ROM Production (Kton) | 646.7268 | 743.0519 | 1068.6611 | 1006.5601 | 3465 | 3300.387 | 105%
PAMA | 410.7747 | 476.2453 | 642.3773 | 600.6026 | 2130 | 2130
MAP | 108.214 | 126.57 | 161.715 | 153.5009 | 550 | 550
PJPN | 123.3898 | 136.0869 | 264.5688 | 252.4565 | 776.5021 | 620.387
SNS | 4.3483 | 4.1496 | 0 | 0 | 8.4979
SR ROM with void | 16.5085 | 13.9607 | 12.8782 | 12.0088 | 13.5354 | 15.6497
FC Product CP (Kton) | 737.9146 | 710.3136 | 1000 | 952.1702 | 3400.3985 | 3230
TCM.HCV.LS | 437.9277 | 340.8186 | 545 | 526.6522 | 1850.3985 | 1630
TCM.HCV.HS | 299.9869 | 369.495 | 455 | 425.5181 | 1550 | 1480
TCM.HCV.MS | 0 | 0 | 0 | 0 | 0 | 120
FC Product 3rd party (Kton) | 57.1257 | 53.4973 | 58.8103 | 75.2631 | 244.6963 | 1676.5
EBH.HCV.LS | 7.1098 | 40.5275 | 51.9524 | 50.1264 | 149.7161 | 671.5
MBL.MCV.MS | 50.0159 | 12.9697 | 6.8579 | 25.1368 | 94.9803 | 1005
SR FC | 14.4684 | 14.6041 | 13.7624 | 12.6948 | 13.7925 | 15.9907
TCM.HCV.LS | 437.9277 | 340.8186 | 545 | 526.6522 | 1850.3985 | 1630
CV(GAR) | 6639.7412 | 6575.7643 | 6520.7567 | 6413.6679 | 6528.5689 | 6355.6513
Sul < 0.7 | 0.67682 | 0.72117 | 0.75068 | 0.70439 | 0.71459 | 0.60341
ASH < 5.0 | 4.095 | 4.8678 | 4.8552 | 4.7827 | 4.6569 | 4.8411
IM | 7.0529 | 7.3083 | 7.9509 | 8.0027 | 7.6348 | 7.3863
TM | 11.8734 | 11.9787 | 11.5839 | 12.7491 | 12.0568 | 13.8465
TCM.HCV.HS | 299.9869 | 369.495 | 455 | 425.5181 | 1550 | 1480
CV(GAR) | 6546.3914 | 6530.9807 | 6526.6593 | 6464.7052 | 6514.5003 | 6482.812
Sul < 2.0 | 1.5725 | 1.6814 | 1.7443 | 1.7526 | 1.6983 | 1.8762
ASH < 5.0 | 4.2591 | 5.642 | 5.8311 | 5.9529 | 5.5152 | 10.2546
IM | 6.4203 | 6.5636 | 6.5024 | 5.9296 | 6.3439 | 6.6258
TM | 11.3214 | 11.334 | 11.0993 | 11.6749 | 11.3563 | 11.2522
EBH.HCV.LS | 7.1098 | 40.5275 | 51.9524 | 50.1264 | 149.7161 | 671.5
CV(GAR) | 6322 | 6322 | 6322 | 6322 | 6322 | 6322
Sul < 1.2 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6
ASH < 5.0 | 7 | 7 | 7 | 7 | 7 | 7
IM | 12 | 12 | 12 | 12 | 12 | 12
TM | 14 | 14 | 14 | 14 | 14 | 14
MBL.MCV.MS | 50.0159 | 12.9697 | 6.8579 | 25.1368 | 94.9803 | 1005
CV(GAR) | 5400 | 5400 | 5400 | 5400 | 5400 | 5400
Sul < 1.2 | 1 | 1 | 1 | 1 | 1 | 1
ASH < 5.0 | 6 | 6 | 6 | 6 | 6 | 6
IM | 15 | 15 | 15 | 15 | 15 | 15
TM | 24 | 24 | 24 | 24 | 24 | 24
BEK | Q1 | Q2 | Q3 | Q4 | Total | Budget 2025
OB Removal (KBcm) | 21749.2528 | 24093.4887 | 24685.9727 | 22971.2861 | 93500.0002 | 90950 | 102.8%
TRUST | 4618.2176 | 7008.5275 | 6020.9727 | 6352.2824 | 24000.0002 | 24000
PAMA | 11147.4983 | 12680.8654 | 15810 | 15361.6364 | 55000 | 52450
SNS | 5983.5369 | 4404.0958 | 2855 | 1257.3673 | 14500 | 14500
ROM Production (Kton) | 2384.6632 | 2085.0239 | 2050 | 1730.313 | 8250 | 8000 | 103.1%
TRUST | 652.3144 | 613.8466 | 605 | 528.8389 | 2400 | 2400
PAMA | 1195.5137 | 925.2214 | 1340 | 1139.2649 | 4600 | 4400
SNS | 536.835 | 545.9558 | 105 | 62.2092 | 1250 | 1200
SR ROM | 9.1205 | 11.5555 | 12.0419 | 13.2758 | 11.3333 | 11.3688
SR FC | 10.152 | 11.4412 | 11.7552 | 11.1415 | 11.1177 | 11.2284
FC Product (KTons) | 2142.3624 | 2105.859 | 2100 | 2061.7787 | 8410 | 8100
BEK.HCV.LS | 1740.8722 | 1393.7176 | 1500 | 1465.4102 | 6100 | 5560
CV(GAR) | 6143.341 | 6093.826 | 6259.7146 | 6239.0552 | 6183.6379 | 5915.2264
TS | 0.53125 | 0.58045 | 0.54968 | 0.55713 | 0.55324 | 0.5772
Ash | 4.4045 | 4.053 | 3.9956 | 3.9029 | 4.1031 | 4.8848
IM | 10.5333 | 10.9563 | 10.632 | 10.7311 | 10.7017 | 11.4694
TM | 15.9061 | 16.6032 | 14.4757 | 14.8009 | 15.4481 | 15.2419
BEK.HCV.HS | 401.4902 | 712.1413 | 600 | 596.3685 | 2310 | 2540
CV(GAR) | 6068.5304 | 6130.3711 | 6186.9204 | 6199.9973 | 6152.2863 | 5792.8232
TS | 1.9721 | 1.9193 | 1.8692 | 1.8821 | 1.9059 | 1.7606
Ash | 5.4116 | 5.2734 | 4.5471 | 4.5855 | 4.9312 | 5.7572
IM | 10.4965 | 10.1441 | 10.6134 | 10.5561 | 10.4336 | 10.7369
TM | 15.6136 | 14.4443 | 14.4835 | 14.2718 | 14.6132 | 14.5518
JBG | Q1 | Q2 | Q3 | Q4 | Total | Budget 2025
OB Removal (KBcm) | 0 | 160 | 904 | 1055 | 2119 | 5038.608 | 42.06%
Pit UCE-Extend | 0 | 160 | 904 | 1055 | 2119 | 5038.608
ROM Production (Kton) | 0 | 0 | 26 | 174 | 200 | 448 | 44.64%
Pit UCE-Extend | 0 | 0 | 26 | 174 | 200 | 448
SR ROM | 0 | 0 | 34.7692 | 6.0632 | 10.595 | 11.2469
SR FC | 0 | 0 | 37.6667 | 6.1696 | 10.8667 | 11.6365
JBG Coal Loading | 0 | 18.1 | 55.4 | 149 | 222.5 | 430.7
JBG FC Product (Kton) / JBG | 0 | 0 | 24 | 171 | 195 | 433
CV(GAR) | 0 | 0 | 4437.3537 | 4340.4136 | 4352.3447 | 4423.7946
TS | 0 | 0 | 0.42332 | 0.36636 | 0.37337 | 0.36899
Ash | 0 | 0 | 4.8365 | 5.3242 | 5.2642 | 4.4323
IM | 0 | 0 | 17.0106 | 16.1786 | 16.281 | 16.9259
TM | 0 | 0 | 29.6866 | 30.0155 | 29.975 | 30.2366
GPK | Q1 | Q2 | Q3 | Q4 | Total | Budget 2025
OB Removal (KBcm) | 1701.9405 | 1990.7375 | 2415 | 2392.3221 | 8500 | 8500 | 100%
ARKA | 1701.9405 | 1990.7375 | 2415 | 2392.3221 | 8500 | 8500
ROM Production (Kton) | 602.3065 | 607.809 | 402 | 487.8846 | 2100 | 2100 | 100%
ARKA | 467.6224 | 475.3724 | 298.4777 | 326.8236 | 1568.296 | 1467
SLS | 134.6841 | 132.4366 | 103.5223 | 161.061 | 531.704 | 633
Other Contractor |  |  |  |  | 0
SR ROM | 2.8257 | 3.2753 | 6.0075 | 4.9035 | 4.0476 | 4.0476
SR FC | 2.7346 | 3.3124 | 9.66 | 4.1488 | 4.1463 | 4.1463
FC Production (Ktons) | 622.379 | 600.9939 | 250 | 576.6271 | 2050 | 2050
CV(GAR) | 3743.3845 | 3694.6284 | 3682.2564 | 3731.4145 | 3718.2692 | 3727.504
TS | 0.16781 | 0.1684 | 0.14951 | 0.15746 | 0.16284 | 0.15227
Ash | 8.6931 | 8.2025 | 8.9174 | 7.1447 | 8.1411 | 7.9761
IM | 19.8588 | 22.3469 | 22.6876 | 21.6495 | 21.4369 | 27.2546
TM | 38.5308 | 38.7925 | 38.1244 | 38.0217 | 38.4148 | 38.2852
TIS | Q1 | Q2 | Q3 | Q4 | Total | Budget 2025
OB Removal (KBcm) | 2112.1103 | 2642.4797 | 3171.7973 | 2781.7994 | 10708.1867 | 10708.1867 | 100%
PJPN | 2112.1103 | 2642.4797 | 3171.7973 | 2781.7994 | 10708.1867 | 10708.1867
ROM Production (Kton) | 118.3203 | 152.169 | 180 | 155.5107 | 606 | 605.9999 | 100%
PJPN | 94.5177 | 82.189 | 125 | 155.5107 | 457.2174 | 605.9999
ROM PIT I | 23.8026 | 69.98 | 55 | 0 | 148.7826
SR ROM | 17.8508 | 17.3654 | 17.6211 | 17.8882 | 17.6703 | 17.6703
SR FC | 54.065 | 25.0118 | 25.3744 | 8.6584 | 18.1188 | 18.1188
FC Production (Ktons) | 39.0661 | 105.6495 | 125 | 321.2844 | 591 | 591
TIS.HCV.HS | 39.0661 | 105.6495 | 125 | 321.2844 | 591 | 591
CV(GAR) | 6758.4701 | 6901.4344 | 7139.9975 | 7104.6838 | 7052.9339 | 6914.9248
TS | 1.2622 | 1.294 | 1.1122 | 1.1336 | 1.1662 | 0.97968
Ash | 3.6776 | 2.8149 | 3.2028 | 3.2507 | 3.1909 | 3.7674
IM | 6.3312 | 5.6335 | 4.8388 | 4.7768 | 5.0458 | 8.6903
TM | 10.996 | 10.7919 | 7.7586 | 7.8267 | 8.5519 | 4.7342
NPR | Q1 | Q2 | Q3 | Q4 | Total | Budget 2025
OB Removal (KBcm) | 0 | 1029 | 2392 | 2262.5 | 5683.5 | 5683.5
PAMA | 0 | 1029 | 2392 | 2262.5 | 5683.5 | 5683.5
ROM Production (Kton) | 0 | 25 | 170 | 255 | 450 | 450
PAMA | 0 | 25 | 170 | 255 | 450 | 450
SR ROM | 0 | 41.16 | 14.0706 | 8.8725 | 12.63 | 12.63
SR FC | 0 | 0 | 22.3551 | 11.7228 | 18.945 | 18.945
FC Production (Ktons) | 0 | 0 | 107 | 193 | 300 | 300
CV(GAR) | 0 | 0 | 5950.5674 | 5916.5515 | 5928.6838 | 5016.4003
TS | 0 | 0 | 1.4251 | 1.3911 | 1.4032 | 0.85231
Ash | 0 | 0 | 6.9566 | 7.4381 | 7.2664 | 4.606
IM | 0 | 0 | 10.5059 | 10.745 | 10.6597 | 5.8143
TM | 0 | 0 | 15.9919 | 15.9467 | 15.9628 | 11.202
Note on A8: Belfry Parulian Pandiangan: include high ash
Note on A86: Belfry Parulian Pandiangan: incoming coal volume (quality is not as actual but as range in contract)
Note on A92: Belfry Parulian Pandiangan: incoming coal volume (quality is not as actual but as range in contract)
Note on A100: Belfry Parulian Pandiangan: include Mud
Note on A125: Belfry Parulian Pandiangan: include Mud and sliding volume

## BudgVSact. June (hidden)
SITES | OB |  | ROM |  | FC |  | SR (OB/ROM) |  | Diff. (Act.%)
| Budget | Actual | Budget | Actual | Budget | Actual | Budget | Actual | OB | ROM
IMM | 45360.0431 | 43301.1126 | 3220 | 3176.7724 | 3275.5 | 3346.4136 | 14.087 | 13.6305 | 95.46% | 98.66%
TCM | 25550 | 21049.9873 | 1487 | 1389.7788 | 1562 | 1448.2282 | 17.1822 | 15.1463 | 82.39% | 93.46%
BEK | 45094 | 45842.7415 | 3966.5 | 4469.687 | 4050 | 4248.2213 | 11.3687 | 10.2564 | 101.7% | 112.7%
JBG | 1603.028 | 160 | 57 | 0 | 53 | 0 | 28.1233 | #DIV/0! | 9.981% | 0%
GPK | 3825 | 3692.6779 | 1062 | 1210.1154 | 1100 | 1223.3729 | 3.6017 | 3.0515 | 96.54% | 113.9%
TIS | 4924.429 | 4754.59 | 270.886 | 270.4893 | 245 | 144.7156 | 18.179 | 17.5777 | 96.55% | 99.85%
TOTAL | 126356.5002 | 118801.1093 | 10063.386 | 10516.8429 | 10285.5 | 10410.9515 | 12.5561 | 11.2963 | 94.02% | 104.5%
|  |  |  | 104.5% |  | 101.2%