## Budget 2025
ITM plan year 2024
As of 18 Nov'24
IMM | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Total
OB Removal (KBcm) | 7619.4483 | 7224.3023 | 6870.0231 | 7815.9147 | 8233.4755 | 7596.8792 | 8769.11 | 8498.0492 | 8442.1757 | 8242.1086 | 7836.3005 | 7566.691 | 94714.4782 | Done
PAMA (WB) | 2904.786 | 2754.4503 | 2424.321 | 2767.1447 | 2927.6178 | 2460.4194 | 3157.9028 | 3107.2173 | 2899.6426 | 2829.8233 | 2690.1553 | 2609.1784 | 33532.659
PAMA (EB) | 4714.6622 | 4469.852 | 4445.7021 | 5048.77 | 5305.8577 | 5136.4598 | 5611.2072 | 5390.8319 | 5542.5331 | 5412.2853 | 5146.1452 | 4957.5126 | 61181.8192
ROM Production (Kton) | 537.5 | 532.5 | 537.5 | 537.5 | 537.5 | 537.5 | 610 | 625 | 625 | 625 | 625 | 620 | 6950
PAMA (WB) | 192.5 | 187.5 | 192.5 | 190 | 185 | 155 | 130 | 135 | 145 | 110 | 120 | 120 | 1862.5
PAMA (EB) | 345 | 345 | 345 | 347.5 | 352.5 | 382.5 | 480 | 490 | 480 | 515 | 505 | 500 | 5087.5
Fine Coal | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SR ROM Total | 14.1757 | 13.5668 | 12.7814 | 14.5412 | 15.3181 | 14.1337 | 14.3756 | 13.5969 | 13.5075 | 13.1874 | 12.5381 | 12.2043 | 13.628
FC Product (Kton) | 541.75 | 536.75 | 541.75 | 551.75 | 551.75 | 551.75 | 635.75 | 637.75 | 637.75 | 637.75 | 637.75 | 637.75 | 7100
PAMA (WB) | 192.5 | 187.5 | 192.5 | 190 | 185 | 155 | 130 | 135 | 145 | 110 | 120 | 120 | 1862.5
PAMA (EB) | 345 | 345 | 345 | 349 | 354 | 384 | 493 | 490 | 480 | 515 | 505 | 505 | 5110
Fine Coal | 4.25 | 4.25 | 4.25 | 12.75 | 12.75 | 12.75 | 12.75 | 12.75 | 12.75 | 12.75 | 12.75 | 12.75 | 127.5
SR FC Total | 14.0645 | 13.4593 | 12.6812 | 14.1657 | 14.9225 | 13.7687 | 13.7933 | 13.325 | 13.2374 | 12.9237 | 12.2874 | 11.8647 | 13.3401
IMM-WB.HCV.LS | 154.9822 | 150.1922 | 153.4446 | 142.7318 | 131.892 | 90.2567 | 45.0528 | 60.1041 | 62.6233 | 73.6379 | 78.4656 | 85.4199 | 1228.8032
CV(GAR) | 6066.6995 | 6061.099 | 6072.9614 | 6113.1737 | 6106.3251 | 6216.0563 | 6397.4706 | 6374.5335 | 6369.463 | 6395.7374 | 6207.9868 | 6224.9984 | 6169.7769
TS | 0.79939 | 0.7996 | 0.80631 | 0.80238 | 0.79513 | 0.79814 | 0.80006 | 0.80071 | 0.80424 | 0.87778 | 0.89103 | 0.79705 | 0.8108
Ash | 8.5932 | 8.5723 | 8.4653 | 8.3497 | 8.4545 | 8.0612 | 8.0877 | 8.0139 | 8.0939 | 8.3113 | 8.6583 | 8.1212 | 8.3746
Moist | 8.4968 | 8.6036 | 8.5701 | 8.2959 | 8.436 | 8.1042 | 7.1125 | 7.0457 | 7.1276 | 7.1603 | 7.2147 | 7.5403 | 8.0403
TM | 13.5221 | 13.629 | 13.5955 | 13.3212 | 13.4614 | 13.1296 | 12.1378 | 12.0711 | 12.153 | 12.1857 | 12.24 | 12.5656 | 13.0657
IMM-WB.HCV.HS | 37.5178 | 37.3078 | 39.0554 | 47.2682 | 53.108 | 64.7433 | 84.9472 | 74.8959 | 82.3767 | 36.3621 | 41.5344 | 34.5801 | 633.6968
CV(GAR) | 5995.4058 | 6102.8668 | 6012.8803 | 5956.2491 | 5900.982 | 5903.8514 | 5953.1501 | 5935.2903 | 5994.0694 | 5972.607 | 5974.5067 | 5973.0938 | 5965.7827
TS | 2.4296 | 2.4051 | 2.5319 | 2.5966 | 2.6453 | 2.7647 | 2.7578 | 2.7055 | 2.6432 | 2.4887 | 2.3842 | 1.9722 | 2.579
Ash | 13.6503 | 13.0727 | 13.5362 | 14.1977 | 14.7482 | 14.5558 | 13.6829 | 14.4235 | 13.8303 | 13.8021 | 13.9633 | 13.2396 | 13.9606
Moist | 6.0447 | 6.0271 | 6.0381 | 6.067 | 6.0651 | 7.0545 | 6.8576 | 6.9141 | 7.1513 | 7.5031 | 7.5101 | 7.1237 | 6.744
TM | 11.07 | 11.0525 | 11.0635 | 11.0924 | 11.0904 | 12.0799 | 11.883 | 11.9395 | 12.1767 | 12.5284 | 12.5355 | 12.1491 | 11.7694
IMM-EB.MCV.LS | 3.3846 | 2.1986 | 2.3031 | 2.7672 | 1.8759 | 1.1106 | 0 | 0 | 0 | 0 | 0 | 0 | 13.6399
CV(GAR) | 5821.883 | 5816.4871 | 5824.2204 | 5826.2223 | 5821.6228 | 5824.0809 | 0 | 0 | 0 | 0 | 0 | 0 | 5822.4314
TS | 0.89813 | 0.89994 | 0.9013 | 0.90153 | 0.90292 | 0.90326 | 0 | 0 | 0 | 0 | 0 | 0 | 0.90072
Ash | 8.6642 | 8.6538 | 8.6424 | 8.5289 | 8.516 | 8.5015 | 0 | 0 | 0 | 0 | 0 | 0 | 8.5978
Moist | 11.333 | 11.3369 | 11.3693 | 11.3501 | 11.3996 | 11.3577 | 0 | 0 | 0 | 0 | 0 | 0 | 11.3544
TM | 16.333 | 16.3369 | 16.3693 | 16.3501 | 16.3996 | 16.3577 | 0 | 0 | 0 | 0 | 0 | 0 | 16.3544
IMM-EB.MCV.MS | 2.5219 | 7.2155 | 26.7201 | 6.3272 | 12.6302 | 4.8088 | 12.095 | 14.9981 | 83.6973 | 94.4006 | 71.3353 | 85.9656 | 422.7155
CV(GAR) | 6013.744 | 5958.5719 | 6011.5142 | 6033.7912 | 5987.1311 | 6002.8141 | 6036.2059 | 6005.6296 | 5996.4183 | 6012.5832 | 6026.6617 | 6027.4417 | 6013.6725
TS | 1.5719 | 1.5705 | 1.5645 | 1.5541 | 1.5514 | 1.5491 | 1.5706 | 1.5667 | 1.5493 | 1.5533 | 1.5598 | 1.5724 | 1.5595
Ash | 6.0748 | 6.1531 | 6.1792 | 5.1976 | 5.2946 | 5.2369 | 5.1053 | 5.3674 | 5.3569 | 5.1697 | 5.1649 | 5.301 | 5.3287
Moist | 10.1273 | 10.2338 | 10.5326 | 10.3526 | 10.7819 | 10.4813 | 10.3659 | 10.4684 | 10.4436 | 10.274 | 10.2404 | 9.9508 | 10.2792
TM | 15.1273 | 15.2338 | 15.5326 | 15.3526 | 15.7819 | 15.4813 | 15.3659 | 15.4684 | 15.4436 | 15.274 | 15.2404 | 14.9508 | 15.2792
IMM-EB.MCV.HS | 339.0935 | 335.5859 | 315.9768 | 339.9056 | 339.494 | 378.0807 | 480.905 | 475.0019 | 396.3027 | 420.5994 | 433.6647 | 419.0344 | 4673.6446
CV(GAR) | 5916.7973 | 5925.4345 | 5916.7949 | 5912.981 | 5924.7515 | 5924.6893 | 5904.2294 | 5885.0998 | 5912.8315 | 5911.5994 | 5931.5837 | 5905.9088 | 5914.4155
TS | 2.4966 | 2.3878 | 2.3758 | 2.4776 | 2.3743 | 2.3234 | 2.4258 | 2.4636 | 2.4167 | 2.4358 | 2.3206 | 2.4316 | 2.4107
Ash | 5.9843 | 5.6663 | 5.7801 | 5.6993 | 5.574 | 5.7147 | 5.7035 | 5.9277 | 5.6702 | 5.6371 | 5.5902 | 5.6939 | 5.72
Moist | 10.2836 | 10.5562 | 10.6838 | 10.4873 | 10.6898 | 10.7239 | 10.6197 | 10.5236 | 10.4781 | 10.4971 | 10.5525 | 10.6017 | 10.5582
TM | 15.2836 | 15.5562 | 15.6838 | 15.4873 | 15.6898 | 15.7239 | 15.6197 | 15.5236 | 15.4781 | 15.4971 | 15.5525 | 15.6017 | 15.5582
Fine Coal | 4.25 | 4.25 | 4.25 | 12.75 | 12.75 | 12.75 | 12.75 | 12.75 | 12.75 | 12.75 | 12.75 | 12.75 | 127.5
CV(GAR) | 3146.0674 | 3146.0674 | 3146.0674 | 3146.0674 | 3146.0674 | 3146.0674 | 3146.0674 | 3146.0674 | 3146.0674 | 3146.0674 | 3146.0674 | 3146.0674 | 3146.0674
TS | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Ash | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40
Moist | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11
TM | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20
TCM | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Total
OB Removal (KBcm) | 4195 | 4015 | 4020 | 4250 | 4410 | 4660 | 4720 | 5055 | 4740 | 3990 | 3805 | 3790 | 51650 | Done
PAMA | 2025 | 1905 | 1870 | 2010 | 2110 | 2210 | 2320 | 2305 | 2240 | 1890 | 1745 | 1770 | 24400
MAP | 890 | 810 | 750 | 940 | 950 | 950 | 1000 | 1050 | 950 | 900 | 860 | 950 | 11000
PJPN | 1280 | 1300 | 1400 | 1300 | 1350 | 1500 | 1400 | 1700 | 1550 | 1200 | 1200 | 1070 | 16250
ROM Production (Kton) | 200 | 215 | 217 | 255 | 285 | 315 | 310 | 335.387 | 307 | 300 | 281 | 280 | 3300.387
PAMA | 130 | 145 | 150 | 160 | 170 | 200 | 195 | 210 | 210 | 195 | 180 | 185 | 2130
MAP | 45 | 40 | 37 | 45 | 50 | 50 | 50 | 55 | 47 | 45 | 41 | 45 | 550
PJPN | 25 | 30 | 30 | 50 | 65 | 65 | 65 | 70.387 | 50 | 60 | 60 | 50 | 620.387
SR ROM with void | 20.975 | 18.6744 | 18.5253 | 16.6667 | 15.4737 | 14.7937 | 15.2258 | 15.0721 | 15.4397 | 13.3 | 13.5409 | 13.5357 | 15.6497
FC Product CP (Kton) | 217 | 235 | 258 | 257 | 290 | 305 | 315 | 320 | 285 | 253 | 242 | 253 | 3230
TCM.HCV.LS | 110 | 130 | 130 | 140 | 150 | 170 | 170 | 150 | 155 | 115 | 115 | 95 | 1630
TCM.HCV.HS | 100 | 100 | 120 | 110 | 130 | 120 | 130 | 150 | 120 | 130 | 120 | 150 | 1480
TCM.HCV.MS | 7 | 5 | 8 | 7 | 10 | 15 | 15 | 20 | 10 | 8 | 7 | 8 | 120
FC Product 3rd party (Kton) | 139.1 | 139.4 | 138.6 | 138.1 | 139 | 138.3 | 138.5 | 137.7 | 145.6 | 146.2 | 138.3 | 137.7 | 1676.5
EBH.HCV.LS | 56.6 | 56.9 | 56.1 | 55.6 | 56.5 | 55.8 | 56 | 55.2 | 55.6 | 56.2 | 55.8 | 55.2 | 671.5
MBL.MCV.MS | 82.5 | 82.5 | 82.5 | 82.5 | 82.5 | 82.5 | 82.5 | 82.5 | 90 | 90 | 82.5 | 82.5 | 1005
SR FC | 19.3318 | 17.0851 | 15.5814 | 16.537 | 15.2069 | 15.2787 | 14.9841 | 15.7969 | 16.6316 | 15.7708 | 15.7231 | 14.9802 | 15.9907
TCM.HCV.LS | 110 | 130 | 130 | 140 | 150 | 170 | 170 | 150 | 155 | 115 | 115 | 95 | 1630
CV(GAR) | 6331.7794 | 6327.6426 | 6345.3425 | 6327.8237 | 6373.2296 | 6243.3002 | 6268.7387 | 6402.2298 | 6455.744 | 6429.1851 | 6453.9309 | 6360.7189 | 6355.6513
Sul < 0.7 | 0.63239 | 0.69248 | 0.652 | 0.6548 | 0.61487 | 0.6376 | 0.63464 | 0.55063 | 0.52383 | 0.52786 | 0.54698 | 0.54361 | 0.60341
ASH < 5.0 | 5.14 | 4.5591 | 4.5963 | 5.1237 | 4.8279 | 4.5406 | 5.4694 | 4.9514 | 4.2318 | 4.7988 | 4.93 | 4.9975 | 4.8411
IM | 7.9684 | 7.5074 | 7.3053 | 7.3142 | 7.2934 | 7.0845 | 7.3044 | 7.5576 | 7.1827 | 7.4775 | 7.325 | 7.6231 | 7.3863
TM | 13.5018 | 14.5066 | 14.2007 | 13.7425 | 13.7596 | 15.8885 | 14.3471 | 13.1866 | 13.1296 | 12.9827 | 12.4646 | 13.5285 | 13.8465
TCM.HCV.HS | 100 | 100 | 120 | 110 | 130 | 120 | 130 | 150 | 120 | 130 | 120 | 150 | 1480
CV(GAR) | 6528.8013 | 6523.441 | 6602.1856 | 6481.0855 | 6487.5274 | 6515.5714 | 6445.0323 | 6472.1448 | 6412.4032 | 6476.7335 | 6460.6228 | 6423.2952 | 6482.812
Sul < 2.0 | 1.8419 | 2.1454 | 1.7213 | 1.772 | 1.7758 | 2.0871 | 1.8138 | 1.8287 | 1.8482 | 1.8968 | 1.819 | 1.9905 | 1.8762
ASH < 5.0 | 6.7257 | 7.6729 | 55.9656 | 5.9371 | 5.2918 | 7.3265 | 5.9375 | 5.9832 | 6.008 | 6.0191 | 6.0931 | 5.979 | 10.2546
IM | 7.2396 | 7.118 | 6.7065 | 6.8833 | 6.7129 | 6.6877 | 6.6455 | 6.3583 | 6.7264 | 6.4663 | 6.2063 | 6.1537 | 6.6258
TM | 11.8026 | 10.6165 | 10.6667 | 11.5389 | 11.4782 | 10.0232 | 11.715 | 11.1861 | 11.926 | 11.4844 | 11.0808 | 11.4168 | 11.2522
TCM.LCV.MS.HA | 7 | 5 | 8 | 7 | 10 | 15 | 15 | 20 | 10 | 8 | 7 | 8 | 120
CV(GAR) | 3581.7631 | 3599.0009 | 4341.3047 | 3587.2263 | 3651.2002 | 5641.0449 | 5567.1958 | 5442.6121 | 5422.5222 | 5471.7948 | 5388.109 | 5438.9485 | 4963.5346
Sul < 1.2 | 1.16 | 1.15 | 1.44 | 0.51 | 0.5 | 1.45 | 1.5217 | 1.5933 | 1.6133 | 1.5833 | 1.5533 | 1.6133 | 1.3582
ASH < 5.0 | 13.6 | 13.18 | 12.69 | 14.445 | 14.2 | 6.835 | 8.9933 | 11.1517 | 11.1417 | 11.0117 | 11.1717 | 11.9817 | 11.1647
IM | 7.41 | 7.54 | 7.16 | 6.52 | 6.43 | 6.09 | 6.1267 | 6.1633 | 6.1633 | 6.1633 | 6.1633 | 6.1633 | 6.3891
TM | 13.89 | 14.11 | 14.412 | 13.208 | 13.588 | 13.532 | 13.3947 | 14.0533 | 14.0233 | 13.9833 | 14.4533 | 14.0533 | 13.8507
EBH.HCV.LS | 56.6 | 56.9 | 56.1 | 55.6 | 56.5 | 55.8 | 56 | 55.2 | 55.6 | 56.2 | 55.8 | 55.2 | 671.5
CV(GAR) | 6322 | 6322 | 6322 | 6322 | 6322 | 6322 | 6322 | 6322 | 6322 | 6322 | 6322 | 6322 | 6322
Sul < 1 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6
ASH | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7
IM | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12
TM | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14
MBL.MCV.MS | 82.5 | 82.5 | 82.5 | 82.5 | 82.5 | 82.5 | 82.5 | 82.5 | 90 | 90 | 82.5 | 82.5 | 1005
CV(GAR) | 5400 | 5400 | 5400 | 5400 | 5400 | 5400 | 5400 | 5400 | 5400 | 5400 | 5400 | 5400 | 5400
Sul < 1.2 | [12 empty] | 1 | bar: Jan to Dec
ASH | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6
IM | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15
TM | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24
BEK | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Total
OB Removal (KBcm) | 7995 | 7084 | 7619 | 7232 | 7571 | 7593 | 8097 | 8330 | 7698 | 7482 | 6860 | 7389 | 90950 | Done
TRUST | 2085 | 1784 | 1974 | 1997 | 1991 | 1968 | 2132 | 2305 | 2063 | 2062 | 1755 | 1884 | 24000
PAMA | 4250 | 3810 | 4105 | 4235 | 4480 | 4475 | 4785 | 4825 | 4495 | 4420 | 4115 | 4455 | 52450
SNS | 1660 | 1490 | 1540 | 1000 | 1100 | 1150 | 1180 | 1200 | 1140 | 1000 | 990 | 1050 | 14500
ROM Production (Kton) | 684 | 658 | 685.5 | 564 | 663 | 712 | 745 | 752 | 704 | 627.5 | 589 | 616 | 8000
TRUST | 194 | 188 | 185.5 | 156 | 196 | 212 | 245 | 252 | 234 | 192.5 | 169 | 176 | 2400
PAMA | 360 | 350 | 375 | 335 | 380 | 415 | 375 | 400 | 370 | 350 | 340 | 350 | 4400
SNS | 130 | 120 | 125 | 73 | 87 | 85 | 125 | 100 | 100 | 85 | 80 | 90 | 1200
SR ROM | 11.6886 | 10.766 | 11.1145 | 12.8227 | 11.4193 | 10.6643 | 10.8685 | 11.0771 | 10.9347 | 11.9235 | 11.6469 | 11.9951 | 11.3688
SR FC | 11.4214 | 10.12 | 10.8843 | 11.1262 | 11.6477 | 11.6815 | 11.5671 | 11.7324 | 10.9971 | 11.3364 | 10.7188 | 11.5453 | 11.2284
FC Product (KTons) | 700 | 700 | 700 | 650 | 650 | 650 | 700 | 710 | 700 | 660 | 640 | 640 | 8100
BEK.HCV.LS | 400 | 480 | 480 | 465 | 465 | 460 | 500 | 490 | 480 | 460 | 440 | 440 | 5560
CV(GAR) | 6030.4358 | 5774.2277 | 5860.9708 | 5868.1864 | 5954.6027 | 5916.1255 | 5984.187 | 5944.3266 | 5921.0085 | 5916.7362 | 5898.291 | 5928.9325 | 5915.2264
TS | 0.53158 | 0.52889 | 0.5114 | 0.47877 | 0.51889 | 0.54684 | 0.6156 | 0.65164 | 0.57083 | 0.61028 | 0.68843 | 0.67517 | 0.5772
Ash | 4.5798 | 4.3819 | 4.7059 | 4.7159 | 4.47 | 4.6727 | 5.1675 | 5.2807 | 5.3764 | 5.2082 | 4.9555 | 5.0376 | 4.8848
IM | 11.5325 | 12.1617 | 11.7688 | 10.9822 | 11.9963 | 11.3734 | 10.8514 | 11.2599 | 11.1283 | 11.3129 | 11.8103 | 11.5197 | 11.4694
TM | 16.0731 | 18.3447 | 16.1139 | 15.2818 | 15.685 | 15.0345 | 13.9867 | 14.31 | 14.2913 | 14.4636 | 14.865 | 14.5485 | 15.2419
BEK.HCV.HS | 300 | 220 | 220 | 185 | 185 | 190 | 200 | 220 | 220 | 200 | 200 | 200 | 2540
CV(GAR) | 5978.3055 | 5788.4874 | 5780.4749 | 5757.1239 | 5689.0306 | 5723.4269 | 5710.0663 | 5767.3036 | 5816.7184 | 5783.944 | 5714.3882 | 5899.7671 | 5792.8232
TS | 1.787 | 1.8051 | 1.7535 | 1.753 | 1.7123 | 1.7854 | 1.8239 | 1.742 | 1.7014 | 1.7606 | 1.7678 | 1.7233 | 1.7606
Ash | 4.7301 | 5.5271 | 5.5458 | 5.7433 | 6.1338 | 6.4532 | 6.4437 | 6.2121 | 5.7608 | 5.8895 | 6.1089 | 5.112 | 5.7572
IM | 11.0894 | 10.939 | 11.1033 | 10.7531 | 10.9318 | 10.5429 | 10.9263 | 10.5327 | 10.5196 | 10.609 | 10.4098 | 10.3006 | 10.7369
TM | 14.7767 | 14.7885 | 14.9686 | 14.6226 | 15.0392 | 14.4524 | 14.7662 | 14.3018 | 14.2251 | 14.4043 | 14.4451 | 13.7474 | 14.5518
JBG | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Total
OB Removal (KBcm) | 103.007 | 93.07 | 98.059 | 280.6245 | 579.3785 | 448.889 | 536.383 | 575.345 | 590.094 | 632.103 | 557.72 | 543.935 | 5038.608 | Done
Contractor Pit UCE ext | 103.007 | 93.07 | 98.059 | 280.6245 | 579.3785 | 448.889 | 536.383 | 575.345 | 590.094 | 632.103 | 557.72 | 543.935 | 5038.608
ROM Production (Kton) | 0 | 0 | 0 | 0 | 20 | 37 | 51 | 60 | 70 | 75 | 68 | 67 | 448
Contractor Pit UCE ext | 0 | 0 | 0 | 0 | 20 | 37 | 51 | 60 | 70 | 75 | 68 | 67 | 448
SR ROM | 0 | 0 | 0 | 0 | 28.9689 | 12.1321 | 10.5173 | 9.5891 | 8.4299 | 8.428 | 8.2018 | 8.1184 | 11.2469
SR FC | 0 | 0 | 0 | 0 | 32.1877 | 12.8254 | 10.7277 | 9.9197 | 8.6779 | 8.7792 | 8.4503 | 8.2414 | 11.6365
JBG Coal Loading | 14.6 | 14.6 | 7.3 | 7.3 | 21.9 | 36.5 | 43.8 | 58.4 | 58.4 | 58.4 | 58.4 | 51.1 | 430.7
JBG FC Product (Kton) / JBG | 0 | 0 | 0 | 0 | 18 | 35 | 50 | 58 | 68 | 72 | 66 | 66 | 433
CV(GAR) | 0 | 0 | 0 | 0 | 4442.3525 | 4414.0197 | 4416.3842 | 4432.5862 | 4408.926 | 4423.0872 | 4453.786 | 4407.9045 | 4423.7946
TS | 0 | 0 | 0 | 0 | 0.38874 | 0.35403 | 0.38864 | 0.37486 | 0.36433 | 0.35476 | 0.35693 | 0.38386 | 0.36899
Ash | 0 | 0 | 0 | 0 | 4.3469 | 4.2775 | 4.5772 | 4.4107 | 4.3138 | 4.438 | 4.3733 | 4.6218 | 4.4323
IM | 0 | 0 | 0 | 0 | 17.434 | 17.2038 | 17.034 | 16.8716 | 16.9773 | 16.7251 | 16.9357 | 16.7621 | 16.9259
TM | 0 | 0 | 0 | 0 | 30.1867 | 30.2656 | 30.3349 | 30.2198 | 30.2331 | 30.2451 | 30.1783 | 30.2279 | 30.2366
GPK | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Total
OB Removal (KBcm) | 630 | 580 | 630 | 610 | 700 | 675 | 745 | 790 | 785 | 880 | 705 | 770 | 8500 | Done
ARKA | 630 | 580 | 630 | 610 | 700 | 675 | 745 | 790 | 785 | 880 | 705 | 770 | 8500
ROM Production (Kton) | 184 | 166 | 182 | 175 | 180 | 175 | 160 | 160 | 160 | 196 | 175 | 187 | 2100
ARKA | 119 | 108 | 118 | 114 | 131 | 127 | 125 | 124 | 126 | 139 | 114 | 122 | 1467
SLS | 65 | 58 | 64 | 61 | 49 | 48 | 35 | 36 | 34 | 57 | 61 | 65 | 633
SR ROM | 3.4239 | 3.494 | 3.4615 | 3.4857 | 3.8889 | 3.8571 | 4.6562 | 4.9375 | 4.9062 | 4.4898 | 4.0286 | 4.1176 | 4.0476
SR FC | 3.15 | 3.2222 | 3.3158 | 3.4857 | 3.8889 | 3.8571 | 8.2778 | 15.8 | 8.7222 | 4.1905 | 2.7115 | 3.08 | 4.1463
FC Production (Ktons) | 200 | 180 | 190 | 175 | 180 | 175 | 90 | 50 | 90 | 210 | 260 | 250 | 2050
CV(GAR) | 3597.7504 | 3594.5296 | 3663.6762 | 3731.5323 | 3747.0877 | 3753.0309 | 3709.9842 | 3710.8591 | 3754.9789 | 3802.469 | 3810.8052 | 3790.9104 | 3727.504
TS | 0.11569 | 0.11701 | 0.15581 | 0.15133 | 0.15302 | 0.14876 | 0.16964 | 0.1691 | 0.15833 | 0.16553 | 0.17248 | 0.16287 | 0.15227
Ash | 10.1457 | 10.2139 | 9.4792 | 8.2664 | 7.972 | 8.1087 | 9.7175 | 9.7409 | 8.5788 | 6.4456 | 5.4512 | 5.9086 | 7.9761
IM | 27.2738 | 27.292 | 26.9771 | 25.1243 | 25.0639 | 24.2542 | 31.6027 | 31.4781 | 27.5216 | 26.4417 | 28.9143 | 29.0422 | 27.2546
TM | 37.9185 | 37.923 | 38.043 | 37.9509 | 37.979 | 38.0738 | 37.7175 | 37.7338 | 37.8637 | 38.4165 | 39.0685 | 39.1676 | 38.2852
TIS | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Total
OB Removal (KBcm) | 767.6336 | 734.7931 | 815.1462 | 831.0273 | 859.4709 | 916.3581 | 1023.2017 | 1020.3858 | 1007.9939 | 961.3227 | 867.198 | 903.6556 | 10708.1867 | Done
Contractor | 767.6336 | 734.7931 | 815.1462 | 831.0273 | 859.4709 | 916.3581 | 1023.2017 | 1020.3858 | 1007.9939 | 961.3227 | 867.198 | 903.6556 | 10708.1867
ROM Production (Kton) | 40.6021 | 37.5931 | 41.6296 | 45.5535 | 50.2535 | 55.2541 | 61.4542 | 61.231 | 61.1144 | 55.8895 | 46.816 | 48.6088 | 605.9999
Contractor | 40.6021 | 37.5931 | 41.6296 | 45.5535 | 50.2535 | 55.2541 | 61.4542 | 61.231 | 61.1144 | 55.8895 | 46.816 | 48.6088 | 605.9999
SR ROM | 18.9063 | 19.5459 | 19.5809 | 18.2429 | 17.1027 | 16.5844 | 16.6498 | 16.6645 | 16.4936 | 17.2004 | 18.5235 | 18.5904 | 17.6703
SR FC | 23.9885 | 26.2426 | 20.3787 | 20.7757 | 17.1894 | 16.6611 | 17.0534 | 17.0064 | 17.9999 | 16.022 | 15.7672 | 16.4301 | 18.1188
FC Production (Ktons) | 32 | 28 | 40 | 40 | 50 | 55 | 60 | 60 | 56 | 60 | 55 | 55 | 591
CV(GAR) | 6898.8055 | 6898.8055 | 6898.8055 | 7061.2455 | 7061.2455 | 7061.2455 | 6892.9578 | 6892.9578 | 6930.9674 | 6803.0068 | 6804.9228 | 6822.1666 | 6914.9248
TS | 1.2251 | 1.1251 | 1.0112 | 0.95955 | 0.95955 | 0.91395 | 0.84903 | 0.85955 | 0.8749 | 1.0751 | 1.0129 | 1.0815 | 0.97968
Ash | 3.7895 | 3.7895 | 3.7895 | 3.6003 | 3.6003 | 3.6003 | 3.8711 | 3.8711 | 3.8711 | 3.7895 | 3.7895 | 3.7895 | 3.7674
TM | 8.7195 | 8.7195 | 8.7195 | 7.3393 | 7.3393 | 7.3393 | 9.7585 | 9.7585 | 9.7585 | 8.7195 | 8.7195 | 8.7195 | 8.6903
IM | 4.7164 | 4.7164 | 4.7164 | 4.4047 | 4.4047 | 4.4047 | 5.0329 | 5.0329 | 5.0329 | 4.7164 | 4.7164 | 4.7164 | 4.7342
NPR | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Total
OB Removal (KBcm) | 0 | 0 | 129 | 535 | 542 | 543 | 586 | 594 | 578 | 752 | 682 | 742.5 | 5683.5 | Done
Contractor | 0 | 0 | 129 | 535 | 542 | 543 | 586 | 594 | 578 | 752 | 682 | 742.5 | 5683.5
ROM Production (Kton) | 0 | 0 | 0 | 0 | 25 | 55 | 60 | 60 | 55 | 65 | 65 | 65 | 450
Contractor | 0 | 0 | 0 | 0 | 25 | 55 | 60 | 60 | 55 | 65 | 65 | 65 | 450
SR ROM | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 21.68 | 9.8727 | 9.7667 | 9.9 | 10.5091 | 11.5692 | 10.4923 | 11.4231 | 12.63
SR FC | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 31.8824 | 14.6757 | 14.65 | 14.85 | 15.6216 | 17.4884 | 15.8605 | 17.2674 | 18.945
FC Production (Ktons) | 0 | 0 | 0 | 0 | 17 | 37 | 40 | 40 | 37 | 43 | 43 | 43 | 300
CV(GAD) | 0 | 0 | 0 | 0 | 6479.8736 | 6587.4532 | 6598.4997 | 6640.8571 | 6546.9132 | 6622.5542 | 6577.0752 | 6514.6914 | 5016.4003
TS | 0 | 0 | 0 | 0 | 1.1963 | 1.2298 | 1.1899 | 1.1598 | 1.0431 | 1.0999 | 1.0172 | 0.99869 | 0.85231
Ash | 0 | 0 | 0 | 0 | 6.1898 | 6.1677 | 6.5217 | 6.2198 | 5.498 | 6.2002 | 5.4953 | 5.9413 | 4.606
IM |  |  |  | 0 | 8.626 | 7.4 | 6.7387 | 6.6266 | 8.5113 | 6.8655 | 8.0495 | 8.45 | 5.8143
TM | 0 | 0 | 0 | 0 | 14.7805 | 14.414 | 14.3683 | 14.3998 | 15.0003 | 14.3847 | 15.0759 | 15.0952 | 11.202
| 21310.0888 | 19731.1654 | 20181.2283 | 21554.5665 | 22895.3249 | 22433.1263 | 128105.5002
| 1646.1021 | 1609.0931 | 1663.6296 | 1577.0535 | 1760.7535 | 1886.7541 | 10143.386
| 1690.75 | 1679.75 | 1729.75 | 1673.75 | 1756.75 | 1808.75 | 10339.5

## Outlook 6+6
ITM outlook 2025 (6+6)
| Act. | Act. | Act. | Act. | Act. | Act. | Out. | Out. | Out. | Out. | Out. | Out. | Out.
IMM | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Total | Budget 2025
OB Removal (KBcm) | 6763.0376 | 7421.6153 | 6667.0223 | 6530.8426 | 7716.6778 | 7595.242 | 8982.5413 | 8828.7539 | 8894.6901 | 8984.4938 | 8557.0874 | 8253.8722 | 95195.8761 | 94714.4782 | 100.5%
PAMA (WB) | 2244.6941 | 2827.069 | 2295.7418 | 2096.5402 | 2379.9843 | 2441.293 | 2684.5774 | 2586.0616 | 2605.3533 | 2792.096 | 2669.408 | 2582.3384 | 30205.1571 | 33532.659
PAMA (EB) | 4518.3435 | 4594.5463 | 4371.2805 | 4434.3024 | 5336.6935 | 5153.949 | 6297.9639 | 6242.6923 | 6289.3368 | 6192.3978 | 5887.6794 | 5671.5338 | 64990.719 | 61181.8192
ROM Production (Kton) | 542.8336 | 554.1195 | 482.7867 | 444.512 | 639.8002 | 581.9161 | 635.3145 | 660 | 650 | 650 | 650 | 581.2173 | 7072.5 | 6950 | 101.8%
PAMA (WB) | 158.4259 | 192.5857 | 141.1236 | 88.5606 | 157.3174 | 130.1721 | 115.1302 | 130 | 130 | 130 | 130 | 125 | 1628.3154 | 1862.5
PAMA (EB) | 384.4077 | 361.5338 | 341.6631 | 355.9514 | 482.4828 | 451.744 | 520.1844 | 530 | 520 | 520 | 520 | 456.2173 | 5444.1846 | 5087.5
Fine Coal (WB) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SR ROM Total | 12.4588 | 13.3935 | 13.8095 | 14.6922 | 12.0611 | 13.0521 | 14.1387 | 13.3769 | 13.6841 | 13.8223 | 13.1647 | 14.201 | 13.46 | 13.628
FC Product (Kton) | 612.6829 | 584.9149 | 501.0107 | 479.3049 | 587.8985 | 588.8116 | 625.75 | 664.25 | 672.75 | 632 | 632 | 553.6264 | 7135 | 7100
PAMA (WB) | 203.8423 | 213.1594 | 151.0762 | 100.5344 | 127.3543 | 132.8129 | 175 | 160 | 130 | 115 | 115 | 106.2204 | 1730 | 1862.5
PAMA (EB) | 408.8406 | 371.7556 | 349.9345 | 378.5787 | 460.5346 | 455.9987 | 446.5 | 500 | 538.5 | 504.25 | 504.25 | 434.656 | 5353.7986 | 5110
Fine Coal | 0 | 0 | 0 | 0.19187 | 0.0095 | 0 | 4.25 | 4.25 | 4.25 | 12.75 | 12.75 | 12.75 | 51.2014 | 127.5
SR FC Total | 11.0384 | 12.6884 | 13.3071 | 13.6257 | 13.1259 | 12.8993 | 14.3548 | 13.2913 | 13.2214 | 14.216 | 13.5397 | 14.9087 | 13.3421 | 13.3401
IMM-WB.HCV.LS | 146.1825 | 147.4608 | 104.9995 | 70.1282 | 84.5309 | 85.3152 | 110 | 82.533 | 60.3373 | 65.6223 | 60.8164 | 46.8 | 1064.7261 | 1228.8032
CV(GAR) | 6193.9879 | 6105.8162 | 6211.2744 | 6152.0829 | 6133.0399 | 6095.5899 | 5925.7694 | 6154.0269 | 6337.0595 | 6300.2368 | 6181.488 | 6258.309 | 6153.9592 | 6169.7769
TS | 0.61678 | 0.68122 | 0.59906 | 0.64019 | 0.77254 | 0.68499 | 0.96099 | 0.99075 | 0.81136 | 0.9035 | 0.8412 | 0.81643 | 0.75817 | 0.8108
Ash | 8.4183 | 8.3936 | 8.4815 | 7.987 | 8.4695 | 7.7685 | 9.6265 | 8.3293 | 8.6379 | 8.9847 | 8.7769 | 8.2 | 8.5209 | 8.3746
Moist | 8.6372 | 9.4242 | 8.7142 | 9.2339 | 8.7193 | 9.902 | 8.8242 | 7.8617 | 7.2805 | 7.2694 | 7.2517 | 7.1513 | 8.5545 | 8.0403
TM | 11.4895 | 12.3252 | 11.1339 | 12.344 | 12.3701 | 12.7314 | 13.5133 | 12.8821 | 12.3059 | 12.2948 | 12.2771 | 12.1766 | 12.284 | 13.0657
IMM-WB.HCV.HS | 57.6598 | 65.6986 | 46.0767 | 30.4062 | 42.8234 | 47.4977 | 65 | 77.467 | 69.6627 | 49.3777 | 54.1836 | 59.4204 | 665.2739 | 633.6968
CV(GAR) | 5947.3932 | 5939.4465 | 6026.7648 | 5928.2234 | 6043.0525 | 6015.1688 | 5986.6305 | 5963.8688 | 5931.2924 | 5803.0189 | 5831.9498 | 5854.6471 | 5937.8903 | 5965.7827
TS | 1.9789 | 2.2887 | 2.171 | 1.9301 | 2.0258 | 2.5172 | 2.549 | 2.6091 | 2.7874 | 2.8222 | 2.7372 | 2.5772 | 2.4536 | 2.579
Ash | 12.3989 | 11.629 | 11.3803 | 12.1525 | 11.4907 | 11.721 | 11.7837 | 12.597 | 14.2562 | 15.9894 | 15.8505 | 16.1381 | 13.1732 | 13.9606
Moist | 7.8249 | 7.5595 | 6.9977 | 7.2613 | 7.0928 | 7.1803 | 7.6688 | 7.625 | 6.9692 | 7.373 | 7.2666 | 6.9805 | 7.34 | 6.744
TM | 10.9111 | 11.827 | 11.262 | 11.6423 | 10.9592 | 10.8715 | 12.4771 | 12.6458 | 11.9946 | 12.3984 | 12.292 | 12.0059 | 11.8486 | 11.7694
IMM-EB.MCV.LS | 4.1512 | 4.8753 | 8.9721 | 7.4826 | 9.8667 | 5.2659 | 0 | 0 | 0 | 0 | 0 | 0 | 40.6138 | 13.6399
CV(GAR) | 5768.2424 | 5970.6107 | 5842.9196 | 6060.3315 | 5981.1886 | 5851.139 | 0 | 0 | 0 | 0 | 0 | 0 | 5925.3273 | 5822.4314
TS | 0.90471 | 0.97326 | 0.8997 | 0.91618 | 0.86187 | 1.0314 | 0 | 0 | 0 | 0 | 0 | 0 | 0.91996 | 0.90072
Ash | 8.498 | 6.4547 | 6.9734 | 5.5177 | 5.7561 | 6.6075 | 0 | 0 | 0 | 0 | 0 | 0 | 6.4556 | 8.5978
Moist | 10.8615 | 11.3343 | 10.9152 | 11.1195 | 11.7179 | 11.4638 | 0 | 0 | 0 | 0 | 0 | 0 | 11.2638 | 11.3544
TM | 14.3085 | 13.9608 | 14.8854 | 13.9345 | 14.5185 | 15.4912 | 0 | 0 | 0 | 0 | 0 | 0 | 14.5297 | 16.3544
IMM-EB.MCV.MS | 16.3857 | 4.2319 | 27.4815 | 41.3212 | 24.2579 | 32.4906 | 35 | 30.4675 | 80.152 | 88.5288 | 72.5116 | 60.9485 | 513.7772 | 422.7155
CV(GAR) | 6095.6967 | 5702.0802 | 5950.0061 | 5974.4204 | 6089.8148 | 6004.3095 | 5920.2903 | 6012.8395 | 6017.1851 | 5997.8717 | 6036.7778 | 6034.8958 | 6007.3557 | 6013.6725
TS | 1.5214 | 1.2568 | 1.4098 | 1.484 | 1.5036 | 1.4015 | 1.5626 | 1.6135 | 1.5928 | 1.5671 | 1.5972 | 1.5769 | 1.5464 | 1.5595
Ash | 5.1476 | 7.9573 | 6.2815 | 5.8971 | 5.4007 | 5.6631 | 6.9484 | 5.7416 | 5.4286 | 5.4882 | 5.2386 | 5.2612 | 5.623 | 5.3287
Moist | 11.5254 | 13.0173 | 11.4442 | 12.1489 | 11.2413 | 12.0093 | 10.7379 | 10.5057 | 10.289 | 10.2528 | 10.1536 | 9.852 | 10.6823 | 10.2792
TM | 13.6454 | 15.0827 | 14.2922 | 14.1446 | 13.5812 | 14.3611 | 15.7324 | 15.5057 | 15.289 | 15.2528 | 15.1536 | 14.852 | 14.9161 | 15.2792
IMM-EB.MCV.HS | 388.3038 | 362.6484 | 313.481 | 329.7748 | 426.41 | 418.2421 | 411.5 | 469.5325 | 458.348 | 415.7212 | 431.7384 | 373.7074 | 4799.4077 | 4673.6446
CV(GAR) | 5993.4453 | 6000.7559 | 5998.3259 | 5980.6624 | 6016.1816 | 6037.4357 | 5851.8828 | 5882.2518 | 5920.8888 | 5906.9496 | 5933.0041 | 5902.3215 | 5949.3221 | 5914.4155
TS | 2.2774 | 2.2808 | 2.3122 | 2.3366 | 2.2917 | 2.3283 | 2.4874 | 2.5095 | 2.4359 | 2.4708 | 2.345 | 2.4542 | 2.3821 | 2.4107
Ash | 5.9664 | 5.886 | 6.2337 | 5.9769 | 5.734 | 5.8093 | 6.5739 | 6.135 | 5.6629 | 5.7751 | 5.7115 | 5.724 | 5.9254 | 5.72
Moist | 11.4322 | 11.4905 | 11.1144 | 11.4873 | 11.5079 | 11.274 | 10.8051 | 10.5072 | 10.4484 | 10.4839 | 10.4887 | 10.5794 | 10.9409 | 10.5582
TM | 13.742 | 13.586 | 13.4706 | 13.7887 | 13.7274 | 13.4627 | 15.6671 | 15.5072 | 15.4484 | 15.4839 | 15.4887 | 15.5794 | 14.6418 | 15.5582
Fine Coal | 0 | 0 | 0 | 0.19187 | 0.0095 | 0 | 4.25 | 4.25 | 4.25 | 12.75 | 12.75 | 12.75 | 51.2014 | 127.5
CV(GAR) | 0 | 0 | 0 | 3966.2693 | 4270.5018 | 0 | 3146.0674 | 3146.0674 | 3146.0674 | 3146.0674 | 3146.0674 | 3146.0674 | 3149.3496 | 3146.0674
TS | 0 | 0 | 0 | 0.95 | 1.2 | 0 | 2 | 2 | 2 | 2 | 2 | 2 | 1.9959 | 2
Ash | 0 | 0 | 0 | 24.4 | 21.1 | 0 | 40 | 40 | 40 | 40 | 40 | 40 | 39.938 | 40
Moist | 0 | 0 | 0 | 12 | 12.38 | 0 | 11 | 11 | 11 | 11 | 11 | 11 | 11.004 | 11
TM | 0 | 0 | 0 | 22.9 | 20.37 | 0 | 20 | 20 | 20 | 20 | 20 | 20 | 20.0109 | 20
TCM | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Total | Budget 2025
OB Removal (KBcm) | 3736.1074 | 3365.8927 | 3574.4767 | 2859.5105 | 3323.9622 | 3270.3635 | 4685 | 4783 | 4966 | 4167.3759 | 3907 | 4261.3111 | 46900 | 51650 | 90.8%
PAMA | 1350.2909 | 1037.3669 | 1287.9434 | 1083.7445 | 1489.2826 | 1746.4091 | 2530 | 2583 | 2946 | 2342 | 2212 | 2488 | 23096.0375 | 24400
MAP | 1111.151 | 916.3988 | 928.1686 | 747.5562 | 747.6521 | 820.0399 | 1000 | 1050 | 950 | 900.3759 | 860 | 931.6974 | 10963.0399 | 11000
PJPN | 1274.6654 | 1412.127 | 1358.3647 | 1028.2098 | 1087.0275 | 703.9144 | 1155 | 1150 | 1070 | 925 | 835 | 841.6138 | 12840.9226 | 16250
ROM Production (Kton) | 197.2844 | 200.7536 | 248.6888 | 198.2023 | 259.7856 | 238.8222 | 275 | 365 | 390 | 400 | 362 | 329.4631 | 3465 | 3300.387 | 105%
PAMA | 128.1928 | 118.2278 | 164.3541 | 128.7862 | 159.7519 | 139.0814 | 175 | 175 | 190 | 200 | 182 | 178 | 1938.3942 | 2130
MAP | 31.1921 | 36.3972 | 40.6248 | 29.6651 | 37.0206 | 39.3866 | 50 | 60 | 60 | 60 | 50 | 46 | 540.2862 | 550
PJPN | 37.8996 | 46.1285 | 39.3617 | 35.6014 | 60.0186 | 60.3542 | 50 | 130 | 140 | 140 | 130 | 105.4631 | 974.8271 | 620.387
SNS | 0 | 0 | 4.3483 | 4.1496 | 2.9946 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11.4925
SR ROM with void | 18.9377 | 16.7663 | 14.3733 | 14.4272 | 12.795 | 13.6937 | 17.0364 | 13.1041 | 12.7333 | 10.4184 | 10.7928 | 12.9341 | 13.5354 | 15.6497
FC Product CP (Kton) | 236.9432 | 220.6496 | 280.3218 | 200.3136 | 238.3063 | 285.541 | 285 | 285 | 295 | 370 | 365 | 338 | 3400.0756 | 3230
TCM.HCV.LS | 162.6798 | 131.4776 | 143.7703 | 110.8186 | 152.7335 | 123.5704 | 150 | 130 | 140 | 210 | 210 | 205 | 1870.0501 | 1630
TCM.HCV.HS | 74.2634 | 89.172 | 136.5515 | 89.495 | 85.5729 | 161.9707 | 135 | 155 | 155 | 160 | 155 | 133 | 1530.0255 | 1480
TCM.HCV.MS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 120
FC Product 3rd party (Kton) | 57.1257 | 53.4973 | 58.8103 | 75.2631 | 125.3982 | 94.7562 | 83.1464 | 58.1837 | 37.1395 | 68.7549 | 52.9974 | 55 | 820.0726 | 1676.5
EBH.HCV.LS | 7.1098 | 40.5275 | 51.9524 | 50.1264 | 109.9789 | 87.8438 | 83.1464 | 58.1837 | 37.1395 | 60.3145 | 52.9974 | 45 | 684.3203 | 671.5
MBL.MCV.MS | 50.0159 | 12.9697 | 6.8579 | 25.1368 | 15.4192 | 6.9123 | 0 | 0 | 0 | 8.4404 | 0 | 10 | 135.7523 | 1005
SR FC | 15.7679 | 15.2545 | 12.7513 | 14.2752 | 13.9483 | 11.4532 | 16.4386 | 16.7825 | 16.8339 | 11.2632 | 10.7041 | 12.6074 | 13.7938 | 15.9907
TCM.HCV.LS | 162.6798 | 131.4776 | 143.7703 | 110.8186 | 152.7335 | 123.5704 | 150 | 130 | 140 | 210 | 210 | 205 | 1870.0501 | 1630
CV(GAR) | 6732.4288 | 6572.6205 | 6596.2445 | 6621.4349 | 6741.0993 | 6692.9195 | 6657.8158 | 6624.8329 | 6659.8708 | 6614.0604 | 6499.335 | 6509.8578 | 6619.4798 | 6355.6513
Sul < 0.7 | 0.62137 | 0.63583 | 0.77706 | 0.69371 | 0.7093 | 0.60986 | 0.74439 | 0.74419 | 0.72939 | 0.7313 | 0.73394 | 0.72252 | 0.70763 | 0.60341
ASH < 5.0 | 3.4667 | 4.5743 | 4.3675 | 4.7704 | 3.7542 | 3.8464 | 4.5216 | 4.8391 | 4.7494 | 4.5482 | 5.136 | 4.9914 | 4.4918 | 4.8411
IM | 6.8418 | 7.5669 | 6.8218 | 6.8812 | 6.8542 | 6.8497 | 6.9396 | 7.1349 | 7.0913 | 6.91 | 7.4196 | 7.1056 | 7.0435 | 7.3863
TM | 11.1733 | 12.0917 | 12.4658 | 11.343 | 11.0393 | 11.0674 | 10.1907 | 10.1318 | 10.1046 | 11.193 | 11.4006 | 11.7903 | 11.1935 | 13.8465
TCM.HCV.HS | 74.2634 | 89.172 | 136.5515 | 89.495 | 85.5729 | 161.9707 | 135 | 155 | 155 | 160 | 155 | 133 | 1530.0255 | 1480
CV(GAR) | 6697.6812 | 6682.5379 | 6375.2052 | 6514.9911 | 6575.1364 | 6545.7939 | 6451.6436 | 6460.3591 | 6447.9254 | 6407.7499 | 6411.4462 | 6345.2982 | 6473.3992 | 6482.812
Sul < 2.0 | 1.6302 | 1.4797 | 1.6016 | 1.6141 | 1.5958 | 1.6294 | 1.7793 | 1.8444 | 1.7624 | 1.679 | 1.754 | 1.859 | 1.7017 | 1.8762
ASH < 5.0 | 2.9843 | 3.6683 | 5.3381 | 5.334 | 5.1498 | 6.3739 | 6.1377 | 6.7338 | 6.1344 | 5.7549 | 5.5483 | 6.4676 | 5.6811 | 10.2546
IM | 6.3755 | 6.3149 | 6.5134 | 6.5208 | 6.2533 | 6.2533 | 6.1216 | 6.4294 | 6.3968 | 6.2418 | 6.0833 | 5.7327 | 6.2588 | 6.6258
TM | 11.045 | 10.871 | 11.7658 | 12.1103 | 11.2862 | 10.0871 | 10.7312 | 10.8891 | 10.7194 | 11.0741 | 11.3127 | 11.8047 | 11.0933 | 11.2522
EBH.HCV.LS | 7.1098 | 40.5275 | 51.9524 | 50.1264 | 109.9789 | 87.8438 | 83.1464 | 58.1837 | 37.1395 | 60.3145 | 52.9974 | 45 | 684.3203 | 671.5
CV(GAR) | 6322 | 6322 | 6322 | 6322 | 6322 | 6322 | 6322 | 6322 | 6322 | 6322 | 6322 | 6322 | 6322 | 6322
Sul < 1.2 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6
ASH < 5.0 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7
IM | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12
TM | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14
MBL.MCV.MS | 50.0159 | 12.9697 | 6.8579 | 25.1368 | 15.4192 | 6.9123 | 0 | 0 | 0 | 8.4404 | 0 | 10 | 135.7523 | 1005
CV(GAR) | 5400 | 5400 | 5400 | 5400 | 5400 | 5400 | 5400 | 5400 | 5400 | 5400 | 5400 | 5400 | 5400 | 5400
Sul < 1.2 | [12 empty] | 1 | 1 | bar: Jan to Dec
ASH < 5.0 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6
IM | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15
TM | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24
BEK | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Total | Budget 2025
OB Removal (KBcm) | 7740.8131 | 6674.4387 | 7334.0009 | 6431.8589 | 7155.0963 | 4209.2759 | 3809 | 8880 | 8735 | 8556 | 8467 | 8535.516 | 86527.9999 | 90950 | 95.14%
TRUST | 1657.8774 | 1407.4207 | 1552.9195 | 1926.5002 | 1498.8408 | 509.6157 | 399 | 2211 | 2245 | 2135 | 2122 | 2165.8254 | 19830.9997 | 24000
PAMA | 4075.4608 | 3313.976 | 3758.0614 | 3301.263 | 4117.1198 | 2842.4129 | 2750 | 5289 | 5295 | 5285 | 5285 | 5292.7059 | 50604.9999 | 52450
SNS | 2007.4749 | 1953.042 | 2023.02 | 1204.0958 | 1539.1357 | 857.2473 | 660 | 1380 | 1195 | 1136 | 1060 | 1076.9847 | 16092.0003 | 14500
ROM Production (Kton) | 737.0865 | 743.2998 | 904.2769 | 705.0239 | 817.6832 | 480.0651 | 325 | 795 | 732 | 655 | 613 | 587.5646 | 8095 | 8000 | 101.2%
TRUST | 144.008 | 216.6716 | 291.6349 | 238.8466 | 276.4787 | 109.4615 | 60 | 215 | 209 | 185 | 165 | 138.8988 | 2250 | 2400
PAMA | 410.2388 | 366.3467 | 418.9281 | 215.2214 | 277.1813 | 240.8111 | 180 | 500 | 463 | 440 | 420 | 418.2724 | 4350 | 4400
SNS | 182.8397 | 160.2815 | 193.7138 | 250.9558 | 264.0233 | 129.7925 | 85 | 80 | 60 | 30 | 28 | 30.3934 | 1495 | 1200
SR ROM | 10.5019 | 8.9795 | 8.1103 | 9.1229 | 8.7504 | 8.7681 | 11.72 | 11.1698 | 11.9331 | 13.0626 | 13.8124 | 14.5269 | 10.6891 | 11.3688
SR FC | 10.3695 | 9.7157 | 10.3458 | 9.5166 | 8.8291 | 6.999 | 9.4751 | 12.3333 | 12.1319 | 12.2229 | 12.0957 | 14.4676 | 10.7328 | 11.2284
FC Product (KTons) | 746.5015 | 686.976 | 708.8848 | 675.859 | 810.3971 | 601.4072 | 402 | 720 | 720 | 700 | 700 | 589.9744 | 8062 | 8100
BEK.HCV.LS | 625.8496 | 567.9555 | 547.067 | 503.7176 | 489.6375 | 461.795 | 302 | 510 | 510 | 470 | 480 | 403.9776 | 5872 | 5560
CV(GAR) | 6097.4967 | 6119.1856 | 6220.8649 | 6062.7439 | 6140.1294 | 6191.6877 | 6281 | 6269.0811 | 6201.9085 | 6161.6015 | 6136.9934 | 6137.6232 | 6163.5983 | 5915.2264
TS | 0.54477 | 0.56824 | 0.47738 | 0.62875 | 0.59201 | 0.56239 | 0.52861 | 0.52031 | 0.52863 | 0.56474 | 0.54742 | 0.5172 | 0.54885 | 0.5772
Ash | 4.6247 | 4.6318 | 3.9165 | 4.3087 | 4.0161 | 3.8465 | 3.34 | 3.6587 | 3.6632 | 3.7697 | 3.9356 | 3.92 | 4.0136 | 4.8848
IM | 10.4598 | 10.574 | 10.5752 | 11.1112 | 11.0859 | 10.9708 | 10.88 | 10.8131 | 10.9926 | 10.9796 | 11.0121 | 11.0808 | 10.8579 | 11.4694
TM | 16.139 | 16.0366 | 15.5041 | 16.8779 | 16.1084 | 15.2831 | 14.64 | 14.5937 | 15.3187 | 15.5456 | 15.709 | 15.7519 | 15.6717 | 15.2419
BEK.HCV.HS | 120.6519 | 119.0205 | 161.8178 | 172.1413 | 320.7595 | 139.6122 | 100 | 210 | 210 | 230 | 220 | 185.9967 | 2190 | 2540
CV(GAR) | 6099.469 | 6066.5599 | 6046.9118 | 6012.6397 | 6083.696 | 6162.7207 | 6185 | 6154.0172 | 6129.8604 | 6090.9755 | 6085.8513 | 6077.9452 | 6096.6565 | 5792.8232
TS | 1.9961 | 1.995 | 1.9374 | 1.9318 | 1.8618 | 1.9218 | 1.87 | 1.9046 | 1.9023 | 1.9369 | 1.9274 | 1.8978 | 1.9172 | 1.7606
Ash | 4.8307 | 4.7802 | 6.309 | 6.1221 | 6.1221 | 5.6906 | 5.19 | 5.4518 | 5.4711 | 5.5443 | 5.5385 | 5.5696 | 5.6288 | 5.7572
IM | 10.559 | 11.003 | 10.0774 | 10.2964 | 10.2377 | 9.8856 | 10.03 | 10.1902 | 10.2066 | 10.2618 | 10.2586 | 10.3149 | 10.2615 | 10.7369
TM | 15.5418 | 16.161 | 15.2644 | 15.4267 | 15.2786 | 14.3926 | 13.81 | 14.0034 | 14.348 | 14.8677 | 14.9492 | 15.0392 | 14.92 | 14.5518
JBG | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Total | Budget 2025
OB Removal (KBcm) | 0 | 0 | 0 | 0 | 0 | 47.865 | 104.35 | 343 | 394.034 | 442.034 | 428.034 | 359.683 | 2119 | 5038.608 | 42.06%
Pit UCE-Extend | 0 | 0 | 0 | 0 | 0 | 47.865 | 104.35 | 343 | 394.034 | 442.034 | 428.034 | 359.683 | 2119 | 5038.608
ROM Production (Kton) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26 | 59 | 57 | 58 | 200 | 448 | 44.64%
Pit UCE-Extend | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26 | 59 | 57 | 58 | 200 | 448
SR ROM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15.1552 | 7.4921 | 7.5094 | 6.2014 | 10.595 | 11.2469
SR FC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17.9106 | 7.8935 | 7.7824 | 5.9947 | 10.9793 | 11.6365
JBG Coal Loading | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7.5 | 36.7 | 68 | 44.2 | 66.1 | 222.5 | 430.7
JBG FC Product (Kton) / JBG | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22 | 56 | 55 | 60 | 193 | 433
CV(GAR) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4432.8755 | 4380.2803 | 4389.5884 | 4258.1278 | 4350.9533 | 4423.7946
TS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.4259 | 0.39214 | 0.38833 | 0.32217 | 0.37315 | 0.36899
Ash | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.8165 | 5.5125 | 5.082 | 5.3704 | 5.2663 | 4.4323
IM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16.9178 | 16.5652 | 16.4508 | 15.5682 | 16.2628 | 16.9259
TM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29.7121 | 30.3939 | 30.2747 | 29.4248 | 29.9809 | 30.2366
GPK | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Total | Budget 2025
OB Removal (KBcm) | 534.7729 | 568.3212 | 598.8463 | 615.7375 | 586.9521 | 712.2887 | 785 | 985 | 975 | 875 | 730 | 783.0812 | 8750 | 8500 | 102.9%
ARKA | 534.7729 | 568.3212 | 598.8463 | 615.7375 | 586.9521 | 712.2887 | 785 | 985 | 975 | 875 | 730 | 783.0812 | 8750 | 8500
ROM Production (Kton) | 202.9475 | 206.0717 | 193.2873 | 202.809 | 197.4591 | 174.3256 | 160 | 160 | 160 | 210 | 210 | 223.0999 | 2300 | 2100 | 109.5%
ARKA | 134.1946 | 121.7323 | 118.1879 | 126.2134 | 139.7455 | 118.8056 | 120 | 122.1422 | 116.0407 | 135.3947 | 135.3947 | 143.8408 | 1531.6923 | 1467
SLS | Jan: 43.9337; Feb: 48.0318; Mar: 42.7186; Apr: 42.4366; May: 20.4725; Jun: 15.5157 | 213.1088 | 633
IWJ | 24.8193 | 36.3076 | 32.3808 | 34.159 | 37.2411 | 40.0042 | 40 | 37.8578 | 43.9593 | 74.6053 | 74.6053 | 79.2592 | 555.1989
SR ROM | 2.635 | 2.7579 | 3.0982 | 3.036 | 2.9725 | 4.086 | 4.9062 | 6.1562 | 6.0938 | 4.1667 | 3.4762 | 3.51 | 3.8043 | 4.0476
SR FC | 1.992 | 3.2809 | 3.3142 | 2.9183 | 3.3721 | 4.2392 | 6.5417 | 9.85 | 6.9643 | 3.7234 | 3.0417 | 3.2628 | 3.8881 | 4.1463
FC Production (Ktons) | 268.4669 | 173.22 | 180.692 | 210.9939 | 174.0629 | 168.0224 | 120 | 100 | 140 | 235 | 240 | 240 | 2250.4582 | 2050
CV(GAR) | 3724.8809 | 3770.9785 | 3744.4236 | 3734.7558 | 3761.5128 | 3721.5417 | 3633.8297 | 3697.9789 | 3700.5466 | 3695.4461 | 3699.2232 | 3711.1078 | 3718.6649 | 3727.504
TS | 0.18179 | 0.1619 | 0.15271 | 0.18618 | 0.1849 | 0.20676 | 0.17969 | 0.16299 | 0.14662 | 0.13927 | 0.17224 | 0.1598 | 0.1695 | 0.15227
Ash | 9.388 | 9.0395 | 7.3286 | 7.4295 | 6.5335 | 7.3269 | 9.0546 | 8.3445 | 8.5258 | 8.3156 | 8.055 | 7.4461 | 8.0585 | 7.9761
IM | 21.0636 | 19.2873 | 18.6168 | 20.3173 | 19.9803 | 28.5884 | 19.6667 | 23.1677 | 23.3135 | 22.2251 | 23.4399 | 22.7405 | 21.851 | 27.2546
TM | 38.3472 | 38.2059 | 39.1151 | 39.3409 | 39.2721 | 38.778 | 39.1219 | 37.7729 | 37.7536 | 37.788 | 37.4985 | 37.9473 | 38.3822 | 38.2852
TIS | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Total | Budget 2025
OB Removal (KBcm) | 661.7443 | 587.5763 | 862.7898 | 732.0436 | 823.0024 | 817.6408 | 1097.953 | 1114.5398 | 1084.4996 | 1037.8284 | 926.0556 | 962.5132 | 10708.1867 | 10708.1867 | 100%
PJPN | 661.7443 | 587.5763 | 862.7898 | 732.0436 | 823.0024 | 817.6408 | 1097.953 | 1114.5398 | 1084.4996 | 1037.8284 | 926.0556 | 962.5132 | 10708.1867 | 10708.1867
ROM Production (Kton) | 36.6685 | 40.4296 | 41.2222 | 46.5491 | 48.0715 | 50.9448 | 60 | 60 | 60 | 56.1071 | 53.3813 | 52.6259 | 606 | 605.9999 | 100%
PJPN | 36.6685 | 40.4296 | 17.4196 | 19.5691 | 11.1527 | 16.2194 | 40 | 56 | 56 | 50.4881 | 45.9136 | 45.4222 | 435.2828 | 605.9999
ROM PIT I |  |  | 23.8026 | 26.98 | 36.9188 | 34.7254 | 20 | 4 | 4 | 5.6189 | 7.4676 | 7.2038 | 170.7172
SR ROM | 18.0466 | 14.5333 | 20.9302 | 15.7263 | 17.1204 | 16.0495 | 18.2992 | 18.5757 | 18.075 | 18.4973 | 17.3479 | 18.2897 | 17.6703 | 17.6703
SR FC | 69.6709 | 99.0111 | 36.5071 | 28.5403 | 19.1497 | 17.7074 | 36.5984 | 24.7676 | 21.69 | 15.9666 | 7.7087 | 7.5788 | 18.1188 | 18.1188
FC Production (Ktons) | 9.4982 | 5.9345 | 23.6335 | 25.6495 | 42.9772 | 46.1752 | 30 | 45 | 50 | 65 | 120.131 | 127.0011 | 591 | 591
TIS.HCV.HS | 9.4982 | 5.9345 | 23.6335 | 25.6495 | 42.9772 | 46.1752 | 30 | 45 | 50 | 65 | 120.131 | 127.0011 | 591 | 591
CV(GAR) | 6571.5022 | 6870.6132 | 6804.7599 | 6863.1036 | 6917.9129 | 6963.7003 | 7170.0218 | 7094.2278 | 7079.3938 | 7013.5739 | 7109.4116 | 7087.6034 | 7034.3402 | 6914.9248
TS | 1.7712 | 0.82 | 1.1687 | 1.2244 | 1.1903 | 1.2474 | 1.2556 | 1.2956 | 1.1556 | 1.2556 | 1.1826 | 1.2556 | 1.229 | 0.97968
Ash | 4.8216 | 2.98 | 3.3931 | 3.002 | 2.8749 | 2.7396 | 3.3955 | 3.4668 | 3.4561 | 3.4401 | 3.4396 | 3.3511 | 3.3229 | 3.7674
IM | 5.7298 | 6.25 | 6.5933 | 5.0621 | 5.506 | 5.0076 | 5.0174 | 4.9378 | 4.933 | 4.9389 | 4.8275 | 4.9063 | 5.0567 | 8.6903
TM | 10.0619 | 11.07 | 11.3529 | 10.8902 | 10.731 | 10.3596 | 7.8879 | 7.7789 | 7.7968 | 7.8224 | 7.8338 | 7.9709 | 8.6071 | 4.7342
NPR | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Total | Budget 2025
OB Removal (KBcm) | 0 | 0 | 0 | 11.937 | 62.275 | 304.289 | 577 | 587 | 568 | 694 | 619 | 676.499 | 4100 | 5683.5
PAMA | 0 | 0 | 0 | 11.937 | 62.275 | 304.289 | 577 | 587 | 568 | 694 | 619 | 676.499 | 4100 | 5683.5
ROM Production (Kton) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50 | 50 | 50 | 50 | 200 | 450
PAMA | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50 | 50 | 50 | 50 | 200 | 450
SR ROM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11.36 | 13.88 | 12.38 | 13.53 | 20.5 | 12.63
SR FC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19.8286 | 13.7556 | 9.6643 | 27.3333 | 18.945
FC Production (Ktons) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35 | 45 | 70 | 150 | 300
CV(GAR) | Jun: 0; Jul: 0; Aug: 0; Sep: 0; Oct: 5722.7136; Nov: 6001.7893; Dec: 5641.6638 | 5768.6131 | 5016.4003
TS | Jun: 0; Jul: 0; Aug: 0; Sep: 0; Oct: 1.3931; Nov: 1.214; Dec: 1.071 | 1.1891 | 0.85231
Ash | Jun: 0; Jul: 0; Aug: 0; Sep: 0; Oct: 5.7001; Nov: 5.4743; Dec: 7.2124 | 6.3381 | 4.606
IM | Jun: 0; Jul: 0; Aug: 0; Sep: 0; Oct: 13.9234; Nov: 11.903; Dec: 11.7364 | 12.2967 | 5.8143
TM | Jun: 0; Jul: 0; Aug: 0; Sep: 0; Oct: 18.5003; Nov: 16.5226; Dec: 16.8259 | 17.1256 | 11.202
| Q1 | Q1 | Q1 | Q2 | Q2 | Q2 | Q3 | Q3 | Q3 | Q4 | Q4 | Q4
| 19436.4753 | 18617.8442 | 19037.136 | 17181.9302 | 19667.9658 | 16956.965 | 110898.3164
| 1716.8206 | 1744.6741 | 1870.2619 | 1597.0963 | 1962.7996 | 1526.0738 | 10417.7262
| 1874.0927 | 1671.6951 | 1694.5429 | 1592.1209 | 1853.642 | 1689.9575 | 10376.051
Note on A8: Belfry Parulian Pandiangan: include high ash
Note on A86: Belfry Parulian Pandiangan: incoming coal volume (quality is not as actual but as range in contract)
Note on A92: Belfry Parulian Pandiangan: incoming coal volume (quality is not as actual but as range in contract)
Note on A100: Belfry Parulian Pandiangan: include Mud
Note on A125: Belfry Parulian Pandiangan: include Mud and sliding volume

## Outlook Quarterly 6+6
ITM outlook 2025 (4+8)
| Act. | Out. | Out. | Out. | Out.
IMM | Q1 | Q2 | Q3 | Q4 | Total | Budget 2025
OB Removal (KBcm) | 20851.6751 | 21842.7625 | 26705.9852 | 25795.4533 | 95195.8761 | 94714.4782 | 100.5%
PAMA (WB) | 7367.5048 | 6917.8176 | 7875.9923 | 8043.8424 | 30205.1571 | 33532.659
PAMA (EB) | 13484.1703 | 14924.9449 | 18829.9929 | 17751.6109 | 64990.719 | 61181.8192
ROM Production (Kton) | 1579.7398 | 1666.2283 | 1945.3145 | 1881.2173 | 7072.5 | 6950 | 101.8%
PAMA (WB) | 492.1351 | 376.0501 | 375.1302 | 385 | 1628.3154 | 1862.5
PAMA (EB) | 1087.6047 | 1290.1782 | 1570.1844 | 1496.2173 | 5444.1846 | 5087.5
Fine Coal (WB) | 0 | 0 | 0 | 0 | 0 | 0
SR ROM Total | 13.1994 | 13.1091 | 13.7284 | 13.7121 | 13.46 | 13.628
FC Product (Kton) | 1698.6086 | 1656.015 | 1962.75 | 1817.6264 | 7135 | 7100
PAMA (WB) | 568.0779 | 360.7017 | 465 | 336.2204 | 1730 | 1862.5
PAMA (EB) | 1130.5307 | 1295.1119 | 1485 | 1443.156 | 5353.7986 | 5110
Fine Coal | 0 | 0.20137 | 12.75 | 38.25 | 51.2014 | 127.5
SR FC Total | 12.2757 | 13.19 | 13.6064 | 14.1918 | 13.3421 | 13.3401
IMM-WB.HCV.LS | 398.6428 | 239.9743 | 252.8702 | 173.2387 | 1064.7261 | 1228.8032
CV(GAR) | 6165.9257 | 6125.2907 | 6098.4069 | 6247.2227 | 6153.9592 | 6169.7769
TS | 0.63595 | 0.70274 | 0.935 | 0.85811 | 0.75817 | 0.8108
Ash | 8.4258 | 8.0793 | 8.9672 | 8.6998 | 8.5209 | 8.3746
Moist | 8.9486 | 9.2901 | 8.1417 | 7.2313 | 8.5545 | 8.0403
TM | 11.705 | 12.4909 | 13.0192 | 12.2567 | 12.284 | 13.0657
IMM-WB.HCV.HS | 169.4351 | 120.7274 | 212.1298 | 162.9817 | 665.2739 | 633.6968
CV(GAR) | 5965.8964 | 6003.1615 | 5960.1454 | 5831.4598 | 5937.8903 | 5965.7827
TS | 2.1513 | 2.195 | 2.6492 | 2.7046 | 2.4536 | 2.579
Ash | 11.8233 | 11.748 | 12.8927 | 15.9974 | 13.1732 | 13.9606
Moist | 7.4971 | 7.1697 | 7.4231 | 7.1946 | 7.34 | 6.744
TM | 11.3616 | 11.0967 | 12.3803 | 12.2199 | 11.8486 | 11.7694
IMM-EB.MCV.LS | 17.9985 | 22.6152 | 0 | 0 | 40.6138 | 13.6399
CV(GAR) | 5860.2842 | 5977.0925 | 0 | 0 | 5925.3273 | 5822.4314
TS | 0.92078 | 0.91931 | 0 | 0 | 0.91996 | 0.90072
Ash | 7.1846 | 5.8755 | 0 | 0 | 6.4556 | 8.5978
Moist | 11.0164 | 11.4607 | 0 | 0 | 11.2638 | 11.3544
TM | 14.5019 | 14.5518 | 0 | 0 | 14.5297 | 16.3544
IMM-EB.MCV.MS | 48.099 | 98.0697 | 145.6194 | 221.989 | 513.7772 | 422.7155
CV(GAR) | 5977.8247 | 6012.8659 | 5992.987 | 6020.7454 | 6007.3557 | 6013.6725
TS | 1.4343 | 1.4615 | 1.5899 | 1.5796 | 1.5464 | 1.5595
Ash | 6.0427 | 5.6968 | 5.8594 | 5.3443 | 5.623 | 5.3287
Moist | 11.6102 | 11.8781 | 10.4422 | 10.1104 | 10.6823 | 10.2792
TM | 14.1414 | 14.077 | 15.4409 | 15.1104 | 14.9161 | 15.2792
IMM-EB.MCV.HS | 1064.4332 | 1174.427 | 1339.3806 | 1221.167 | 4799.4077 | 4673.6446
CV(GAR) | 5997.3733 | 6013.777 | 5886.1434 | 5914.7447 | 5949.3221 | 5914.4155
TS | 2.2888 | 2.3173 | 2.4775 | 2.4212 | 2.3821 | 2.4107
Ash | 6.0178 | 5.829 | 6.1083 | 5.737 | 5.9254 | 5.72
Moist | 11.3584 | 11.4189 | 10.5786 | 10.5148 | 10.9409 | 10.5582
TM | 13.6089 | 13.6503 | 15.5362 | 15.5148 | 14.6418 | 15.5582
Fine Coal | 0 | 0.20137 | 12.75 | 38.25 | 51.2014 | 127.5
CV(GAR) | 0 | 3980.6221 | 3146.0674 | 3146.0674 | 3149.3496 | 3146.0674
TS | 0 | 0.96179 | 2 | 2 | 1.9959 | 2
Ash | 0 | 24.2443 | 40 | 40 | 39.938 | 40
Moist | 0 | 12.0179 | 11 | 11 | 11.004 | 11
TM | 0 | 22.7806 | 20 | 20 | 20.0109 | 20
TCM | Q1 | Q2 | Q3 | Q4 | Total | Budget 2025
OB Removal (KBcm) | 10676.4767 | 9453.8362 | 14434 | 12335.687 | 46900 | 51650 | 90.8%
PAMA | 3675.6012 | 4319.4363 | 8059 | 7042 | 23096.0375 | 24400
MAP | 2955.7184 | 2315.2482 | 3000 | 2692.0733 | 10963.0399 | 11000
PJPN | 4045.1571 | 2819.1518 | 3375 | 2601.6138 | 12840.9226 | 16250
ROM Production (Kton) | 646.7268 | 696.8101 | 1030 | 1091.4631 | 3465 | 3300.387 | 105%
PAMA | 410.7747 | 427.6195 | 540 | 560 | 1938.3942 | 2130
MAP | 108.214 | 106.0722 | 170 | 156 | 540.2862 | 550
PJPN | 123.3898 | 155.9742 | 320 | 375.4631 | 974.8271 | 620.387
SNS | 4.3483 | 7.1442 | 0 | 0 | 11.4925
SR ROM with void | 16.5085 | 13.5673 | 14.0136 | 11.302 | 13.5354 | 15.6497
FC Product CP (Kton) | 737.9146 | 724.161 | 865 | 1073 | 3400.0756 | 3230
TCM.HCV.LS | 437.9277 | 387.1224 | 420 | 625 | 1870.0501 | 1630
TCM.HCV.HS | 299.9869 | 337.0386 | 445 | 448 | 1530.0255 | 1480
TCM.HCV.MS | 0 | 0 | 0 | 0 | 0 | 120
FC Product 3rd party (Kton) | 57.1257 | 53.4973 | 58.8103 | 75.2631 | 244.6963 | 1676.5
EBH.HCV.LS | 7.1098 | 40.5275 | 51.9524 | 50.1264 | 149.7161 | 671.5
MBL.MCV.MS | 50.0159 | 12.9697 | 6.8579 | 25.1368 | 94.9803 | 1005
SR FC | 14.4684 | 13.0549 | 16.6867 | 11.4964 | 13.7938 | 15.9907
TCM.HCV.LS | 437.9277 | 387.1224 | 420 | 625 | 1870.0501 | 1630
CV(GAR) | 6639.7412 | 6691.4648 | 6648.2918 | 6541.3342 | 6619.4798 | 6355.6513
Sul < 0.7 | 0.67682 | 0.67309 | 0.73933 | 0.72931 | 0.70763 | 0.60341
ASH < 5.0 | 4.095 | 4.0745 | 4.6958 | 4.8911 | 4.4918 | 4.8411
IM | 7.0529 | 6.8605 | 7.0506 | 7.1454 | 7.0435 | 7.3863
TM | 11.8734 | 11.1352 | 10.1438 | 11.4587 | 11.1935 | 13.8465
TCM.HCV.HS | 299.9869 | 337.0386 | 445 | 448 | 1530.0255 | 1480
CV(GAR) | 6546.3914 | 6545.0647 | 6453.3842 | 6390.4884 | 6473.3992 | 6482.812
Sul < 2.0 | 1.5725 | 1.6168 | 1.7961 | 1.7584 | 1.7017 | 1.8762
ASH < 5.0 | 4.2591 | 5.787 | 6.3442 | 5.895 | 5.6811 | 10.2546
IM | 6.4203 | 6.3243 | 6.3247 | 6.0358 | 6.2588 | 6.6258
TM | 11.3214 | 10.9288 | 10.7821 | 11.3736 | 11.0933 | 11.2522
EBH.HCV.LS | 7.1098 | 40.5275 | 51.9524 | 50.1264 | 149.7161 | 671.5
CV(GAR) | 6322 | 6322 | 6322 | 6322 | 6322 | 6322
Sul < 1.2 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6
ASH < 5.0 | 7 | 7 | 7 | 7 | 7 | 7
IM | 12 | 12 | 12 | 12 | 12 | 12
TM | 14 | 14 | 14 | 14 | 14 | 14
MBL.MCV.MS | 50.0159 | 12.9697 | 6.8579 | 25.1368 | 94.9803 | 1005
CV(GAR) | 5400 | 5400 | 5400 | 5400 | 5400 | 5400
Sul < 1.2 | 1 | 1 | 1 | 1 | 1 | 1
ASH < 5.0 | 6 | 6 | 6 | 6 | 6 | 6
IM | 15 | 15 | 15 | 15 | 15 | 15
TM | 24 | 24 | 24 | 24 | 24 | 24
BEK | Q1 | Q2 | Q3 | Q4 | Total | Budget 2025
OB Removal (KBcm) | 21749.2528 | 17796.2311 | 21424 | 25558.516 | 86527.9999 | 90950 | 95.14%
TRUST | 4618.2176 | 3934.9567 | 4855 | 6422.8254 | 19830.9997 | 24000
PAMA | 11147.4983 | 10260.7957 | 13334 | 15862.7059 | 50604.9999 | 52450
SNS | 5983.5369 | 3600.4787 | 3235 | 3272.9847 | 16092.0003 | 14500
ROM Production (Kton) | 2384.6632 | 2002.7722 | 1852 | 1855.5646 | 8095 | 8000 | 101.2%
TRUST | 652.3144 | 624.7868 | 484 | 488.8988 | 2250 | 2400
PAMA | 1195.5137 | 733.2138 | 1143 | 1278.2724 | 4350 | 4400
SNS | 536.835 | 644.7716 | 225 | 88.3934 | 1495 | 1200
SR ROM | 9.1205 | 8.8858 | 11.568 | 13.774 | 10.6891 | 11.3688
SR FC | 10.152 | 8.5245 | 11.6308 | 12.8436 | 10.7328 | 11.2284
FC Product (KTons) | 2142.3624 | 2087.6633 | 1842 | 1989.9744 | 8062 | 8100
BEK.HCV.LS | 1740.8722 | 1455.1502 | 1322 | 1353.9776 | 5872 | 5560
CV(GAR) | 6143.341 | 6129.7036 | 6245.8901 | 6145.7234 | 6163.5983 | 5915.2264
TS | 0.53125 | 0.59533 | 0.52542 | 0.54442 | 0.54885 | 0.5772
Ash | 4.4045 | 4.0636 | 3.5876 | 3.8733 | 4.0136 | 4.8848
IM | 10.5333 | 11.0581 | 10.8976 | 11.0213 | 10.8579 | 11.4694
TM | 15.9061 | 16.1129 | 14.884 | 15.6651 | 15.6717 | 15.2419
BEK.HCV.HS | 401.4902 | 632.5131 | 520 | 635.9967 | 2190 | 2540
CV(GAR) | 6068.5304 | 6081.8005 | 6150.2198 | 6085.3923 | 6096.6565 | 5792.8232
TS | 1.9721 | 1.8941 | 1.897 | 1.9222 | 1.9172 | 1.7606
Ash | 5.4116 | 6.0269 | 5.4092 | 5.5497 | 5.6288 | 5.7572
IM | 10.4965 | 10.1759 | 10.166 | 10.2762 | 10.2615 | 10.7369
TM | 15.6136 | 15.1234 | 14.1054 | 14.9461 | 14.92 | 14.5518
JBG | Q1 | Q2 | Q3 | Q4 | Total | Budget 2025
OB Removal (KBcm) | 0 | 47.865 | 841.384 | 1229.751 | 2119 | 5038.608 | 42.06%
Pit UCE-Extend | 0 | 47.865 | 841.384 | 1229.751 | 2119 | 5038.608
ROM Production (Kton) | 0 | 0 | 26 | 174 | 200 | 448 | 44.64%
Pit UCE-Extend | 0 | 0 | 26 | 174 | 200 | 448
SR ROM | 0 | 0 | 32.3609 | 7.0675 | 10.595 | 11.2469
SR FC | 0 | 0 | 38.2447 | 7.1915 | 10.9793 | 11.6365
JBG Coal Loading | 0 | 0 | 44.2 | 178.3 | 222.5 | 430.7
JBG FC Product (Kton) / JBG | 0 | 0 | 22 | 171 | 193 | 433
CV(GAR) | 0 | 0 | 4432.8755 | 4340.4136 | 4350.9533 | 4423.7946
TS | 0 | 0 | 0.4259 | 0.36636 | 0.37315 | 0.36899
Ash | 0 | 0 | 4.8165 | 5.3242 | 5.2663 | 4.4323
IM | 0 | 0 | 16.9178 | 16.1786 | 16.2628 | 16.9259
TM | 0 | 0 | 29.7121 | 30.0155 | 29.9809 | 30.2366
GPK | Q1 | Q2 | Q3 | Q4 | Total | Budget 2025
OB Removal (KBcm) | 1701.9405 | 1914.9784 | 2745 | 2388.0812 | 8750 | 8500 | 102.9%
ARKA | 1701.9405 | 1914.9784 | 2745 | 2388.0812 | 8750 | 8500
ROM Production (Kton) | 508.7988 | 463.1893 | 358.1829 | 414.6302 | 1744.8011 | 2100 | 83.09%
ARKA | 374.1147 | 384.7645 | 358.1829 | 414.6302 | 1531.6923 | 1467
SLS | 134.6841 | 78.4248 | 0 | 0 | 213.1088 | 633
Other Contractor |  |  |  |  | 0
SR ROM | 3.345 | 4.1343 | 7.6637 | 5.7595 | 5.0149 | 4.0476
SR FC | 2.7346 | 3.4624 | 7.625 | 3.34 | 3.8881 | 4.1463
FC Production (Ktons) | 622.379 | 553.0792 | 360 | 715 | 2250.4582 | 2050
CV(GAR) | 3743.3845 | 3739.1623 | 3677.5944 | 3701.971 | 3718.6649 | 3727.504
TS | 0.16781 | 0.19203 | 0.16219 | 0.15723 | 0.1695 | 0.15227
Ash | 8.6931 | 7.1164 | 8.6517 | 7.9363 | 8.0585 | 7.9761
IM | 19.8588 | 22.724 | 22.0574 | 22.8058 | 21.851 | 27.2546
TM | 38.5308 | 39.1483 | 38.215 | 37.7443 | 38.3822 | 38.2852
TIS | Q1 | Q2 | Q3 | Q4 | Total | Budget 2025
OB Removal (KBcm) | 2112.1103 | 2372.6869 | 3296.9924 | 2926.3971 | 10708.1867 | 10708.1867 | 100%
PJPN | 2112.1103 | 2372.6869 | 3296.9924 | 2926.3971 | 10708.1867 | 10708.1867
ROM Production (Kton) | 118.3203 | 145.5654 | 180 | 162.1143 | 606 | 605.9999 | 100%
PJPN | 94.5177 | 46.9412 | 152 | 141.8239 | 435.2828 | 605.9999
ROM PIT I | 23.8026 | 98.6243 | 28 | 20.2903 | 170.7172
SR ROM | 17.8508 | 16.2998 | 18.3166 | 18.0514 | 17.6703 | 17.6703
SR FC | 54.065 | 20.6677 | 26.3759 | 9.3755 | 18.1188 | 18.1188
FC Production (Ktons) | 39.0661 | 114.8019 | 125 | 312.1321 | 591 | 591
TIS.HCV.HS | 39.0661 | 114.8019 | 125 | 312.1321 | 591 | 591
CV(GAR) | 6758.0516 | 6924.0836 | 7106.4848 | 7080.5805 | 7034.3402 | 6914.9248
TS | 1.2622 | 1.2209 | 1.23 | 1.2275 | 1.229 | 0.97968
Ash | 3.6776 | 2.8489 | 3.4454 | 3.4037 | 3.3229 | 3.7674
IM | 6.3312 | 5.2064 | 4.955 | 4.8828 | 5.0567 | 8.6903
TM | 10.996 | 10.6172 | 7.8122 | 7.8872 | 8.6071 | 4.7342
NPR | Q1 | Q2 | Q3 | Q4 | Total | Budget 2025
OB Removal (KBcm) | 0 | 378.501 | 1732 | 1989.499 | 4100 | 5683.5
PAMA | 0 | 378.501 | 1732 | 1989.499 | 4100 | 5683.5
ROM Production (Kton) | 0 | 0 | 50 | 150 | 200 | 450
PAMA | 0 | 0 | 50 | 150 | 200 | 450
SR ROM | 0 | 0 | 34.64 | 13.2633 | 20.5 | 12.63
SR FC | 0 | 0 | 0 | 13.2633 | 27.3333 | 18.945
FC Production (Ktons) | 0 | 0 | 0 | 150 | 150 | 300
CV(GAR) | 0 | 0 | 0 | 5768.6131 | 5768.6131 | 5016.4003
TS | 0 | 0 | 0 | 1.1891 | 1.1891 | 0.85231
Ash | 0 | 0 | 0 | 6.3381 | 6.3381 | 4.606
IM | 0 | 0 | 0 | 12.2967 | 12.2967 | 5.8143
TM | 0 | 0 | 0 | 17.1256 | 17.1256 | 11.202
Note on A8: Belfry Parulian Pandiangan: include high ash
Note on A86: Belfry Parulian Pandiangan: incoming coal volume (quality is not as actual but as range in contract)
Note on A92: Belfry Parulian Pandiangan: incoming coal volume (quality is not as actual but as range in contract)
Note on A100: Belfry Parulian Pandiangan: include Mud
Note on A125: Belfry Parulian Pandiangan: include Mud and sliding volume

## BudgVSact. June (hidden)
SITES | OB |  | ROM |  | FC |  | SR (OB/ROM) |  | Diff. (Act.%)
| Budget | Actual | Budget | Actual | Budget | Actual | Budget | Actual | OB | ROM
IMM | 45360.0431 | 42694.4376 | 3220 | 3245.9681 | 3275.5 | 3354.6236 | 14.087 | 13.1531 | 94.12% | 100.8%
TCM | 25550 | 20130.313 | 1487 | 1343.5369 | 1562 | 1462.0756 | 17.1822 | 14.9831 | 78.79% | 90.35%
BEK | 45094 | 39545.4839 | 3966.5 | 4387.4354 | 4050 | 4230.0256 | 11.3687 | 9.0133 | 87.7% | 110.6%
JBG | 1603.028 | 47.865 | 57 | 0 | 53 | 0 | 28.1233 | #DIV/0! | 2.986% | 0%
GPK | 3825 | 3616.9188 | 1062 | 1176.9001 | 1100 | 1175.4582 | 3.6017 | 3.0733 | 94.56% | 110.8%
TIS | 4924.429 | 4484.7972 | 270.886 | 263.8857 | 245 | 153.868 | 18.179 | 16.9952 | 91.07% | 97.42%
TOTAL | 126356.5002 | 110519.8154 | 10063.386 | 10417.7262 | 10285.5 | 10376.051 | 12.5561 | 10.6088 | 87.47% | 103.5%
|  |  |  | 103.5% |  | 100.9%