## Outlook 07 Mar 2026
[15 empty] | A |  | A
FINAL DRAFT OF ITM PLANBASE
ITM MINE PLAN YEAR 2026
|  |  | Act. | Act. | Out | Out | Out | Out | Out | Out | Out | Out | Out | Out | 2026-03-07 |  | Y2026 Bgt
ok | IMM | EO Y25 | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec |  |  | Total
| ROM Production |  | 575.5544 | 441.7529 | 587.9539 | 582.5 | 592.5 | 592.5 | 652.5 | 652.5 | 652.5 | 392.5 | 377.5 | 377.7388 | 6478 |  | 7050
| FC Product (Kton) |  | 531.5484 | 477.2416 | 580 | 582.5 | 592.5 | 592.5 | 652.5 | 652.5 | 652.5 | 392.5 | 377.5 | 394.2101 | 6478 |  | 7200
| FC Ready to Haul Product (Kton) |  | 553.6496 | 474.5457 | 580 | 582.5 | 592.5 | 592.5 | 652.5 | 652.5 | 652.5 | 392.5 | 377.5 | 374.8047 | 6478 |  | 7199.9996
| IMM-WB.HCV.LS |  | 17.3193 | 26.1347 | 17 | 45.2206 | 57.0314 | 62.4613 | 47.6872 | 51.9909 | 42.7311 | 27.8546 | 26.8235 | 17.7251 | 439.9798 |  | 556.926
| CV (GAR) |  | 6242.0706 | 6274.0898 | 6203.2605 | 6196.0192 | 6164.1589 | 6164.5407 | 6222.3098 | 6214.4688 | 6206.9013 | 6157.1972 | 6270.3956 | 6247.1167 | 6204.3721 | 6204.3721 | 6246.3652
| TS |  | 0.76077 | 0.87178 | 0.89479 | 0.95483 | 0.95073 | 0.95456 | 0.95647 | 0.95692 | 0.94923 | 0.94083 | 0.95736 | 0.96141 | 0.93878 | 0.93878 | 0.95283
| Ash |  | 6.9604 | 5.9793 | 8.1425 | 8.0119 | 8.1309 | 8.819 | 8.8339 | 8.7863 | 8.7568 | 9.6604 | 7.6819 | 7.4604 | 8.2998 | 8.2998 | 7.8724
| Moist |  | 8.8683 | 9.3536 | 7.1043 | 7.158 | 7.2097 | 8.8576 | 8.6973 | 8.6606 | 8.8941 | 8.6009 | 8.8775 | 9.1399 | 8.3907 | 8.3907 | 8.3275
| TM |  | 12.343 | 12.8294 | 12.0651 | 12.1937 | 12.2454 | 13.8933 | 13.733 | 13.6963 | 13.9298 | 13.6366 | 13.9132 | 14.1756 | 13.2694 | 13.2694 | 13.3632
| IMM-WB.HCV.HS |  | 31.7995 | 53.8257 | 73 | 44.7794 | 32.9686 | 27.5387 | 42.8128 | 23.0091 | 32.2689 | 22.1454 | 8.1765 | 24.6956 | 417.0202 |  | 403.074
| CV (GAR) |  | 5848.1221 | 5938.0193 | 5810.079 | 5708.9693 | 5402.5245 | 5384.3057 | 5485.5575 | 5491.6141 | 5486.7622 | 5432.1961 | 5970.8466 | 5944.3828 | 5673.4319 | 5673.4319 | 5756.5194
| TS |  | 2.4002 | 2.3046 | 2.4287 | 2.8135 | 3.0907 | 3.0966 | 3.2593 | 3.3082 | 3.2598 | 2.9249 | 2.9025 | 2.9103 | 2.8105 | 2.8105 | 2.8681
| Ash |  | 12.3258 | 9.9001 | 13.0644 | 15.5869 | 20.3478 | 20.3403 | 18.7318 | 18.3138 | 18.6186 | 19.1837 | 11.6276 | 11.8853 | 15.455 | 15.455 | 15.0175
| Moist |  | 8.0765 | 9.2456 | 7.1321 | 6.7535 | 6.274 | 7.7326 | 7.9238 | 8.0665 | 8.0274 | 8.0821 | 8.5807 | 8.6779 | 7.7806 | 7.7806 | 6.9178
| TM |  | 12.0682 | 12.7775 | 11.5441 | 11.7892 | 11.3097 | 12.7683 | 12.9595 | 13.1022 | 13.0631 | 13.1178 | 13.6164 | 13.7136 | 12.4334 | 12.4334 | 11.9535
| IMM-EB.MCV.LS |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 6.9178
| CV (GAR) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | #DIV/0! | 11.9535
| TS |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | #DIV/0! | 503.637
| Ash |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | #DIV/0! | 6280.3072
| Moist |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | #DIV/0! | 5929.635
| TM |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | #DIV/0! | 1.5717
| IMM-EB.MCV.MS |  | 80.8673 | 67.1126 | 75.5 | 43.0078 | 19.676 | 0 | 37.3943 | 55.4324 | 23.4514 | 8.3241 | 23.2397 | 0 | 434.0056 |  | 503.637
| CV (GAR) |  | 5986.8946 | 6050.4082 | 5896.2356 | 5905.0256 | 5879.4947 | 0 | 5893.685 | 5882.7947 | 5855.419 | 5801.9013 | 5846.0973 | 0 | 5928.4445 | 5928.4445 | 5929.635
| TS |  | 1.5353 | 1.4745 | 1.5823 | 1.5782 | 1.5735 | 0 | 1.5776 | 1.5765 | 1.5849 | 1.5829 | 1.5914 | 0 | 1.5556 | 1.5556 | 1.5717
| Ash |  | 5.5379 | 4.923 | 5.4496 | 6.4732 | 7.3827 | 0 | 7.1823 | 7.1348 | 7.55 | 7.9432 | 8.0193 | 0 | 6.2371 | 6.2371 | 6.033
| Moist |  | 11.7483 | 12.1605 | 10.9625 | 10.0273 | 10.3783 | 0 | 10.419 | 10.4203 | 10.5259 | 10.6511 | 10.7006 | 0 | 11.0154 | 11.0154 | 10.4529
| TM |  | 14.5206 | 14.5192 | 15.9625 | 15.0273 | 15.3783 | 0 | 15.419 | 15.4203 | 15.5259 | 15.6511 | 15.7006 | 0 | 15.1918 | 15.1918 | 15.4529
| IMM-EB.MCV.HS |  | 401.5622 | 330.1685 | 402 | 436.9922 | 470.324 | 490 | 512.1057 | 509.5676 | 541.5486 | 321.6759 | 306.7603 | 339.2894 | 5061.9944 |  | 5586.363
| CV (GAR) |  | 5998.2743 | 6043.5383 | 5889.1241 | 5922.1096 | 5908.4675 | 5928.1565 | 5940.3018 | 5929.6098 | 5929.1918 | 5911.6219 | 5908.4216 | 5890.2905 | 5932.4945 | 5932.4945 | 5919.4855
| TS |  | 2.3559 | 2.2726 | 2.371 | 2.382 | 2.4419 | 2.3916 | 2.3697 | 2.383 | 2.3947 | 2.3848 | 2.3841 | 2.3644 | 2.3778 | 2.3778 | 2.3928
| Ash |  | 5.4084 | 5.3738 | 5.6747 | 6.9735 | 6.9535 | 6.4093 | 6.1702 | 6.3357 | 6.1845 | 6.385 | 6.7998 | 6.909 | 6.3033 | 6.3033 | 6.3137
| Moist |  | 11.4382 | 11.7662 | 10.6485 | 10.4814 | 10.3446 | 10.3228 | 10.385 | 10.3977 | 10.4158 | 10.4139 | 10.4833 | 10.5166 | 10.5993 | 10.5993 | 10.4444
| TM |  | 14.2639 | 13.9206 | 15.6485 | 15.4814 | 15.3446 | 15.3228 | 15.385 | 15.3977 | 15.4158 | 15.4139 | 15.4833 | 15.5166 | 15.2412 | 15.2412 | 15.4444
| Fine Coal |  | 0 | 0 | 12.5 | 12.5 | 12.5 | 12.5 | 12.5 | 12.5 | 12.5 | 12.5 | 12.5 | 12.5 | 125 |  | 150
| CV (GAR) |  | 0 | 0 | 3146.0674 | 3146.0674 | 3146.0674 | 3146.0674 | 3146.0674 | 3146.0674 | 3146.0674 | 3146.0674 | 3146.0674 | 3146.0674 | 3146.0674 | 3146.0674 | 3146.0674
| TS |  | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
| Ash |  | 0 | 0 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40
| Moist |  | 0 | 0 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11
| TM |  | 0 | 0 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20
| ROM Stock | 1.6006 | 51.4797 | 22.1507 | 22.8018 | 22.8018 | 22.8018 | 22.8018 | 22.8018 | 22.8018 | 22.8018 | 22.8018 | 22.8018 | 6.3306 | 6.3306 |  | 25.9633
| FC Stock | 220.4065 | 128.1635 | 129.4718 | 129.4718 | 129.4718 | 129.4718 | 129.4718 | 129.4718 | 129.4718 | 129.4718 | 129.4718 | 129.4718 | 148.8772 | 148.8772 |  | 180.6415
Ok | TCM |  | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Total |  | Total
| Pama |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
| Bas |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
| Map |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
| Rml |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
| ROM Production |  | 216.6741 | 178.2019 | 265 | 290 | 300 | 315 | 297.061 | 90.1874 | 321.6279 | 310 | 310 | 305.8156 | 3199.5679 |  | 4000
| FC Production TCM (Kton) |  | 349.2329 | 262.2481 | 220 | 260 | 270 | 270 | 230.456 | 205 | 270 | 275 | 285 | 303.063 | 3200 |  | 4150
| TCM.HCV.LS |  | 284.0288 | 182.5422 | 155 | 180 | 180 | 180 | 140 | 125 | 170 | 160 | 170 | 173.063 | 2099.634 |  | 1860
| TCM.HCV.HS |  | 65.2041 | 79.7059 | 65 | 80 | 90 | 90 | 90.456 | 80 | 100 | 115 | 115 | 130 | 1100.366 |  | 2290
| EBH.HCV.LS | [13 empty] | 0 |  | 671.5
| EBH 6000 | [13 empty] | 0 |  | 0
| MBL 5800 | [13 empty] | 0 |  | 0
| MBL.MCV.MS | [13 empty] | 0 |  | 1005
| FC Loading |  | 493.4678 | 277.8816 | 220 | 230 | 230 | 220 | 190.5876 | 205 | 270 | 300 | 285 | 278.063 | 3200 |  | 4090
| FC Product CP (TCM all) |  | 349.2329 | 262.2481 | 220 | 260 | 270 | 270 | 230.456 | 205 | 270 | 275 | 285 | 303.063 | 3200 |  | 4626.5
| FC Product CP (TCM only) |  | 349.2329 | 262.2481 | 220 | 260 | 270 | 270 | 230.456 | 205 | 270 | 275 | 285 | 303.063 | 3200 | 271.6468 | 2950
| TCM.HCV.LS |  | 284.0288 | 182.5422 | 155 | 180 | 180 | 180 | 140 | 125 | 170 | 160 | 170 | 173.063 | 2099.634 | 179.3286 | 1860
| CV (GAR) |  | 6649.9207 | 6656.3271 | 6533.8198 | 6538.2337 | 6561.0291 | 6654.6544 | 6637.2659 | 6758.8841 | 6586.419 | 6612.7088 | 6666.2893 | 6618.1148 | 6621.4869 | 6622.2472 | 6579.5619
| Sul < 0.7 |  | 0.73202 | 0.54966 | 0.68 | 0.69 | 0.7 | 0.75 | 0.67 | 0.75 | 0.69 | 0.69 | 0.7 | 0.75 | 0.69674 | 0.69728 | 0.69985
| ASH < 5.0 |  | 3.6103 | 3.9702 | 5.83 | 4.62 | 4.54 | 4.3 | 4.09 | 3.79 | 4.18 | 4.07 | 3.72 | 4.11 | 4.2048 | 4.2018 | 4.0613
| IM |  | 6.4151 | 6.9996 | 6.43 | 7.23 | 7.22 | 6.75 | 6.74 | 5.83 | 6.51 | 6.36 | 6.09 | 6.16 | 6.5776 |  | 6.6436
| TM |  | 11.4833 | 11.3069 | 11.28 | 11.62 | 11.47 | 11.02 | 11.09 | 11.18 | 11.87 | 11.73 | 11.49 | 11.57 | 11.4373 | 136.7681 | 11.641
| TCM.HCV.HS |  | 65.2041 | 79.7059 | 65 | 80 | 90 | 90 | 90.456 | 80 | 100 | 115 | 115 | 130 | 1100.366 | 1093.0314 | 2290
| CV (GAR) |  | 6531.1518 | 6505.5844 | 6504.0284 | 6453.4142 | 6548.9679 | 6511.7875 | 6533.8801 | 6512.4154 | 6488.435 | 6417.465 | 6347.4654 | 6353.4566 | 6464.8272 | 77537.2489 | 6418.8032
| Sul < 2.0 |  | 1.7368 | 1.6609 | 1.56 | 1.63 | 1.5 | 1.61 | 1.7 | 1.69 | 1.7 | 1.7 | 1.74 | 1.96 | 1.6964 | 20.0896 | 1.7095
| ASH < 5.0 |  | 6.0202 | 6.1157 | 5.4 | 5.75 | 4.98 | 5.39 | 5.34 | 5.27 | 5.45 | 6.04 | 7.44 | 5.62 | 5.7751 | 68.5054 | 5.2448
| IM |  | 5.9183 | 6.5949 | 6.37 | 6.8 | 6.86 | 6.72 | 6.28 | 6.79 | 6.76 | 6.27 | 5.84 | 6.74 | 6.4959 |  | 6.0611
| TM |  | 10.6275 | 10.9526 | 11.06 | 11.42 | 11.07 | 11.17 | 11.24 | 11.28 | 11.28 | 11.97 | 11.86 | 11.84 | 11.3842 | 135.7441 | 11.5066
| EBH.HCV.LS |  | 56.6 | 56.9 | 56.1 | 55.6 | 56.5 | 55.8 | 56 | 55.2 | 55.6 | 56.2 | 55.8 | 55.2 | 671.5 | #REF! | 630
| CV (GAR) |  | 6322 | 6322 | 6322 | 6322 | 6322 | 6322 | 6322 | 6322 | 6322 | 6322 | 6322 | 6322 | 6322 | #REF! | 6322
| Sul 0.6 |  | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | #REF! | 0.6
| ASH |  | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | #REF! | 7
| IM |  | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 |  | 12
| TM |  | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 168 | 14
| EBH 6000 | [13 empty] | 0 | 0 | 172.5
| CV (GAR) |  | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 72000 | 6000
| Sul 0.6 |  | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 7.2 | 0.6
| ASH 9.0 |  | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 108 | 9
| IM |  | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 |  | 12
| TM |  | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 168 | 14
| MBL 5800 | [13 empty] | 0 | #REF! | 172.5
| CV (GAR) |  | 5800 | 5800 | 5800 | 5800 | 5800 | 5800 | 5800 | 5800 | 5800 | 5800 | 5800 | 5800 | 5800 | #REF! | 5800
| Sul 1.0 | [13 empty] | 1 | #REF! | 1 | bar: Jan to Dec
| ASH 6.0 |  | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | #REF! | 6
| IM |  | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 |  | 13
| TM |  | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 |  | 19
| MBL.MCV.MS |  | 82.5 | 82.5 | 82.5 | 82.5 | 82.5 | 82.5 | 82.5 | 82.5 | 90 | 90 | 82.5 | 82.5 | 1005 | 1005 | 540
| CV (GAR) |  | 5400 | 5400 | 5400 | 5400 | 5400 | 5400 | 5400 | 5400 | 5400 | 5400 | 5400 | 5400 | 5400 | 64800 | 5400
| Sul 1.2 | [13 empty] | 1 | 12 | 1 | bar: Jan to Dec
| ASH |  | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 72 | 6
| IM 14.00-15.00 |  | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 |  | 15
| TM 22.00-24.00 |  | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 |  | 24
| ROM Stock | 262.1758 | 157.0693 | 62.2621 | 114.2621 | 152.2621 | 195.2621 | 254.2621 | 335.8671 | 236.0546 | 299.6824 | 344.6824 | 379.6824 | 391.435 | 391.435 |  | 337
| FC Stock | 237.5474 | 97.9464 | 89.1562 | 89.1562 | 119.1562 | 159.1562 | 209.1562 | 249.0245 | 249.0245 | 249.0245 | 224.0245 | 224.0245 | 249.0245 | 249.0245 |  | 173.158
Ok | JBG |  | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Total |  | Total
| ROM Production |  | 0 | 0 | 0 | 0 | 0 | 0 | 24.638 | 49.4429 | 55.2399 | 58.1793 | 0 | 0 | 187.5 | 187.5 | 540
| JBG FC Product (Kton) |  | 0 | 0 | 0 | 0 | 0 | 0 | 24.638 | 49.443 | 55.24 | 58.1793 | 0 | 0 | 187.5003 | 187.5003 | 537.0014
| Cv (GAR) |  | 0 | 0 | 0 | 0 | 0 | 0 | 4439.1516 | 4421.4437 | 4385.0123 | 4337.0536 | 0 | 0 | 4386.8521 |  | 4388.0437
| TS |  | 0 | 0 | 0 | 0 | 0 | 0 | 0.38922 | 0.35966 | 0.38875 | 0.37477 | 0 | 0 | 0.37681 |  | 0.37887
| Ash |  | 0 | 0 | 0 | 0 | 0 | 0 | 4.3463 | 4.4855 | 4.3593 | 5.2255 | 0 | 0 | 4.6596 |  | 4.7823
| IM |  | 0 | 0 | 0 | 0 | 0 | 0 | 17.1055 | 17.1993 | 16.7036 | 16.1664 | 0 | 0 | 16.7204 |  | 16.3515
| TM |  | 0 | 0 | 0 | 0 | 0 | 0 | 29.4567 | 30.3014 | 30.346 | 30.5019 | 0 | 0 | 30.2658 |  | 30.2957
| Loading Barge | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21.9 | 43.8 | 58.4 | 58.4 | 0 | 0 | 182.5 |  | 525.6
| ROM Stock | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.449 | 5.2395 | 5.3821 | 5.3821 |  | 2.1596
| FC Stock | 1.37 | 1.37 | 1.37 | 1.37 | 1.37 | 1.37 | 1.37 | 25.9943 | 16.7774 | 13.4496 | 7.0151 | 4.5449 | 3.7995 | 3.7995 |  | 9.9078
ok | BEK |  | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Total |  | Total
| ROM Production |  | 576.437 | 539.8666 | 580 | 675 | 710 | 720 | 755 | 705 | 710 | 623 | 565 | 312.6965 | 7472 |  | 8000
| FC Product (KTons) |  | 745.284 | 724.965 | 750 | 700 | 700 | 700 | 600 | 550 | 550 | 485 | 485 | 481.751 | 7472 |  | 8550
| BEK.HCV.LS |  | 590.8307 | 588.6676 | 600 | 550 | 550 | 550 | 550 | 500 | 500 | 445 | 445 | 432.5017 | 6302 |  | 6950
| Cv (GAR) |  | 6238.3493 | 6234.4298 | 6264.8478 | 6267.3931 | 6282.5103 | 6257.1032 | 6260.0346 | 6293.1971 | 6295.2151 | 6284.4253 | 6331.2714 | 6325.053 | 6275.053 | 6275.053 | 6298.766
| TS |  | 0.55589 | 0.40814 | 0.54051 | 0.58548 | 0.62396 | 0.59405 | 0.58668 | 0.59475 | 0.59668 | 0.57334 | 0.61037 | 0.65035 | 0.57305 | 0.57305 | 0.6461
| Ash |  | 3.922 | 3.6858 | 3.9246 | 4.4915 | 4.8597 | 5.0629 | 4.9715 | 4.819 | 4.9249 | 5.1757 | 5.2764 | 5.0949 | 4.6383 | 4.6383 | 4.8026
| IM |  | 9.9092 | 10.5125 | 10.3374 | 11.3224 | 11.0999 | 11.0342 | 11.192 | 11.4193 | 11.1565 | 12.1519 | 12.0344 | 12.336 | 11.1375 | 11.1375 | 11.7535
| TM |  | 15.2672 | 15.5416 | 14.4523 | 15.0536 | 14.7338 | 14.9331 | 14.8838 | 15.0295 | 14.9498 | 16.0016 | 16.0394 | 16.2624 | 15.2181 | 15.2181 | 15.5007
| BEK.HCV.HS |  | 154.4533 | 136.2974 | 150 | 150 | 150 | 150 | 50 | 50 | 50 | 40 | 40 | 49.2493 | 1170 |  | 1600
| Cv (GAR) |  | 6118.757 | 6190.0446 | 6188.3272 | 6201.4228 | 6223.2217 | 6240.7037 | 6267.5518 | 6261.227 | 6269.9884 | 6365.8344 | 6352.7282 | 6363.8395 | 6221.2786 | 6221.2786 | 6238.6552
| TS |  | 1.5346 | 1.4946 | 1.5982 | 1.5682 | 1.5392 | 1.5357 | 1.522 | 1.5344 | 1.5334 | 1.6703 | 1.6696 | 1.5926 | 1.5542 | 1.5542 | 1.7954
| Ash |  | 4.5732 | 4.7058 | 4.9137 | 5.6343 | 6.049 | 5.987 | 6.6157 | 6.3459 | 6.2009 | 5.4046 | 5.5235 | 5.362 | 5.4655 | 5.4655 | 5.8543
| IM |  | 9.6113 | 9.6645 | 9.9958 | 10.081 | 10.0409 | 10.1127 | 10.0464 | 10.001 | 9.9992 | 10.5885 | 10.8975 | 11.1134 | 10.0388 | 10.0388 | 11.07
| TM |  | 15.9043 | 15.0832 | 14.4658 | 14.251 | 14.0419 | 14.0097 | 13.8757 | 13.8141 | 13.8134 | 14.4075 | 14.7655 | 14.9667 | 14.5357 | 14.5357 | 14.7103
| ROM Stock | 741.1791 | 562.1023 | 377.0326 | 204.1326 | 175.7576 | 182.2076 | 198.6076 | 349.8326 | 501.3076 | 657.7576 | 792.6426 | 869.8176 | 699.1996 | 699.1996 |  | 272.9037
| FC Stock | 105.7752 | 53.0489 | 79.4389 | 85.6889 | 82.1889 | 178.6889 | 275.1889 | 272.1889 | 219.4389 | 216.6889 | 149.2639 | 116.8389 | 94.3217 | 94.3217 |  | 46.8402
Ok | GPK |  | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Total |  | Total
| ROM Production |  | 165.3666 | 180.2117 | 210 | 220 | 215 | 225 | 160.8537 | 160 | 235 | 250 | 235 | 243.568 | 2500 |  | 2999.7836
| FC Product (Kton) |  | 208.8007 | 165.9109 | 210 | 220 | 215 | 225 | 160 | 170 | 200 | 240 | 240 | 245.2884 | 2500 |  | 3050
| Cv (GAR) |  | 3686.9816 | 3591.8487 | 3655.1283 | 3655.4581 | 3628.5343 | 3639.3072 | 3636.8875 | 3645.1974 | 3645.9388 | 3646.0414 | 3645.7628 | 3621.3533 | 3642.2441 | 3642.2441 | 3705.4628
| TS |  | 0.16943 | 0.1619 | 0.15632 | 0.14139 | 0.13074 | 0.1289 | 0.14011 | 0.15625 | 0.17133 | 0.17843 | 0.16335 | 0.16912 | 0.15601 | 0.15601 | 0.16234
| Ash |  | 8.2581 | 10.6039 | 9.7002 | 9.1432 | 9.1815 | 9.2789 | 9.1482 | 9.0848 | 9.0826 | 8.8327 | 8.9088 | 9.167 | 9.17 | 9.17 | 7.9479
| IM |  | 21.0636 | 18.4747 | 21.4941 | 24.5103 | 26.2148 | 27.0473 | 25.1399 | 22.6458 | 21.9868 | 22.3411 | 23.4988 | 23.791 | 23.2792 | 23.2792 | 23.1657
| TM |  | 39.3989 | 40.1657 | 38.4447 | 38.677 | 38.5758 | 38.503 | 38.4941 | 38.4607 | 38.4506 | 38.5719 | 38.541 | 38.7506 | 38.7318 | 38.7318 | 39.0747
| FC Load/Ready Sale (Kton) |  | 190.7026 | 172.8879 | 210 | 215 | 210 | 220 | 157.8415 | 150 | 195 | 255 | 260 | 263.568 | 2500 |  | 3040
| ROM Stock | 75.8604 | 36.6139 | 55.0391 | 55.0391 | 55.0391 | 55.0391 | 55.0391 | 55.8928 | 45.8928 | 80.8928 | 90.8928 | 85.8928 | 84.1724 | 84.1724 |  | 108.1839
| FC Stock | 2.4152 | 20.5804 | 9.6305 | 13.6034 | 18.6034 | 23.6034 | 28.6034 | 30.7619 | 50.7619 | 55.7619 | 40.7619 | 20.7619 | 2.4823 | 2.4823 |  | 77.4847
Ok | TIS |  | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Total |  | Total
| ROM Production |  | 23.5673 | 17.4631 | 36 | 45 | 50 | 57 | 58.9127 | 66 | 66 | 63.6243 | 61 | 61.4327 | 606 |  | 606
| FC Product (Kton) |  | 0 | 0 | 100 | 100 | 72.1359 | 67.5 | 52.5 | 100 | 80 | 45 | 45 | 43.8641 | 706 |  | 706
| Cv (GAR) |  | 0 | 0 | 6566.6344 | 6574.0878 | 6576.4072 | 6574.092 | 6596.8312 | 6595.9616 | 6595.2498 | 6594.6444 | 6594.6875 | 6598.072 | 6584.5704 | 6584.5704 | 6581.3066
| TS |  | 0 | 0 | 1.367 | 1.3196 | 1.304 | 1.3647 | 1.2159 | 1.2249 | 1.2382 | 1.2454 | 1.2487 | 1.188 | 1.2812 | 1.2812 | 1.2938
| Ash |  | 0 | 0 | 3.8123 | 3.7528 | 3.7333 | 3.7944 | 3.6064 | 3.6163 | 3.6302 | 3.6381 | 3.6412 | 3.5776 | 3.6938 | 3.6938 | 3.7107
| IM |  | 0 | 0 | 4.3642 | 4.3857 | 4.3924 | 4.4855 | 4.5894 | 4.5988 | 4.6139 | 4.6217 | 4.6259 | 4.5571 | 4.5051 | 4.5051 | 4.5095
| TM |  | 0 | 0 | 11.2575 | 11.1932 | 11.1718 | 11.2463 | 11.0407 | 11.052 | 11.0687 | 11.0777 | 11.0818 | 11.0057 | 11.1336 | 11.1336 | 11.142
| FC Load/Ready Sale (Kton) |  | 0 | 0 | 100 | 100 | 72.1359 | 67.5 | 52.5 | 100 | 80 | 45 | 45 | 43.8641 | 706 |  | 606
| ROM Stock | 232.8047 | 255.2899 | 270.2283 | 206.2283 | 151.2283 | 129.0924 | 118.5924 | 125.0051 | 91.0051 | 77.0051 | 95.6293 | 111.6293 | 129.198 | 129.198 |  | 245
| FC Stock | 5.6505 | 5.6227 | 5.3641 | 75.3641 | 100.3641 | 120 | 120 | 120 | 85 | 120 | 97.5 | 55 | 61.3641 | 61.3641 |  | 2
ok | NPR |  | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Total |  | Total
| ROM Production |  | 61.3858 | 63.6142 | 0 | 0 | 0 | 0 | 0 | 29 | 80 | 81 | 74 | 75 | 464 |  | 1200
| FC Product (Kton) |  | 0 | 0 | 0 | 30 | 30 | 30 | 30 | 34 | 80 | 81 | 74 | 75 | 464 |  | 1030
| NPR.MCV.LS |  | 0 | 0 | 0 | 10 | 9 | 9 | 9 | 8 | 25 | 26 | 23 | 24 | 143
| Cv (GAR) |  | 0 | 0 | 0 | 5982.9015 | 5965.0916 | 5950.2359 | 5894.329 | 5811.393 | 5750.8083 | 5681.7927 | 5631.4187 | 5574.9911 | 5744.2399
| TS |  | 0 | 0 | 0 | 0.54496 | 0.53916 | 0.53432 | 0.5385 | 0.54933 | 0.54972 | 0.57826 | 0.58902 | 0.59601 | 0.5663
| Ash |  | 0 | 0 | 0 | 0.54961 | 0.54961 | 1.0081 | 1.6524 | 2.384 | 3.2816 | 4.1957 | 4.8511 | 5.3614 | 3.3905
| IM |  | 0 | 0 | 0 | 0.7828 | 0.7828 | 1.4358 | 2.471 | 3.7118 | 5.0959 | 7.1914 | 8.4414 | 9.3771 | 5.6874
| TM |  | 0 | 0 | 0 | 1.2347 | 1.2347 | 2.2646 | 3.799 | 5.5896 | 7.6843 | 10.6364 | 12.4461 | 13.8045 | 8.4543
| NPR.MCV.HS |  | 0 | 0 | 0 | 20 | 21 | 21 | 21 | 26 | 55 | 55 | 51 | 51 | 321 |  | 1030
| Cv (GAR) |  | 0 | 0 | 0 | 5897.6281 | 5901.4174 | 5904.193 | 5907.357 | 5896.347 | 5892.6469 | 5849.3929 | 5827.7293 | 5836.2024 | 5868.8555 | 5868.4771 | 5938.1343
| TS |  | 0 | 0 | 0 | 1.4326 | 1.447 | 1.4576 | 1.4697 | 1.4726 | 1.4801 | 1.4817 | 1.4843 | 1.4946 | 1.4755 | 1.4755 | 1.1917
| Ash |  | 0 | 0 | 0 | 0.92731 | 0.92731 | 1.6066 | 2.3809 | 3.2851 | 4.1149 | 5.0865 | 5.6814 | 6.1807 | 4.1066 | 4.121 | 6.8257
| IM |  | 0 | 0 | 0 | 1.3493 | 1.3493 | 2.3376 | 3.4642 | 4.5865 | 5.7005 | 7.0612 | 7.9061 | 8.6569 | 5.7415 | 5.7614 | 10.9698
| TM |  | 0 | 0 | 0 | 2.0003 | 2.0003 | 3.4655 | 5.1357 | 6.8333 | 8.5013 | 10.5277 | 11.784 | 12.8927 | 8.5527 | 8.5823 | 16.3194
| FC Load/barges (Kton) |  |  |  |  | 30 | 30 | 30 | 30 | 34 | 80 | 81 | 74 | 75 | 464 |  | 950
| ROM Stock |  | 61.3858 | 125 | 150 | 115 | 80 | 45 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 170
| FC Stock | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 80
| ITM GRAND TOTAL | EO Y25 | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | TOTAL |  | TOTAL
| ROM Production |  | 1618.9852 | 1421.1103 | 1678.9539 | 1812.5 | 1867.5 | 1909.5 | 1948.9653 | 1752.1303 | 2120.3677 | 1778.3036 | 1622.5 | 1376.2516 | 20907.0679 |  | 24395.7836
| FC Production |  | 1834.866 | 1630.3656 | 1860 | 1892.5 | 1879.6359 | 1885 | 1750.094 | 1760.943 | 1887.74 | 1576.6793 | 1506.5 | 1543.1765 | 21007.5003 |  | 25223.0014
| FC + EBH + MBL |  | 1834.866 | 1630.3656 | 1860 | 1892.5 | 1879.6359 | 1885 | 1750.094 | 1760.943 | 1887.74 | 1576.6793 | 1506.5 | 1543.1765 | 21007.5003 |  | 24993.5014
| ROM Stock | 1313.6205 | 1123.9409 | 911.7128 | 752.464 | 672.089 | 664.403 | 694.303 | 899.3994 | 897.0618 | 1138.1397 | 1348.098 | 1475.0635 | 1315.7177 | 1315.7177 |  | 1161.2106
| FC Stock | 573.1649 | 306.7318 | 314.4315 | 394.6544 | 451.1544 | 612.2903 | 763.7903 | 827.4415 | 750.4745 | 784.3968 | 648.0373 | 550.6421 | 559.8693 | 559.8693 |  | 570.0322
Notes :
[6 empty] | -5.5 | -5.5
Note on B45: Belfry Parulian Pandiangan: Exclude High ash stock and exclude fine coal stock
Note on B46: Belfry Parulian Pandiangan: MSY + PSY

## Pro Outlook (Quarterly)
[7 empty] | A |  | A
FINAL DRAFT OF ITM PLANBASE
ITM MINE PLAN YEAR 2026
|  |  | Out | Out | Out | Out | 2026-03-07 |  | Y2026 Bgt
ok | IMM | EO Y25 | Q1 | Q2 | Q3 | Q4 |  |  | Total
| ROM Production |  | 1605.2612 | 1767.5 | 1957.5 | 1147.7388 | 6478 |  | 7050
| FC Product (Kton) |  | 1588.7899 | 1767.5 | 1957.5 | 1164.2101 | 6478 |  | 7200
| FC Ready to Haul Product (Kton) |  | 1608.1953 | 1767.5 | 1957.5 | 1144.8047 | 6478 |  | 7199.9996
| IMM-WB.HCV.LS |  | 60.4541 | 164.7133 | 142.4092 | 72.4032 | 439.9798 |  | 556.926
| CV (GAR) |  | 6244.9992 | 6173.0506 | 6214.8237 | 6221.1475 | 6204.3721 | 5180.6185 | 6246.3652
| TS |  | 0.84645 | 0.95331 | 0.95446 | 0.95199 | 0.93878 | 0.78212 | 0.95283
| Ash |  | 6.8686 | 8.3592 | 8.7934 | 8.3888 | 8.2998 | 6.9193 | 7.8724
| Moist |  | 8.582 | 7.8204 | 8.7429 | 8.8353 | 8.3907 | 6.9367 | 8.3275
| TM |  | 12.4751 | 12.8561 | 13.7787 | 13.871 | 13.2694 | 10.9868 | 13.3632
| IMM-WB.HCV.HS |  | 158.6252 | 105.2867 | 98.0908 | 55.0175 | 417.0202 |  | 403.074
| CV (GAR) |  | 5861.119 | 5528.093 | 5487.3745 | 5742.153 | 5673.4319 | 4915.869 | 5756.5194
| TS |  | 2.3809 | 2.9744 | 3.2709 | 2.915 | 2.8105 | 2.426 | 2.8681
| Ash |  | 11.8426 | 18.321 | 18.5965 | 14.7847 | 15.455 | 13.5045 | 15.0175
| Moist |  | 8.0386 | 6.8594 | 7.9913 | 8.4236 | 7.7806 | 6.6692 | 6.9178
| TM |  | 12.0677 | 11.8951 | 13.0271 | 13.4593 | 12.4334 | 10.6577 | 11.9535
| IMM-EB.MCV.LS |  | 0 | 0 | 0 | 0 | 0 |  | 6.9178
| CV (GAR) |  | #DIV/0! | #DIV/0! | 0 | 0 | #DIV/0! | #DIV/0! | 11.9535
| TS |  | #DIV/0! | #DIV/0! | 0 | 0 | #DIV/0! | #DIV/0! | 503.637
| Ash |  | #DIV/0! | #DIV/0! | 0 | 0 | #DIV/0! | #DIV/0! | 6280.3072
| Moist |  | #DIV/0! | #DIV/0! | 0 | 0 | #DIV/0! | #DIV/0! | 5929.635
| TM |  | #DIV/0! | #DIV/0! | 0 | 0 | #DIV/0! | #DIV/0! | 1.5717
| IMM-EB.MCV.MS |  | 223.4799 | 62.6838 | 116.2781 | 31.5638 | 434.0056 |  | 503.637
| CV (GAR) |  | 5975.3402 | 5897.0116 | 5880.7757 | 5834.4417 | 5928.4445 | 5504.1245 | 5929.635
| TS |  | 1.5329 | 1.5768 | 1.5786 | 1.5891 | 1.5556 | 1.44 | 1.5717
| Ash |  | 5.3234 | 6.7587 | 7.2338 | 7.9992 | 6.2371 | 5.6554 | 6.033
| Moist |  | 11.6066 | 10.1375 | 10.4412 | 10.6876 | 11.0154 | 10.2381 | 10.4529
| TM |  | 15.0073 | 15.1375 | 15.4412 | 15.6876 | 15.1918 | 14.0509 | 15.4529
| IMM-EB.MCV.HS |  | 1133.7307 | 1397.3162 | 1563.2219 | 967.7255 | 5061.9944 |  | 5586.363
| CV (GAR) |  | 5972.7536 | 5919.6382 | 5932.9676 | 5903.1285 | 5932.4945 | 4803.9654 | 5919.4855
| TS |  | 2.337 | 2.4055 | 2.3827 | 2.3774 | 2.3778 | 1.9232 | 2.3928
| Ash |  | 5.4928 | 6.7689 | 6.2291 | 6.7002 | 6.3033 | 5.0224 | 6.3137
| Moist |  | 11.2537 | 10.3797 | 10.3998 | 10.4719 | 10.5993 | 8.5973 | 10.4444
| TM |  | 14.6549 | 15.3797 | 15.3998 | 15.4719 | 15.2412 | 12.2834 | 15.4444
| Fine Coal |  | 12.5 | 37.5 | 37.5 | 37.5 | 125 |  | 150
| CV (GAR) |  | 3146.0674 | 3146.0674 | 3146.0674 | 3146.0674 | 3146.0674 | 2202.2472 | 3146.0674
| TS |  | 2 | 2 | 2 | 2 | 2 | 1.4 | 2
| Ash |  | 40 | 40 | 40 | 40 | 40 | 28 | 40
| Moist |  | 11 | 11 | 11 | 11 | 11 | 7.7 | 11
| TM |  | 20 | 20 | 20 | 20 | 20 | 14 | 20
| ROM Stock | 1.6006 | 22.8018 | 22.8018 | 22.8018 | 6.3306 | 6.3306 |  | 25.9633
| FC Stock | 220.4065 | 129.4718 | 129.4718 | 129.4718 | 148.8772 | 148.8772 |  | 180.6415
ok | TCM |  | Q1 | Q2 | Q3 | Q4 | Total |  | Total
| Pama | [5 empty] | #REF! |  | #REF!
| Bas | [5 empty] | #REF! |  | #REF!
| Map | [5 empty] | #REF! |  | #REF!
| Rml | [5 empty] | #REF! |  | #REF!
| ROM Production |  | 659.876 | 905 | 708.8763 | 925.8156 | 3199.5679 |  | 4000
| FC Production TCM (Kton) |  | 831.481 | 800 | 705.456 | 863.063 | 3200 |  | 4150
| TCM.HCV.LS |  | 621.571 | 540 | 435 | 503.063 | 2099.634 |  | 1860
| TCM.HCV.HS |  | 209.91 | 260 | 270.456 | 360 | 1100.366 |  | 2290
| EBH.HCV.LS |  | 0 | 0 | 0 | 0 | 0 |  | 671.5
| EBH 6000 |  | 0 | 0 | 0 | 0 | 0 |  | 0
| MBL 5800 |  | 0 | 0 | 0 | 0 | 0 |  | 0
| MBL.MCV.MS |  | 0 | 0 | 0 | 0 | 0 |  | 1005
| FC Loading |  | 991.3494 | 680 | 665.5876 | 863.063 | 3200 |  | 4090
| FC Product CP (TCM all) | [5 empty] | 0 |  | 4626.5
| FC Product CP (TCM only) |  | 831.481 | 800 | 705.456 | 863.063 | 3200 | #DIV/0! | 4150
| TCM.HCV.LS |  | 621.571 | 540 | 435 | 503.063 | 2099.634 | #DIV/0! | 1860
| CV (GAR) |  | 6622.8503 | 6584.6391 | 6652.3425 | 6632.675 | 6621.4869 | #DIV/0! | 6579.5619
| Sul < 0.7 |  | 0.66549 | 0.71333 | 0.7008 | 0.71402 | 0.69674 | #DIV/0! | 0.69985
| ASH < 5.0 |  | 4.2695 | 4.4867 | 4.039 | 3.9655 | 4.2048 | #DIV/0! | 4.0613
| IM |  | 6.5905 | 7.0667 | 6.3886 | 6.2 | 6.5776 |  | 6.6436
| TM |  | 11.3808 | 11.37 | 11.4207 | 11.5939 | 11.4373 | 34.7113 | 11.641
| TCM.HCV.HS |  | 209.91 | 260 | 270.456 | 360 | 1100.366 | 752.3431 | 2290
| CV (GAR) |  | 6513.0446 | 6506.6966 | 6510.7278 | 6371.9898 | 6464.8272 | 19840.0765 | 6418.8032
| Sul < 2.0 |  | 1.6532 | 1.5781 | 1.697 | 1.8067 | 1.6964 | 5.0002 | 1.7095
| ASH < 5.0 |  | 5.8644 | 5.3588 | 5.36 | 6.3356 | 5.7751 | 16.8392 | 5.2448
| IM |  | 6.3151 | 6.7931 | 6.6083 | 6.3024 | 6.4959 |  | 6.0611
| TM |  | 10.8849 | 11.2123 | 11.2666 | 11.8879 | 11.3842 | 33.7685 | 11.5066
| EBH.HCV.LS | [5 empty] | 0 | #REF! | 630
| CV (GAR) | [5 empty] | 6322 | #REF! | 6322
| Sul 0.6 | [5 empty] | 0.6 | #REF! | 0.6
| ASH | [5 empty] | 7 | #REF! | 7
| IM | [5 empty] | 12 |  | 12
| TM | [5 empty] | 14 | 0 | 14
| EBH 6000 | [5 empty] | 0 | 0 | 172.5
| CV (GAR) | [5 empty] | 6000 | 0 | 6000
| Sul 0.6 | [5 empty] | 0.6 | 0 | 0.6
| ASH 9.0 | [5 empty] | 9 | 0 | 9
| IM | [5 empty] | 12 |  | 12
| TM | [5 empty] | 14 | 0 | 14
| MBL 5800 | [5 empty] | 0 | #REF! | 172.5
| CV (GAR) | [5 empty] | 5800 | #REF! | 5800
| Sul 1.0 | [5 empty] | 1 | #REF! | 1
| ASH 6.0 | [5 empty] | 6 | #REF! | 6
| IM | [5 empty] | 13 |  | 13
| TM | [5 empty] | 19 |  | 19
| MBL.MCV.MS | [5 empty] | 0 | 0 | 540
| CV (GAR) | [5 empty] | 5400 | 0 | 5400
| Sul 1.2 | [5 empty] | 1 | 0 | 1
| ASH | [5 empty] | 6 | 0 | 6
| IM 14.00-15.00 | [5 empty] | 15 |  | 15
| TM 22.00-24.00 | [5 empty] | 24 |  | 24
| ROM Stock | 262.1758 | 114.2621 | 254.2621 | 299.6824 | 391.435 | 391.435 |  | 337
| FC Stock | 237.5474 | 89.1562 | 209.1562 | 249.0245 | 249.0245 | 249.0245 |  | 173.158
| JBG |  | Q1 | Q2 | Q3 | Q4 | Total |  | Total
| ROM Production |  | 0 | 0 | 129.3207 | 58.1793 | 187.5 | 129.3207 | 540
| JBG FC Product (Kton) |  | 0 | 0 | 129.321 | 58.1793 | 187.5003 | 129.321 | 537.0014
| Cv (GAR) |  | 0 | 0 | 4409.2556 | 4337.0536 | 4386.8521 | 3041.1113 | 4388.0437
| TS |  | 0 | 0 | 0.37772 | 0.37477 | 0.37681 | 0.26052 | 0.37887
| Ash |  | 0 | 0 | 4.4051 | 5.2255 | 4.6596 | 3.0382 | 4.7823
| IM |  | 0 | 0 | 16.9697 | 16.1664 | 16.7204 | 11.7042 | 16.3515
| TM |  | 0 | 0 | 30.1595 | 30.5019 | 30.2658 | 20.8014 | 30.2957
| Loading Barge | 0 | 0 | 0 | 124.1 | 58.4 | 182.5 |  | 525.6
| ROM Stock | 0 | 0 | 0 | 0 | 5.3821 | 5.3821 |  | 2.1596
| FC Stock | 1.37 | 1.37 | 1.37 | 13.4496 | 3.7995 | 3.7995 |  | 9.9078
ok | BEK |  | Q1 | Q2 | Q3 | Q4 | Total |  | Total
| ROM Production |  | 1696.3035 | 2105 | 2170 | 1500.6965 | 7472 |  | 8000
| FC Product (KTons) |  | 2220.249 | 2100 | 1700 | 1451.751 | 7472 |  | 8550
| BEK.HCV.LS |  | 1779.4983 | 1650 | 1550 | 1322.5017 | 6302 |  | 6950
| Cv (GAR) |  | 6245.9873 | 6269.0022 | 6282.0807 | 6313.4748 | 6275.053 | 4950.1432 | 6298.766
| TS |  | 0.50183 | 0.60116 | 0.59251 | 0.61098 | 0.57305 | 0.44483 | 0.6461
| Ash |  | 3.8447 | 4.8047 | 4.9073 | 5.1832 | 4.6383 | 3.5506 | 4.8026
| IM |  | 10.2532 | 11.1521 | 11.2539 | 12.1726 | 11.1375 | 8.583 | 11.7535
| TM |  | 15.0832 | 14.9068 | 14.9521 | 16.0996 | 15.2181 | 11.8395 | 15.5007
| BEK.HCV.HS |  | 440.7507 | 450 | 150 | 129.2493 | 1170 |  | 1600
| Cv (GAR) |  | 6164.4786 | 6221.7827 | 6266.2557 | 6361.0182 | 6221.2786 | 5518.5804 | 6238.6552
| TS |  | 1.5439 | 1.5477 | 1.5299 | 1.6405 | 1.5542 | 1.373 | 1.7954
| Ash |  | 4.7301 | 5.8901 | 6.3875 | 5.4252 | 5.4655 | 4.8662 | 5.8543
| IM |  | 9.7586 | 10.0782 | 10.0155 | 10.8841 | 10.0388 | 8.8364 | 11.07
| TM |  | 15.1608 | 14.1009 | 13.8344 | 14.7314 | 14.5357 | 12.9083 | 14.7103
| ROM Stock | 741.1791 | 204.1326 | 198.6076 | 657.7576 | 699.1996 | 699.1996 |  | 272.9037
| FC Stock | 105.7752 | 85.6889 | 275.1889 | 216.6889 | 94.3217 | 94.3217 |  | 46.8402
ok | GPK |  | Q1 | Q2 | Q3 | Q4 | Total |  | Total
| ROM Production |  | 555.5783 | 660 | 555.8537 | 728.568 | 2500 |  | 2999.7836
| FC Product (Kton) |  | 584.7116 | 660 | 530 | 725.2884 | 2500 |  | 3050
| Cv (GAR) |  | 3648.5477 | 3641.1815 | 3642.9685 | 3637.5999 | 3642.2441 | 2586.9205 | 3705.4628
| TS |  | 0.16258 | 0.13366 | 0.15707 | 0.17029 | 0.15601 | 0.10661 | 0.16234
| Ash |  | 9.4416 | 9.2019 | 9.1031 | 8.9709 | 9.17 | 6.5674 | 7.9479
| IM |  | 20.4836 | 25.9304 | 23.1501 | 23.2146 | 23.2792 | 16.5442 | 23.1657
| TM |  | 39.2738 | 38.5847 | 38.467 | 38.6221 | 38.7318 | 27.5269 | 39.0747
| FC Load/Ready Sale (Kton) |  | 573.5905 | 645 | 502.8415 | 778.568 | 2500 |  | 3040
| ROM Stock | 75.8604 | 55.0391 | 55.0391 | 80.8928 | 84.1724 | 84.1724 |  | 108.1839
| FC Stock | 2.4152 | 13.6034 | 28.6034 | 55.7619 | 2.4823 | 2.4823 |  | 77.4847
ok | TIS |  | Q1 | Q2 | Q3 | Q4 | Total |  | Total
| ROM Production |  | 77.0303 | 152 | 190.9127 | 186.057 | 606 |  | 606
| FC Product (Kton) |  | 100 | 239.6359 | 232.5 | 133.8641 | 706 |  | 706
| Cv (GAR) |  | 6566.6344 | 6574.7872 | 6595.9131 | 6595.782 | 6584.5704 | 5333.9497 | 6581.3066
| TS |  | 1.367 | 1.3276 | 1.2274 | 1.2277 | 1.2812 | 1.0485 | 1.2938
| Ash |  | 3.8123 | 3.7587 | 3.6189 | 3.6193 | 3.6938 | 3.0076 | 3.7107
| IM |  | 4.3642 | 4.4158 | 4.6019 | 4.6019 | 4.5051 | 3.6325 | 4.5095
| TM |  | 11.2575 | 11.2017 | 11.0552 | 11.0555 | 11.1336 | 9.0374 | 11.142
| FC Load/Ready Sale (Kton) |  | 100 | 239.6359 | 232.5 | 133.8641 | 706 |  | 606
| ROM Stock | 232.8047 | 206.2283 | 118.5924 | 77.0051 | 129.198 | 129.198 |  | 245
| FC Stock | 5.6505 | 75.3641 | 120 | 120 | 61.3641 | 61.3641 |  | 2
ok | NPR |  | Q1 | Q2 | Q3 | Q4 | Total |  | Total
| ROM Production |  | 125 | 0 | 109 | 230 | 464 |  | 1200
| FC Product (Kton) |  | 0 | 90 | 144 | 230 | 464 |  | 1030
| NPR.MCV.LS |  | 0 | 28 | 42 | 73 | 143
| Cv (GAR) |  | 0 | 5966.6772 | 5793.1027 | 5630.8086 | 5744.2399
| TS |  | 0 | 0.53967 | 0.54724 | 0.58749 | 0.5663
| Ash |  | 0 | 0.69697 | 2.7615 | 4.7855 | 3.3905
| IM |  | 0 | 0.99267 | 4.2698 | 8.3038 | 5.6874
| TM |  | 0 | 1.5658 | 6.4527 | 12.2481 | 8.4543
| NPR.MCV.HS |  | 0 | 62 | 102 | 157 | 321 |  | 1030
| Cv (GAR) |  | 0 | 5901.1352 | 5896.6186 | 5838.0709 | 5868.8555 | 2974.6018 | 5938.1343
| TS |  | 0 | 1.446 | 1.4761 | 1.4868 | 1.4755 | 0.73856 | 1.1917
| Ash |  | 0 | 1.1574 | 3.5464 | 5.6352 | 4.1066 | 1.3251 | 6.8257
| IM |  | 0 | 1.684 | 4.9561 | 7.854 | 5.7415 | 1.8648 | 10.9698
| TM |  | 0 | 2.4966 | 7.3832 | 11.7041 | 8.5527 | 2.7756 | 16.3194
| FC Load/barges (Kton) |  | 0 | 90 | 144 | 230 | 464 |  | 950
| ROM Stock | 0 | 150 | 45 | 0 | 0 | 0 |  | 170
| FC Stock | 0 | 0 | 0 | 0 | 0 | 0 |  | 80
| ITM GRAND TOTAL | EO Y25 | Q1 | Q2 | Q3 | Q4 | TOTAL |  | TOTAL
| ROM Production |  | 4719.0494 | 5589.5 | 5821.4633 | 4777.0552 | 20907.0679 |  | 24395.7836
| FC Production |  | 5325.2316 | 5657.1359 | 5398.777 | 4626.3558 | 21007.5003 |  | 25223.0014
| FC + EBH + MBL |  | 4493.7506 | 4857.1359 | 4693.321 | 3763.2928 | 14044.2075 |  | 24993.5014
| ROM Stock | 1313.6205 | 752.464 | 694.303 | 1138.1397 | 1315.7177 | 1315.7177 |  | 1161.2106
| FC Stock | 573.1649 | 394.6544 | 763.7903 | 784.3968 | 559.8693 | 559.8693 |  | 570.0322
Notes :
Note on B45: Belfry Parulian Pandiangan: Exclude High ash stock and exclude fine coal stock
Note on B46: Belfry Parulian Pandiangan: MSY + PSY

## IMM 2026 (hidden)
IMM 2026 Production Plan - 3rd Draft Year 2026
Draft file | 3rd Draft Year 2026 - 06102025 email
Draft date | 2025-10-06
2026
Mine | Unit | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Total
IMM
OB removal | KBCM | 7278.9114 | 7191.9895 | 6917.5858 | 7591.9796 | 8045.8787 | 8267.2976 | 8829.1259 | 8278.0262 | 8165.9184 | 8327.5806 | 8033.5402 | 7829.0241 | 94756.8582
ROM production | Kton | 540 | 540 | 540 | 570 | 580 | 580 | 640 | 640 | 640 | 600 | 590 | 590 | 7050
FC production | Kton | 552.5 | 552.5 | 552.5 | 582.5 | 592.5 | 592.5 | 652.5 | 652.5 | 652.5 | 612.5 | 602.5 | 602.5 | 7200
SR (OB:ROM) | BCM/Ton | 13.4795 | 13.3185 | 12.8103 | 13.3193 | 13.8722 | 14.254 | 13.7955 | 12.9344 | 12.7592 | 13.8793 | 13.6162 | 13.2695 | 13.4407
SR (OB:FC) | BCM/Ton | 13.1745 | 13.0172 | 12.5205 | 13.0334 | 13.5795 | 13.9532 | 13.5312 | 12.6866 | 12.5148 | 13.5961 | 13.3337 | 12.9942 | 13.1607
Product type
IMM WB HCV LS | KTon | 19.7652 | 40.887 | 8.6458 | 42.4554 | 63.253 | 70.2032 | 61.5971 | 66.2817 | 54.3778 | 47.9284 | 46.9529 | 34.5784 | 556.926
CV (ADB) | Kcal/kg | 6540.6071 | 6599.799 | 6533.8681 | 6553.8963 | 6512.1268 | 6570.2896 | 6696.1858 | 6686.0597 | 6661.3431 | 6633.4716 | 6579.8963 | 6629.219 | 6609.4807
CV (GAR) | Kcal/kg | 6185.7613 | 6242.0577 | 6179.6193 | 6198.5097 | 6158.7142 | 6207.2217 | 6326.4467 | 6317.1149 | 6292.5657 | 6267.5638 | 6216.1242 | 6262.1079 | 6246.3652
TS | % | 0.96343 | 0.95376 | 0.98836 | 0.94674 | 0.95663 | 0.94961 | 0.94917 | 0.95253 | 0.95139 | 0.95201 | 0.95249 | 0.95485 | 0.95283
Ash | % | 7.4869 | 7.72 | 6.4867 | 8.1279 | 8.1079 | 8.7446 | 7.3198 | 7.5903 | 7.3409 | 8.3554 | 8.0488 | 7.5559 | 7.8724
IM | % | 7.1804 | 7.0985 | 7.1198 | 7.1334 | 7.2098 | 8.8708 | 8.8003 | 8.7422 | 9.0383 | 8.7085 | 8.9142 | 9.0661 | 8.3275
TM | % | 12.2162 | 12.1342 | 12.1555 | 12.1691 | 12.2456 | 13.9065 | 13.8361 | 13.7779 | 14.074 | 13.7442 | 13.9499 | 14.1018 | 13.3632
IMM WB HCV HS | KTon | 70.2348 | 49.113 | 81.3542 | 67.5446 | 51.747 | 24.7968 | 8.4029 | 3.7183 | 15.6222 | 12.0716 | 3.0471 | 15.4216 | 403.074
CV (ADB) | Kcal/kg | 6196.8822 | 5974.955 | 6080.6896 | 6004.2734 | 5910.796 | 6032.2442 | 6347.0877 | 6318.3446 | 6379.8939 | 6294.9862 | 6285.9633 | 6291.2997 | 6085.8259
CV (GAR) | Kcal/kg | 5862.4321 | 5653.8402 | 5753.1387 | 5680.3098 | 5592.7758 | 5702.2197 | 5997.9103 | 5970.6562 | 6028.9986 | 5947.8531 | 5939.7078 | 5944.3828 | 5756.5194
TS | % | 2.5994 | 2.7903 | 2.9004 | 2.8113 | 2.8487 | 2.7973 | 3.6212 | 3.8902 | 3.844 | 2.8893 | 2.988 | 2.9103 | 2.8681
Ash | % | 12.8158 | 16.2642 | 14.3304 | 16.2359 | 18.5937 | 18.3405 | 11.0887 | 11.48 | 11.3134 | 11.8746 | 11.6784 | 11.8853 | 15.0175
IM | % | 6.6954 | 6.3009 | 6.5165 | 6.6691 | 6.4051 | 7.9563 | 8.4645 | 8.4888 | 8.4419 | 8.6813 | 8.581 | 8.6779 | 6.9178
TM | % | 11.7311 | 11.3366 | 11.5522 | 11.7048 | 11.4408 | 12.9921 | 13.5002 | 13.5245 | 13.4776 | 13.717 | 13.6168 | 13.7136 | 11.9535
IMM EB MCV MS | KTon | 86.2678 | 90.7357 | 69.782 | 36.3896 | 22.322 | 0 | 53.8986 | 44.1227 | 19.6545 | 31.3492 | 49.115 | 0 | 503.637
CV (ADB) | Kcal/kg | 6291.3037 | 6281.2361 | 6296.6677 | 6274.3264 | 6272.446 | 0 | 6295.1524 | 6251.8388 | 6261.1058 | 6242.9172 | 6284.8689 | 0 | 6280.3072
CV (GAR) | Kcal/kg | 5939.1407 | 5929.8904 | 5946.6418 | 5925.5088 | 5922.6742 | 0 | 5943.8456 | 5902.0646 | 5910.9357 | 5894.1166 | 5933.8515 | 0 | 5929.635
TS | % | 1.5696 | 1.5561 | 1.5754 | 1.5815 | 1.5564 | 0 | 1.562 | 1.5793 | 1.5835 | 1.5894 | 1.5867 | 0 | 1.5717
Ash | % | 5.3343 | 5.6469 | 5.5875 | 6.2467 | 6.7027 | 0 | 6.3381 | 6.5503 | 6.4982 | 6.7274 | 6.7147 | 0 | 6.033
Moist | % | 10.6763 | 10.6117 | 10.0543 | 10.0629 | 10.3352 | 0 | 10.4038 | 10.6304 | 10.5991 | 10.5088 | 10.4764 | 0 | 10.4529
TM | % | 15.6763 | 15.6117 | 15.0543 | 15.0629 | 15.3352 | 0 | 15.4038 | 15.6304 | 15.5991 | 15.5088 | 15.4764 | 0 | 15.4529
IMM EB MCV HS | KTon | 188.3405 | 207.803 | 243.016 | 238.1434 | 216.8705 | 264.4668 | 297.16 | 286.8131 | 295.6967 | 290.0925 | 282.8961 | 322.6096 | 3133.9082
CV (ADB) | Kcal/kg | 6307.8679 | 6318.723 | 6328.3709 | 6332.5832 | 6340.6568 | 6320.1727 | 6337.7513 | 6333.172 | 6330.4925 | 6329.8811 | 6329.2355 | 6326.6 | 6328.542
CV (GAR) | Kcal/kg | 5954.7459 | 5965.9884 | 5974.3483 | 5978.7543 | 5987.4033 | 5967.7931 | 5984.2843 | 5979.6645 | 5977.1191 | 5976.7143 | 5975.6796 | 5972.9269 | 5975.184
TS | % | 2.1033 | 2.0794 | 2.106 | 2.0797 | 2.1018 | 2.041 | 2.0936 | 2.0722 | 2.0724 | 2.0745 | 2.0812 | 2.0051 | 2.0733
Ash | % | 5.2675 | 5.7306 | 5.7078 | 6.1784 | 6.0706 | 5.8867 | 5.41 | 5.4327 | 5.3539 | 5.6253 | 5.5025 | 5.4681 | 5.6212
IM | % | 10.6843 | 10.4323 | 10.6219 | 10.5135 | 10.2535 | 10.3215 | 10.3487 | 10.4238 | 10.4277 | 10.384 | 10.4917 | 10.5586 | 10.4514
TM | % | 15.6843 | 15.4323 | 15.6219 | 15.5135 | 15.2535 | 15.3215 | 15.3487 | 15.4238 | 15.4277 | 15.384 | 15.4917 | 15.5586 | 15.4514
IMM EB MCV HS Extreme | KTon | 175.3917 | 151.4614 | 137.2021 | 185.467 | 225.8076 | 220.5332 | 218.9414 | 239.0642 | 254.6487 | 218.5584 | 207.9889 | 217.3904 | 2452.4549
CV (ADB) | Kcal/kg | 6148.5002 | 6173.599 | 6202.7068 | 6180.7394 | 6183.0394 | 6227.9223 | 6220.8693 | 6193.1781 | 6232.0558 | 6198.2125 | 6181.8434 | 6165.5065 | 6194.1004
CV (GAR) | Kcal/kg | 5804.5031 | 5828.3378 | 5856.0221 | 5835.7259 | 5837.7986 | 5880.3397 | 5873.6546 | 5847.3026 | 5884.2023 | 5852.5492 | 5837.1079 | 5821.8616 | 5848.3104
TS | % | 2.8038 | 2.8031 | 2.7996 | 2.8042 | 2.7971 | 2.7967 | 2.7997 | 2.8 | 2.8045 | 2.8023 | 2.7992 | 2.8041 | 2.8011
Ash | % | 7.1177 | 7.0099 | 7.1283 | 7.8817 | 7.4269 | 6.6138 | 6.8481 | 6.8499 | 6.6995 | 6.9582 | 7.991 | 8.0177 | 7.1986
IM | % | 10.6315 | 10.5952 | 10.5426 | 10.4276 | 10.4532 | 10.4109 | 10.4175 | 10.471 | 10.4213 | 10.3432 | 10.3393 | 10.2925 | 10.4355
TM | % | 15.6315 | 15.5952 | 15.5426 | 15.4276 | 15.4532 | 15.4109 | 15.4175 | 15.471 | 15.4213 | 15.3432 | 15.3393 | 15.2925 | 15.4355
FINE COAL | KTon | 12.5 | 12.5 | 12.5 | 12.5 | 12.5 | 12.5 | 12.5 | 12.5 | 12.5 | 12.5 | 12.5 | 12.5 | 150
CV (ADB) | Kcal/kg | 3500 | 3500 | 3500 | 3500 | 3500 | 3500 | 3500 | 3500 | 3500 | 3500 | 3500 | 3500 | 3500
CV (GAR) | Kcal/kg | 3146.0674 | 3146.0674 | 3146.0674 | 3146.0674 | 3146.0674 | 3146.0674 | 3146.0674 | 3146.0674 | 3146.0674 | 3146.0674 | 3146.0674 | 3146.0674 | 3146.0674
TS | % | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Ash | % | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40
IM | % | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11
TM | % | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20

## TCM 2026 (hidden)
TCM 2026 Production Plan - 3rd Draft
Draft file | TCM Production Plan 2026 V2.1 (12Nov2025)
Draft date | 2025-11-12
2026
Mine | Unit | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Total
TCM
OB removal | KBCM | 4460.2274 | 4205 | 4555 | 4385 | 4650 | 4470 | 5270 | 5370 | 5025 | 4770 | 4520 | 4550 | 56230.2274
ROM production | Kton | 295 | 310 | 310 | 345 | 345 | 325 | 335 | 360 | 360 | 335 | 335 | 345 | 4000
FC production | Kton | 315 | 315 | 320 | 340 | 340 | 355 | 370 | 360 | 360 | 360 | 360 | 355 | 4150
SR (OB:ROM) | BCM/Ton | 15.1194 | 13.5645 | 14.6935 | 12.7101 | 13.4783 | 13.7538 | 15.7313 | 14.9167 | 13.9583 | 14.2388 | 13.4925 | 13.1884 | 14.0576
SR (OB:FC) | BCM/Ton | 14.1595 | 13.3492 | 14.2344 | 12.8971 | 13.6765 | 12.5915 | 14.2432 | 14.9167 | 13.9583 | 13.25 | 12.5556 | 12.8169 | 13.5495
Product type
TCM HCV LS | KTon | 135 | 135 | 155 | 155 | 150 | 155 | 180 | 180 | 165 | 160 | 150 | 140 | 1860
CV (ADB) | Kcal/kg | 6899.6893 | 6920.7047 | 6837.7175 | 6917.4437 | 6892.5354 | 6971.4711 | 7003.1728 | 7005.1293 | 7007.1105 | 6998.8988 | 7011.1861 | 6916.9893 | 6951.5104
CV (GAR) | Kcal/kg | 6529.6002 | 6484.1141 | 6415.3978 | 6587.1279 | 6569.0123 | 6636.1617 | 6675.1555 | 6679.1831 | 6649.7936 | 6595.7552 | 6589.9319 | 6478.4124 | 6579.5619
TS | % | 0.68755 | 0.71 | 0.69563 | 0.70243 | 0.70005 | 0.68477 | 0.69275 | 0.69235 | 0.71329 | 0.70972 | 0.70872 | 0.70233 | 0.69985
Ash | % | 5.0644 | 4.1285 | 4.1179 | 4.0782 | 3.776 | 3.5886 | 3.6674 | 3.7151 | 3.9734 | 4.0788 | 4.4404 | 4.406 | 4.0613
IM | % | 6.8108 | 6.7009 | 6.5955 | 6.8115 | 7.0371 | 6.6783 | 6.7257 | 6.6636 | 6.3524 | 6.5119 | 6.5288 | 6.3199 | 6.6436
TM | % | 11.8093 | 12.5866 | 12.3645 | 11.2614 | 11.4006 | 11.1669 | 11.0945 | 11.0065 | 11.1278 | 11.8969 | 12.1449 | 12.2598 | 11.641
TCM HCV HS | KTon | 180 | 180 | 165 | 185 | 190 | 200 | 190 | 180 | 195 | 200 | 210 | 215 | 2290
CV (ADB) | Kcal/kg | 6831.0594 | 6787.6404 | 6607.3791 | 6808.4607 | 6651.0595 | 6757.1673 | 6719.965 | 6854.352 | 6906.7639 | 6974.3517 | 6887.8564 | 6925.1341 | 6813.9315
CV (GAR) | Kcal/kg | 6427.165 | 6390.3493 | 6188.2399 | 6464.2998 | 6297.0369 | 6382.9009 | 6344.5985 | 6480.6564 | 6513.9313 | 6537.8449 | 6460.6686 | 6490.3103 | 6418.8032
TS | % | 1.7105 | 1.7265 | 1.7199 | 1.7165 | 1.7058 | 1.7295 | 1.7326 | 1.7013 | 1.7048 | 1.6902 | 1.6911 | 1.6919 | 1.7095
Ash | % | 6.2953 | 5.3064 | 5.9444 | 5.9167 | 5.8241 | 5.5182 | 5.1805 | 5.0706 | 4.6713 | 4.3764 | 4.7373 | 4.4585 | 5.2448
IM | % | 6.0941 | 6.6617 | 6.309 | 6.3027 | 6.0411 | 6.0133 | 5.8094 | 5.9958 | 5.8182 | 5.7405 | 5.9763 | 6.0728 | 6.0611
TM | % | 11.6464 | 12.125 | 12.2523 | 11.039 | 11.0423 | 11.2191 | 11.0708 | 11.1208 | 11.1749 | 11.6399 | 11.8077 | 11.9704 | 11.5066
TCM.LCV.MS.HA | KTon | [12 empty] | 0 | 0%
CV (ADB) | Kcal/kg | [12 empty] | 0
CV (GAR) | Kcal/kg | [12 empty] | 0
TS | % | [12 empty] | 0
Ash | % | [12 empty] | 0
IM | % | [12 empty] | 0
TM | % | [12 empty] | 0

## BEK 2026 (hidden)
BEK 2026 Production Plan - 3rd Draft
Draft file | 00. BEK Inpit and Oupit Production Outlook 2026_ver3.1_14Nov25 2
Draft date | 2025-11-14
2026
Mine | Unit | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Total
BEK
OB removal | KBCM | 6100 | 6000 | 5855 | 5715 | 6175 | 6515 | 6470 | 6520 | 6430 | 6320 | 6100 | 5550 | 73750
ROM production | Kton | 608 | 629 | 640 | 690 | 728 | 691 | 694 | 684 | 675 | 649 | 653 | 659 | 8000
FC production | Kton | 750 | 750 | 750 | 700 | 700 | 700 | 700 | 700 | 700 | 700 | 700 | 700 | 8550
SR (OB:ROM) | BCM/Ton | 10.0329 | 9.539 | 9.1484 | 8.2826 | 8.4821 | 9.4284 | 9.3228 | 9.5322 | 9.5259 | 9.7381 | 9.3415 | 8.4219 | 9.2188
SR (OB:FC) | BCM/Ton | 8.1333 | 8 | 7.8067 | 8.1643 | 8.8214 | 9.3071 | 9.2429 | 9.3143 | 9.1857 | 9.0286 | 8.7143 | 7.9286 | 8.6257
Product type
BEK HCV LS | KTon | 600 | 600 | 600 | 550 | 550 | 550 | 550 | 550 | 600 | 600 | 600 | 600 | 6950
CV (ADB) | Kcal/kg | 6546.3768 | 6636.2496 | 6584.799 | 6600.3086 | 6582.908 | 6572.5469 | 6587.4001 | 6563.5803 | 6585.674 | 6559.4074 | 6561.7665 | 6557.6262 | 6578.1077
CV (GAR) | Kcal/kg | 6264.7702 | 6366.1668 | 6315.2782 | 6326.9628 | 6311.7855 | 6288.5495 | 6311.2116 | 6296.4522 | 6303.7302 | 6276.9466 | 6261.5006 | 6265.265 | 6298.766
TS | % | 0.64727 | 0.64905 | 0.65099 | 0.64972 | 0.65267 | 0.64443 | 0.63964 | 0.64734 | 0.63583 | 0.6448 | 0.64567 | 0.64605 | 0.6461
Ash | % | 4.2503 | 4.3586 | 4.4704 | 4.3907 | 4.6847 | 4.9756 | 4.9018 | 4.8795 | 4.92 | 5.1281 | 5.4966 | 5.1603 | 4.8026
IM | % | 12.0445 | 12.0974 | 12.3202 | 11.3202 | 11.1149 | 10.9477 | 10.7564 | 11.3639 | 11.0233 | 12.3428 | 12.5098 | 12.9282 | 11.7535
TM | % | 15.8281 | 15.6749 | 15.909 | 14.9928 | 14.7757 | 14.7957 | 14.4981 | 14.9713 | 14.8326 | 16.1175 | 16.5134 | 16.8101 | 15.5007
BEK HCV HS | KTon | 150 | 150 | 150 | 150 | 150 | 150 | 150 | 150 | 100 | 100 | 100 | 100 | 1600
CV (ADB) | Kcal/kg | 6442.8814 | 6460.0661 | 6481.067 | 6484.342 | 6505.1692 | 6510.9098 | 6539.8709 | 6542.0612 | 6564.8917 | 6524.361 | 6515.4282 | 6524.8995 | 6504.9457
CV (GAR) | Kcal/kg | 6205.3096 | 6215.2676 | 6231.9274 | 6214.3876 | 6227.4727 | 6233.4515 | 6264.8459 | 6277.7554 | 6299.8944 | 6247.2875 | 6228.7076 | 6236.9676 | 6238.6552
TS | % | 1.7867 | 1.805 | 1.7771 | 1.796 | 1.7897 | 1.8007 | 1.7937 | 1.8076 | 1.7912 | 1.7909 | 1.8111 | 1.7978 | 1.7954
Ash | % | 5.2989 | 5.4699 | 5.3637 | 5.964 | 6.2634 | 5.9378 | 6.5507 | 6.2561 | 5.8254 | 5.562 | 5.9453 | 5.6793 | 5.8543
IM | % | 11.5831 | 11.9002 | 12.0712 | 10.9161 | 10.3238 | 10.3935 | 10.2324 | 10.1988 | 10.043 | 11.4426 | 12.0459 | 12.1594 | 11.07
TM | % | 14.8434 | 15.2387 | 15.4513 | 14.6248 | 14.1519 | 14.212 | 14.0075 | 13.8269 | 13.6742 | 15.2034 | 15.9164 | 16.0357 | 14.7103

## JBG 2026 (hidden)
JBG 2026 Production Plan - 4th draft
Draft file | JBG Production Budget 2026 vol 540 kton delay Q1
Draft date | 2025-11-13
2026
Mine | Unit | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Total
JBG
OB removal | KBCM | 0 | 0 | 0 | 385.02 | 431.76 | 438.8 | 397.3426 | 407.6855 | 424.9956 | 373.5057 | 275.8702 | 272.7869 | 3407.7664
ROM production | Kton | 0 | 0 | 0 | 17.0014 | 47.7589 | 56.9904 | 62.7299 | 65.7948 | 65.6452 | 68.5839 | 73.2824 | 82.213 | 540
FC production | Kton | 0 | 0 | 0 | 17.0014 | 42 | 51 | 57 | 61 | 75 | 76 | 68 | 90 | 537.0014
SR (OB:ROM) | BCM/Ton | 0 | 0 | 0 | 22.6463 | 9.0404 | 7.6995 | 6.3342 | 6.1963 | 6.4741 | 5.446 | 3.7645 | 3.3181 | 6.3107
SR (OB:FC) | BCM/Ton | 0 | 0 | 0 | 22.6463 | 10.28 | 8.6039 | 6.9709 | 6.6834 | 5.6666 | 4.9145 | 4.0569 | 3.031 | 6.3459
Product type
JBG | KTon | 0 | 0 | 0 | 17.0014 | 42 | 51 | 57 | 61 | 75 | 76 | 68 | 90 | 537.0014
CV (ADB) | Kcal/kg | 0 | 0 | 0 | 5226.6633 | 5248.9062 | 5245.3183 | 5265.0651 | 5259.7429 | 5270.8172 | 5268.0635 | 5273.5105 | 5285.5215 | 5265.8311
CV (GAR) | Kcal/kg | 0 | 0 | 0 | 4427.0304 | 4406.8414 | 4375.3671 | 4380.1093 | 4374.844 | 4382.0122 | 4363.6088 | 4390.8153 | 4416.6275 | 4388.0437
TS | % | 0 | 0 | 0 | 0.43114 | 0.37511 | 0.41066 | 0.35762 | 0.39549 | 0.38603 | 0.35792 | 0.37763 | 0.3676 | 0.37887
Ash | % | 0 | 0 | 0 | 4.5108 | 4.7038 | 5.1035 | 4.8289 | 5.1567 | 4.4385 | 5.2357 | 4.7735 | 4.3152 | 4.7823
IM | % | 0 | 0 | 0 | 17.0442 | 16.8401 | 16.4796 | 16.3935 | 16.0625 | 16.4958 | 16.0693 | 16.1706 | 16.3439 | 16.3515
TM | % | 0 | 0 | 0 | 29.7357 | 30.1812 | 30.3317 | 30.4462 | 30.1842 | 30.5769 | 30.479 | 30.2022 | 30.0963 | 30.2957

## GPK 2026 (hidden)
GPK 2026 Production Plan - 3rd Draft
Draft file | GPK Production Plan 2026 V.2.2 (07Nov'25)
Draft date | 2025-11-07
2026
Mine | 2026 | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Total
GPK
OB Removal | KBCM | 885 | 865 | 960 | 995 | 1010 | 1020 | 1095 | 1075 | 1100 | 980 | 935 | 930 | 11850
ROM Production | Kton | 250 | 255 | 260 | 270 | 275 | 275.9836 | 160 | 160 | 163.8 | 315 | 305 | 310 | 2999.7836
FC Production | Kton | 260 | 250 | 260 | 245 | 260 | 265 | 185 | 120 | 170 | 330 | 350 | 355 | 3050
SR (OB:ROM) | BCM/Ton | 3.54 | 3.3922 | 3.6923 | 3.6852 | 3.6727 | 3.6959 | 6.8438 | 6.7188 | 6.7155 | 3.1111 | 3.0656 | 3 | 3.9503
SR (OB:FC) | BCM/Ton | 3.4038 | 3.46 | 3.6923 | 4.0612 | 3.8846 | 3.8491 | 5.9189 | 8.9583 | 6.4706 | 2.9697 | 2.6714 | 2.6197 | 3.8852
Product type
GPK LCV LS | Kton | 260 | 250 | 260 | 245 | 260 | 265 | 185 | 120 | 170 | 330 | 350 | 355 | 3050
CV (ADB) | Kcal/Kg | 4770.1759 | 4742.3833 | 4818.1328 | 4798.2429 | 4559.4768 | 4450.7984 | 4437.1869 | 4582.5717 | 4711.2582 | 4729.886 | 4716.6099 | 4669.154 | 4675.4029
CV (GAR) | Kcal/Kg | 3724.8809 | 3688.5448 | 3676.8865 | 3673.9664 | 3716.5386 | 3700.7556 | 3707.7905 | 3688.589 | 3694.5508 | 3712.381 | 3731.6255 | 3718.7143 | 3705.4628
TS | % | 0.18179 | 0.18669 | 0.16322 | 0.14651 | 0.13547 | 0.13636 | 0.13401 | 0.15388 | 0.17218 | 0.17942 | 0.17146 | 0.16834 | 0.16234
Ash | % | 9.388 | 8.8626 | 9.0061 | 8.4064 | 6.9974 | 7.4694 | 7.5488 | 8.1964 | 8.3453 | 7.8427 | 7.1573 | 7.0215 | 7.9479
IM | % | 21.0636 | 21.4313 | 20.2216 | 20.926 | 25.4713 | 26.6715 | 27.0634 | 24.3135 | 22.4043 | 22.4713 | 23.236 | 23.8446 | 23.1657
TM | % | 38.3472 | 38.8963 | 39.1224 | 39.4835 | 39.2119 | 38.95 | 38.9795 | 39.0412 | 39.1369 | 39.0943 | 39.1997 | 39.2979 | 39.0747

## TIS 2026 (hidden)
TIS 2026 Production Plan - 3rd Draft
Draft file | Draft TIS Production Plan 2026 V2.1 Budget (06Nov2025)
Draft date | 2025-11-06
2026
Mine | Unit | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Total
TIS
OB removal | KBCM | 826.8543 | 802.1218 | 916.4338 | 915.9519 | 899.7411 | 932.4502 | 922.3351 | 1003.9594 | 997.0772 | 948.7772 | 922.5112 | 911.787 | 11000
ROM production | Kton | 21 | 29 | 40 | 42 | 45 | 55 | 55 | 66 | 66 | 66 | 61 | 60 | 606
FC production | Kton | 84.4444 | 81.1111 | 84.4444 | 50 | 50 | 50 | 56 | 50 | 50 | 50 | 50 | 50 | 706
SR (OB:ROM) | BCM/Ton | 39.374 | 27.6594 | 22.9108 | 21.8084 | 19.9942 | 16.9536 | 16.7697 | 15.2115 | 15.1072 | 14.3754 | 15.1231 | 15.1964 | 18.1518
SR (OB:FC) | BCM/Ton | 9.7917 | 9.8892 | 10.8525 | 18.319 | 17.9948 | 18.649 | 16.4703 | 20.0792 | 19.9415 | 18.9755 | 18.4502 | 18.2357 | 15.5807
Product type
TIS.HCV.MS | KTon | 84.4444 | 81.1111 | 84.4444 | 50 | 50 | 50 | 56 | 50 | 50 | 50 | 50 | 50 | 706
CV (ADB) | Kcal/kg | 7049.1108 | 7077.3289 | 7077.499 | 7077.5532 | 7077.6255 | 7074.5186 | 7074.5665 | 7074.5001 | 7073.9411 | 7073.8395 | 7073.4997 | 7075.9736 | 7072.5383
CV (GAR) | Kcal/kg | 6567.8688 | 6567.8367 | 6570.7504 | 6571.6791 | 6572.9175 | 6572.8651 | 6596.0462 | 6595.9616 | 6595.2498 | 6595.1204 | 6594.6875 | 6597.8381 | 6581.3066
TS | % | 1.3299 | 1.3629 | 1.3414 | 1.3345 | 1.3254 | 1.3739 | 1.2233 | 1.2249 | 1.2382 | 1.2406 | 1.2487 | 1.1898 | 1.2938
Ash | % | 3.7601 | 3.8064 | 3.78 | 3.7716 | 3.7604 | 3.8055 | 3.6147 | 3.6163 | 3.6302 | 3.6328 | 3.6412 | 3.5797 | 3.7107
IM | % | 4.6116 | 4.3675 | 4.376 | 4.3788 | 4.3824 | 4.4856 | 4.597 | 4.5988 | 4.6139 | 4.6167 | 4.6259 | 4.5589 | 4.5095
TM | % | 11.1237 | 11.252 | 11.2227 | 11.2134 | 11.2009 | 11.2586 | 11.05 | 11.052 | 11.0687 | 11.0717 | 11.0818 | 11.008 | 11.142
TIS.HCV.LS | KTon | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CV (ADB) | Kcal/kg | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CV (GAR) | Kcal/kg | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TS | % | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Ash | % | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
IM | % | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TM | % | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## NPR 2026 (hidden)
NPR 2026 Production Plan - 3rd Draft
Draft file | NPR Production Plan Yearly 2026_R4
Draft date | 2025-11-10
2026
Mine | Unit | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Total
NPR
OB removal | KBCM | 735 | 650 | 750 | 930 | 885 | 1025 | 1100 | 1100 | 1070 | 1000 | 880 | 975 | 11100
ROM production | KTon | 55 | 55 | 50 | 110 | 100 | 120 | 130 | 130 | 120 | 120 | 100 | 110 | 1200
FC production | KTon | 70 | 65 | 70 | 70 | 90 | 100 | 105 | 110 | 105 | 86 | 75 | 84 | 1030
SR (OB:ROM) | BCM/Ton | 13.3636 | 11.8182 | 15 | 8.4545 | 8.85 | 8.5417 | 8.4615 | 8.4615 | 8.9167 | 8.3333 | 8.8 | 8.8636 | 9.25
SR (OB:FC) | BCM/Ton | 10.5 | 10 | 10.7143 | 13.2857 | 9.8333 | 10.25 | 10.4762 | 10 | 10.1905 | 11.6279 | 11.7333 | 11.6071 | 10.7767
Product type
MCV-MS | Ton | 70 | 65 | 70 | 70 | 90 | 100 | 105 | 110 | 105 | 86 | 75 | 84 | 1030
CV (ADB) | Kcal/kg | 6353.0052 | 6348.4814 | 6350.7866 | 6361.6769 | 6357.5273 | 6281.0781 | 6256.904 | 6272.6938 | 6272.0337 | 6331.9142 | 6320.0492 | 6377.1072 | 6317.7471
CV (GAR) | Kcal/kg | 5970.1335 | 5967.3194 | 5968.2395 | 5983.8038 | 5978.4091 | 5897.2627 | 5881.2012 | 5898.1685 | 5896.597 | 5950.7582 | 5937.0834 | 5994.6818 | 5938.1343
TS | % | 1.2358 | 1.304 | 1.2592 | 1.2368 | 1.3062 | 1.1601 | 1.229 | 1.1412 | 1.1426 | 1.0985 | 1.1246 | 1.1252 | 1.1917
Ash | % | 6.5705 | 6.6145 | 6.5319 | 6.4632 | 6.5518 | 7.2795 | 7.3881 | 7.1842 | 7.2228 | 6.6387 | 6.757 | 6.0862 | 6.8257
IM | % | 10.989 | 10.8767 | 10.8954 | 10.9292 | 10.8661 | 11.0319 | 11.0827 | 11.0764 | 11.0552 | 10.9467 | 10.9237 | 10.8366 | 10.9698
TM | % | 16.3534 | 16.2277 | 16.2627 | 16.2198 | 16.1814 | 16.4684 | 16.4219 | 16.3858 | 16.3793 | 16.3074 | 16.3214 | 16.1836 | 16.3194
MCV-HS | Ton | [12 empty] | 0
CV (ADB) | Kcal/kg | [12 empty] | 0
CV (GAR) | Kcal/kg | [12 empty] | 0
TS | % | [12 empty] | 0
Ash | % | [12 empty] | 0
IM | % | [12 empty] | 0
TM | % | [12 empty] | 0